**Board Memo**

**DATE:** 11/9/2023

**AGENDA ITEM DETAILS:**

**School/Department**

Ryle High School

**Product Vendor or Grant Issuer**

Change Order

**Product or Grant Name**

Change Order #1 for Paving 2023, BG 23-342

**Date/Term (Beginning and End Dates/Year)**

9/25/2023

**APPLICABLE BOARD POLICY & STRATEGIC PLAN GOAL:**

05.1  
Goal 4E: Boone County Schools will provide safe, clean, learner ready facilities. 1. Prioritize the district facilities plan to ensure alignment with the desired state as directed by the strategic plan.

**DESCRIBE USE OF CONTRACT/PURCHASE/AGREEMENT**

This change order includes the following:

Proposal 1 – This Change Order is for rebuilding three catch basins in addition to the ones that were included in the bidding documents.

ADD - $24,000.00  
Proposal 2 – This Change Order is a credit for adjusting the allowance which did not need to be fully utilized.  
DEDUCT - $14,608.00

**FUNDING FOR PURCHASES AND OTHER REQUESTS:**

**Total Cost**

$9,392.00

**Funding Source**

Capital Outlay

**\*If more than one funding source, list below along with amount or percent for each source**

N/A

**IF THIS IS A GRANT, ENTER AMOUNT TO BE AWARDED:**

Click or tap here to enter text.

**RECOMMENDATION:**

I recommend the Board approve the Change Order #1 for Paving 2023, BG 23-342, as presented.

**CONTACT PERSON: (submitter)**

Kim Best, Assistant Superintendent of Operations