| Strategy |  | Person Responsible | Dates | I, IP NI | Outcomes/Report | Scores | Dates of Review |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Math Teachers (3) will attend the Math content regional meeting, and Instructional Support Leadership Network on rolling out the new math standards | Through the standard deconstruction process, teachers will develop learning targets. This will allow student learning to be more self-directed. Training of staff will occur with collaboration of math coaches | Ray Spahn, Bonnie Humphries, Brenda Alexander, Kim Jones, Tony Jury | 9/1/2011-6/30/2011 | IP | Math teachers are attending all regional meetings |  | Math 7/29 /10 9/ 15/10 10/20/10 11/17/10 1/19/11 ISLN 8/25/10 9/21/10 10/26/10 11/16/10 |
| District will remain in collaboration with monthly meetings with Carroll County on improving math instruction and rolling out standards | Through the standard deconstruction process, teachers will develop learning targets. This will allow student learning to be more self-directed. Training of staff will occur with collaboration of math coaches | Dot Perkins | 9/1/2011-9/1/2012 | IP | In progress on going |  | 10/18/10 11/4/10 12/9/10 |
| District will continue to provide Math coaches grades K-8 | Through collaboration, cognitive coaching conversations, and consulting regarding math resources, coaches will aid teachers in planning and reflecting on unit development with new math core content standards | Deb Foltz | 7/1/2010-12/20/2011 | IP | Coaches hired for the 2010/2011 school year |  | 5/1/11 |
| The district will continue to use a diagnostic evaluation of student academic progress at set intervals at a minimum 3 times during the school year prior to KCCT assessment. Common Assessments/Learning Checks will be used at each grade/subject level to monitor student progress with adjustments being made in instruction as necessary to ensure student success | School will report diagnostic assessment to Assistant Superintendent after each assessment. A plan will then be developed to further improve instruction and learning in gap areas. The effectiveness of the plan will be determined by the number of students meeting the goal of the district and the school of 70% proficiency. | Ray Spahn | 9/1/2010-9/1/2012 | IP | All schools testing students at this time | Goal = 70 |  |
| Math coaches and regular content teachers will collaborate with fellow teachers to develop and implement activities which help improve student achievement in gap areas. This will be done by closely monitoring Math skills especially in gap areas | Math coach will meet with the building principal after each math assessment to determine a plan for improvement gap areas and to determine the goals that have been met. After the plan is developed, the Math Coach will meet with the Assistant Superintendent to discuss goals and plan for improvement. | Bonnie Humphries Brenda Alexander Kim Jones | 9/1/2010-9/1/2012 |  | Met with assistant superintendent on 2/2/11printed out the missed items on Think Link. Teams are addressing these as part of their math planning & instruction. Would you need a copy of these missed items for documentation purposes? I would be glad to send them to you. |  | 2/2/11 following ITBS & Think Link |
| Coaches and math teachers will research interventions for RTI that are research-based that will be consistent throughout the district and will allow data to be tracked and show signs of math improvement especially in gap areas by implementing new math standards | Professional development will be provided for all teachers regarding data analysis and next steps for instruction. | Bonnie Humphries Brenda Alexander Kim Jones | 1/1/2011-9/1/2012 |  | Neither of these have data tracking models. AIMS web is one of those data tracking models which we discussed with Principal Brown. The Math Intervention Program used in most OVEC districts is Number Worlds and comes highly supported at KCM. The program would require having a Numeracy assessment for students in early primary. We are looking at training all LE teachers on May 31 & June1. |  | MAP? SNAP Attended 2 sessions at OVEC 11/19/10 |
| The district will purchase math textbooks or resource materials for all students once new standards are finalized and textbook companies have incorporated those standards. Book should provide research-based strategies | To improve math instruction and meet the goal of 70% proficiency | Ray Spahn, principals and SBDM councils | 5/30/2011-9/1/2011 |  | This will be done once standards are complete by the state department |  | 3/30/11 |

We are training all staff to use numeracy assessment SNAP to monitor progress of student numeracy growth.

# Text boxes

April 2011

MATH