DECISION PAPER

TO: MEMBEERS OF THE NELSON COUNTY BOARD OF EDUCATION

FROM: Charles Thompson, Director of Construction

CC: Anthony Orr, Superintendent

SUBJECT: Change Order #42 for Thomas Nelson High School

DATE: June 21, 2011

ISSUE: During construction an unsupported edge was discovered. An angle was installed, according to engineer’s direction, to support decking and brick. BCD, Inc. proposes to provide all labor and materials for a cost of $307.33.

RECOMMENDATION: Approval of Change order #42 for Thomas Nelson High School.

RECOMMENDED MOTION: I move that the Nelson County Board of Education approve Change Order #42 for Thomas Nelson High School.