DECISION PAPER

TO: MEMBERS OF THE NELSON COUNTY OARD OF EDUCATION

FROM: Charles Thompson, Director of Construction

CC: Anthony Orr, Superintendent

SUBJECT: Change Order #13 for Nelson County High School athletic renovation

DATE: June 11, 2011

ISSUE: Certain catch basins were changed from a grated lid and frame to a solid lid and frame. The change in fixture required an additional cost of $877.25 from Claunch Construction.

RECOMMENDDATION: Approval of Change Order #13 for Nelson County High School athletic renovation.

RECOMMENDED MOTION: I move that the Nelson County Board of Education approve Change Order #13 for Nelson County High School athletic renovation.