|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Strategy**PARENTAL INVOLVMENT |  | **Person Responsible** | **Dates** | **I, IP NI** | **Outcomes/Report** | **Scores** | **Dates of Review** |
| Schools will use a volunteer sign-up at registration and the beginning of the year for parents to help out in schoolsMarch 2011 | Increase parental involvement in school if there is a list of volunteers. | Kerri Alexander | 9/1/2010-6/30/2012 |  | **Volunteer forms were given out at Ready Fest, Open House and sent home with children the 1st week of school. Approx. 160 for the LE, and 98 for the UE** |  |  |
| Schools will keep an email list and send correspondence to parents regarding academic and other pertinent information related to school functions | To keep parents informed of school events | Kerri Alexander | 9/1/2010-6/30/2012 |  | **Each school in the district has a parent email distribution list to send out information to parents. There is also a Parent Involvement distribution list for the district, and a Facebook page. Parent Involvement Website is being created.** |  |  |
| The district will continue to purchase and use the automated phone system that can contact parents automatically and deliver messages as needed at a moment's notice. | Provide an avenue to keep parents informed but also a safe school module to inform parents. | Kerri Alexander | 9/1/2010-6/30/2012 |  | **This has been purchase-district looking for a new system since the current one went down twice** |  |  |
| District wide PT3's meeting (Parents, Teachers talking together) will be held quarterly. | To provide dialogue between teachers and parents. To help parents get involved in their child's education. | Kerri Alexander | 9/1/2010-6/30/2012 |  | **Upper Elementary PT3-completed on 3-24-11****Middle School PT3- completed 4-28-11****Elementary and High school will be 11-12 school year** |  |  |
| Monthly district parental involvement meetings will be held. | To help plan needs of the school in volunteering. | Kerri Alexander | 9/1/2010-6/30/2012 |  | **Next District Parent Engagement Informational Breakfast will be 09-07-2011 in the Middle School Library from 8:30-9:30.**  |  |  |
| Each school will have at least 2 activities that focus on parental information regarding career and colleges. Whether it deals with saving, curriculum, enrollment etc., it will focus on students and parents being educated in allowing students to make a successful transition to adult life. | Provide key information at appropriate grade levels to help parents plan for making a successful transition to adult life. | Kerri Alexander | 9/1/2010-6/30/2012 |  | **February we are collaborating with Beth Oldendick for Dr. Seuss Birthday. We will be having a Birthday party for Dr. Seuss and children will read a book to their parents, and show them how to take a quiz for SRC points. We will show parents the reading level of their child and books appropriate for their reading level** | **Postponed due to schedule conflict**  |  |
| The district will provide and maintain the Parent Involvement Coordinator. | To coordinate and provide assistance to schools in relation to parent involvement. | Kerri Alexander | 9/1/2010-6/30/2012 |  | **District has provided this** |  |  |
| In order to bring parents into schools, the Upper and Lower Elementary will have a Doughnuts with Dad, and Muffins with Mom assemblies. | An avenue to bring dads and moms into school and provide them with a successful experience with school. | Kerri Alexander | 9/1/2010-6/30/2012 |  | **Due to construction and parking issues. These have been canceled for the 10-11 school year. Will have in 11-12 school year** |  |  |
| There will be a parent night for 2nd, 5th and 8th grade students to ease the transition into their new school. | To ease the transition to the next level for both student and parent. | Kerri Alexander | 9/1/2010-6/30/2012 |  | **TBA-working w/ principals to coordinate date for beginning of 11-12 school year , possibly during open house** |  |  |
| The Middle School will sponsor a Father/Daughter dance and a Mother/Son activity. | An avenue to bring dads and moms into school and provide them with a successful experience with school. | Michelle Cruey Jamie Swartzel | 8/1/2010-6/30/2011 |  |  |  |  |
| By February the Parent Involvement Coordinator will survey parents to determine barriers and to establish new goals for improving parental involvement throughout the schools | To provide feedback to better understand the needs of school parents. |   | 2/1/2011-3/1/2011 |  | **Survey is created and available on district site and parent involvement page. The surveys were also made available to all parents at UE & MS PT3, MS report card night. UE and MS arts and Humanities night** |  |  |