## THOMAS NELSON PHASE 2
NO. | CONTRACTOR | ADD | DEDUCT | COMMENTS | BOE Approval Date
1 | Tennis Technologies |  | 31355 | The track is being changed from half-inch red to three-eights black. This is an initial deduction. | 2011-01-18
2 | California Products |  | 5000 | Track specs were changed which resulted in a materials credit of $5000. | 2011-02-15
3 | Stephens Pipe and Steel |  | 4000 | After a review of fence specifications it was determined the quality was in excess of what is needed. | 2011-02-15
4 | Stephens Pipe and Sreel |  | 44839 | Fencing for TNHS was revised from vinyl coated to galvanized. | 2011-02-15
5 | M and J Construction | 993.25 |  | Unsuitable soil was removed and back filled with #3 stone | 2011-03-15
6 | TWF, Inc. | 1335.84 |  | Additional steel supports were required to ensure roof stability. | 2011-03-15
7 | Professional Fence | 1472 |  | Two additional gates were installed at the baseball and softball fields to allow access to the fields from dugouts. | 2011-03-15
8 | M&J Construction | 195 |  | A section of unsuitable soil was removed | 2011-04-19
9 | TWF, Inc. | 2950 |  | Additional steel supports were welded between bar joists to improve deck stability. TWF Inc can provide all labor and materials for a cost of $2950
10 | Atlas Enterprise |  | 5300 | After review of casework the solid surface vanities in four bathrooms was deleted
11 | Atlas Enterprise |  | 625 | After rev iew of casework the solid surface vaniities in four bathrooms were elimimated. A labor deletion was realized.
| TOTAL | 6946.09 | 91119
| CONTINGENCY | 236355 | 320527.91 | PERCENT CONT REMAINING | 135.6%

## NCHS ATHLETICS
NO. | CONTRACTOR | ADD | DEDUCT | COMMENTS | BOE Approval Date
2 | Re-Tel Products | 1700 |  | With the change in track surfacing an ultimate deduct of $19,000 will be realized. However, some materials costs will increase. | 2011-01-18
5 | Stephens Pipe and Steel | 4100 |  | Fence specification was changed to light commercial from residential. Upgrade resulted in a materials add of $4100. | 2011-02-15
6 | BCD, Inc. | 1509.36 |  | Blocking was added to softball building to make purlins 2' on center rather than 32" on center. Stability will be increased. | 2011-02-15
3 | California Products |  | 13500 | With the change in track surface some vendor costs for materials will change. A $13,500 materials deduct from California Products will occur. | 2011-03-15
8 | Claunch Construction | 3891 |  | Rock excavation for storm drainage. | 2011-03-15
1 | Advanced Polymer | 14800 |  | With the change in track surfacing an ultimate deduct of $19,000 will be realized. However, some materials costs will increase. Advanced Polymer will provide black latex for a cost listed. | 2011-03-15
7 | Knight's Mchanical | 170.96 |  | A discrepancy between plumbing plans and architectural drawings. Knight's willcharge only for materials and absorb labor. | 2011-03-15
9 | BCD,INC | 360.49 |  | An above ceiling access panel for future maintenance in restroom building
10 | Claunch Construction | 2529 |  | Rock removal while installing storm drains. | 2011-04-19
11 | Hawkins |  | 410 | Changes in drainage systems for athletic field resulted in credit given. | 2011-05-17
12 | Claunch Construction | 300 |  | Resolved conflict of existing sewer and gas lines with new storm drain lines | 2011-05-17
13 | Claunch Construction | 877.25 |  | Grated lids and frames were changed to solid
4 | Mei Products |  | 22000 | The track surface was changed from a half inch red to three-eights black. This change order reflects cost savings for red rubber.
| TOTAL | 30238.06 | 35910
| CONTINGENCY | 93874 | 99545.94 | PERCENT CONT REMAINING | 106%

## F HEIGHTS PHASE 2
NO. | CONTRACTOR | ADD | DEDUCT | COMMENTS | BOE Approval Date
1 | Cundiff Steel | 1384 |  | A safety rail was added to ships ladder accessing mechanical mezzanine
3 | Atlas Metal |  | 1115 | After review of submittals it was determined that more marker boards and projection screens were ordered than needed
4 | The Johnson Group | 3334.99 | after | After reviewing shop drawings it was seen that bulbs could not be changed in lobby casework. A change in electrical fixture was required.
5 | BCD. Inc. | 1440.44 |  | Windows in the warehouse were wood rather than metal framed
6 | Cundiff Steel |  | 1910 | Windows in the warehouse were wood rather than metal framed. This resulted in a materials cost reduction.
7 | R7R Inc | 1704 |  | Mixing valves were installed to maintain required water temperature
8 | Joe Filiatreau Flooring |  | 2915.83 | Carpet was changed to VCT at owner's request
| TOTAL | 6479.43 | 5940.83
| CONTINGENCY | 133446 | 132907.4 | PERCENT CONT REMAINING | 99.6%

## PRESCHOOL
NO. | CONTRACTOR | ADD | DEDUCT | COMMENTS | BOE Approval Date
1 | BCD, Inc | 7265.78 |  | Removal of six support walls and installation of supports in preparation for steel beams. | 2011-03-15
2 | R&R Inc | 932 |  | Cost for materials and labor to house 4 HVAC units in metal
3 | Cundiff Steel |  | 1389 | A credit of $1594 was realized due to an inclusion incorrectly of structural steel for canopies. Also included was a $205 add for lengthening of steel columns. A final credit of $1,389 was realized.
4 | R&R Inc |  | 1262 | A credit of $1594 was realized due to an inclusion incorrectly of structural steel for canopies. Also included was a $205 add for lengthening of steel columns. A final credit of $1,389 was realized.
| TOTAL | 8197.78 | 2651
| CONTINGENCY | 112159 | 106612.22 | PERCENT CONT REMAINING | 95.05%

## THOMAS NELSON PHASE 1
NO. | CONTRACTOR | ADD | DEDUCT | COMMENTS | BOE Approval Date
31 | Badgett |  | 1071 | In various locations bar joists were added and reduced as determined by the structural engineer with a final credit resulting for labor. | 2011-01-18
32 | Vulcraft |  | 1299 | In various locations bar joists were added and reduced as determined by the structural engineer. A credit of $1,299 from Vulcraft for materials is realized. | 2011-01-18
33 | M&J Construction | 3920 |  | The field house foundation must rest on either all rock or all soil. With 75% rock the remaining 25% must be rock filled. | 2011-01-18
35 | Kalkreuth Roofing |  | 664.32 | An exterior wall at TNHS in Phase I becomes an interior wall in Phase II. With wall status change a credit for metal siding was realized. | 2011-01-18
36 | Fox Painting | 714 |  | Labor and materials to Fox Painting to finish wall that was revised from exterior to an interior wall.
38 | Knight's Mechanical | 9161.04 |  | Change order has two separate issues. An additional $2600.00 is charged for rock removal. The second issue is also Knight's Mechanical for pipe installation. Installation of science room piping has been completed now in order to avoid future wall demolition for a cost of $6,561.04. This is a shifting of costs among Phases. | 2011-01-18
17 | Knight's Mechanical | 3830.48 |  | A test well originally drilled was found to be unacceptable and replaced. | 2011-01-18
28 | Kelsey Construction | 197605.9 |  | Extensive rock removal for foundation trench and site work. | 2011-04-19
41 | BCD, Inc. | 2433.25 |  | Finish an exposed foundation wall in a classroom to match other three walls. | 2011-04-19
42 | BCD, Inc. | 307.33 |  | An unsupported roof edge received additional welded angles
| TOTAL | 217972 | 3034.32
| CONTINGENCY | 889601.48 | 674663.8 | PERCENT | 75.84%
NO. | CONTRACTOR | ADD | DEDUCT | COMMENTS | BOE Approval Date