DECISION PAPER

TO: MEMBERS OF THE NELSON COUNTY BOARD OF EDUCATION

FROM: Charles Thompson, Director of Construction

CC: Anthony Orr, Superintendent

SUBJECT: Change Order #15 for Nelson County High School Athletic facilities renovation

DATE: September 20, 2011

ISSUE: Poor soil conditions were found at three separate locations at the athletic complex. The condition of the soil and size of each area was confirmed by Greenbaum Geotechnical Services. All areas were excavated with the poor soil being replaced with compacted DGA. Claunch Construction will provide all labor and materials for a cost of $51,041.95.

RECOMMENDATION: Approve Change Order #15 for Nelson County High School athletic facilities renovation.

RECOMMENDED MOTION: I move that the Nelson County Board of Education approve Change Order #15 for Nelson County High School athletic renovation.