Elizabethtown Independent schools

ComprehENsive SCHOOL IMprovement Plan

Helmwood Heights Elementary

ASSURANCE CERTIFICATION

2011-2012

REVISED 11-2011

Will continue to revise after Advance Ed report is complete.

###### This plan will be submitted to the Elizabethtown Independent School Board of Education at the regularly scheduled meeting Nov.21, 2011.

I certify that to the best of my knowledge, the information contained in this application is correct and complete and that the agency named in this application has authorized me, as its representative, to obligate this agency to conduct any ensuing program or activity in accordance with all applicable Federal and State laws, regulations and specific program assurances contained in the Kentucky Comprehensive Improvement Planning Guidebook.  It is understood that this application, once posted to our local district server for public access constitutes an offer, and if accepted by the Kentucky Department of Education or negotiated to acceptance, will form a binding agreement.

Superintendent:  Mr. Gary French, Superintendent

Principal: Ms. Michelle Hart

Most Recent Implementation and Impact Check:  May 20, 2011

Name of  School: Helmwood Heights Elementary

CSIP Team:   Michelle Hart, Carla Kuhn, Debra Metcalf, Leah Gardner, Saimi Rabbini, Bobby Trowbridge

LOCAL PROGRAM CONTACTS

### Comprehensive District Improvement Plan for 2010-2011

| FEDERAL GRANT PROGRAMS | LOCAL CONTACT EMAIL | LOCALTELEPHONE |
| --- | --- | --- |
| NCLB, Title I: Part A (Improving Basic Programs) | Kelly.graham@etown.kyschools.us | 270.765.6146 |
| NCLB, Title 1: Part B (Even Start Continuation) | N/A |  |
| NCLB, Title I: Part C (Education of Migratory Children) | Kelly.graham@etown.kyschools.us | 270.765.6146 |
| NCLB, Title I: Part D (Neglected and Delinquent) | N/A |  |
| NCLB, Title II: Part A (High Quality Teachers and Principals) | Kelly.graham@etown.kyschools.us | 270.765.6146 |
| NCLB, Title II: Part D (Education Technology) | Mike.selvitelle@etown.kyschools.us | 270.765.6146 |
| Individuals with Disabilities Education Act (IDEA) Basic | Debbie.curry@etown.kyschools.us | 270.769.2359 |
| Individuals with Disabilities Education Act (IDEA) Preschool | Debbie.curry@etown.kyschools.us | 270.769.2359 |
| McKinney –Vento Homeless Education Act (NCLB Title X Part B) | N/A |  |
| Carl D. Perkins Vocational and Technical Education Act- Basic | Karen.branham@etown.kyschools.us | 270.765.6146 |
| Extended School Services | Debbie.curry@etown.kyschools.us | 270.769.2359 |
| Gifted and Talented Education (GT Services Plan is available at EIS Central Office) | Kelly.graham@etown.kyschools.us | 270.765.6146 |
| State Preschool Program | Debbie.curry@etown.kyschools.us | 270.769.2359 |
| Kentucky Education Technology System (EIS Master Plan for Technology Education is available at EIS Central Office) | Mike.selvitelle@etown.kyschools.us | 270.765.6146 |
| Textbooks | Karen.branham@etown.kyschools.us | 270.765.6146 |
| Professional Development | Karen.branham@etown.kyschools.us | 270.765.6146 |

SCHOOL IMPROVEMENT PLAN

EXECUTIVE SUMMARY

###### School Mission Statement

Building on the Past, Learning in the Present, Preparing for the Future

###### School Vision Statement

A community where students come first and learning never ends.

The district mission and vision statements were created by the staff through the course of several meetings and examinations of what our direct purpose is with our students, parents and community.  The school mission and vision statements are to be reviewed every time a new Comprehensive School Improvement Plan is created.

The Elizabethtown Independent School Board of Education has both policies and procedures in place to address the Comprehensive District Improvement Plan (CDIP) and Comprehensive School Improvement Plans (CSIP).  These are reviewed annually.

The 2011-2012 Comprehensive District Improvement Plan and Comprehensive School Improvement Plans have four major components.  They are as follows:  Interventions for Students below Proficiency; College and Career Readiness; Family and Community Partnerships; Ensuring A Quality Teacher in Every Classroom. These components are based on findings and outcomes of the District Strategic Planning Committee composed of EIS faculty, staff, board member, parents, and community members.  Data included in the CDIP and CSIPs is based on state and federal accountability systems.  At the regularly scheduled November 14, 2011 Board Meeting, an Implementation and Impact Report on the CDIP and CSIPs will be reviewed with all Board Members.

Needs Assessment

The school uses a variety of resources such as the Standards and Indicators for School Improvement, KCCT Results, as well as the NCLB Goals to form their plan.  The school conducts a data review using IOWA, NCLB, and KCCT data.  Other assessments such as Scantron, GRADE (Group Reading Assessment and Diagnostic Evaluation) and AimsWeb may also be used for benchmarking and progress monitoring.  Additionally, schools and the district may complete surveys of parents, students, teachers, and administrators to gain additional information.

Goals and Strategies

The measurable goals developed for the CSIP are currently based on KCCT and NCLB data. These measurable student achievement goals will allow Elizabethtown Independent Schools to move toward an overall proficiency rate of 100%.  The goals and strategies will focus on providing interventions for targeted students, improving college and career readiness, building family and community partnerships, building professional learning communities, unpacking core standards, analyzing common assessment data, and a culture of continuous improvement.

Evaluation

Implementation of the CSIP strategies and activities will be monitored continuously for effectiveness by all stakeholders, and an Implementation and Impact Check will be completed in May, 2012.  Adjustments to the plan may occur at any time the CDIP or CSIP Committee deems appropriate and necessary.

Stakeholders

Members of the Comprehensive School Improvement Planning Committee, which include parents, teachers, administrators, and community members developed and reviewed the draft 2011-2012 CSIP on November 14, 2011.  In addition, the general public was invited to give input at CSIP Committee meetings, as evident from notices of this opportunity in the News Enterprise.

The general public will be able to view the CSIP at the school office, the Board of Education, as well as on the district website located at www.etown.k12.ky.us.  Notice of these opportunities will be posted in the News Enterprise.

The final version of the CSIP will be submitted to the Elizabethtown Independent Board of Education at the regularly scheduled meeting in November 21, 2011 after SBDM Council approval on November 14, 2011.

ACTION COMPONENT   Interventions for Students below Proficiency

District Name	Elizabethtown Independent Schools		Component Manager  	Jill Valentine

Date  			 November  2011					   Public

| Priority Needs | Measurable Goals |
| --- | --- |
| Based on our 2011 NCLB Report, some students are scoring below proficient levels in Reading and Math. Reading - % Students reaching Proficiency at each school (10-11) Helmwood Heights Elementary – 75% Math - % Students reaching Proficiency at each school Helmwood Heights Elementary – 66% | AP-R1. Based on the 2012 KCCT, the 2012 NCLB Scores will show a 3 percentage point increase in student proficiency for all students in the areas of Reading and Math. Reading - % Students that will reach Proficiency at each school (11-12) Helmwood Heights Elementary – 78% Math - % Students reaching Proficiency at each school Helmwood Heights Elementary – 69% |

ACTION COMPONENT   Interventions for Students below Proficiency

District Name	Elizabethtown Independent Schools		Component Manager  	Jill Valentine

Date  			November  2011					   Public

## Strategies/Activities (Activity or Strategic Sequence of Activities to Achieve Objectives)

| Objective Label/Strategy/Activity | Senate Bill 1 NCLB Connection | Expected Impact in Terms of Student Performance & Classroom Practice | Responsible Person | Start/End Date | Resources Needed/Funding Source | I IP NI | Outcomes/Report of Progress |
| --- | --- | --- | --- | --- | --- | --- | --- |
| The school will imbed Reading and Math Interventions in the master schedule during the regular school day for targeted students below proficiency. | BOTH | NCLB Scores will show a 5 percentage point increase in student proficiency for all students in the areas of Reading and Math. | Principal C.O. | September, 2010- On going | Salary for Interventionist | I | 30 minutes after Reading and Math |
| The school will implement a K-12 progress monitoring system to universally screen all students and routinely monitor the progress of targeted students performing below proficiency in Reading and Math. | BOTH | NCLB Scores will show a 5 percentage point increase in student proficiency for all students in the areas of Reading and Math. Progress monitoring system will be fully functional in each school. | District Principal Counselor Teachers Interventionist | July, 2011- June, 2012 | Cost of Universal Screening System | IP | Not yet available for K,1 Administered to 2nd through 5th grade |
| The school will work with the district to explore and expand services to meet the affective needs of targeted students who may need Alternative Educational Settings. | BOTH | NCLB Scores will show a 5 percentage point increase in student proficiency for all students in the areas of Reading and Math. | District Principal Counselor | July, 2011- June, 2012 | Service Costs | IP | Still working with outside sources to secure assistance. |
| The school will work with the district to develop and implement a Summer Reading Intervention Program for targeted students in local neighborhoods and backyards. | NCLB | NCLB Scores will show a 5 percentage point increase in student proficiency for all students in the areas of Reading and Math. | District Principal Teachers Parents FRYSC | April, 2011- July, 2012 | Stipends for Teachers Materials | I | Program implemented in summer, progress is still being monitored. |

ACTION COMPONENT   Interventions for Students below Proficiency

District Name	Elizabethtown Independent Schools		Component Manager  	Jill Valentine

Date  			 November 2011					   Public

| Objective Label/Strategy/Activity | Senate Bill 1 NCLB Connection | Expected Impact in Terms of Student Performance & Classroom Practice | Responsible Person | Start/End Date | Resources Needed/Funding Source | I IP NI | Outcomes/Report of Progress |
| --- | --- | --- | --- | --- | --- | --- | --- |
| The school will work with the district to plan and conduct home visits for targeted students with an intentional plan for communication: Tell me about your child How can I help your child? Let me show you where your child is currently performing | BOTH | NCLB Scores will show a 5 percentage point increase in student proficiency for all students in the areas of Reading and Math. At least 90% of targeted students’ homes will be visited across the district making successful face to face contact with the parent or guardian. | All Staff | July, 2011- Aug, 2012 | Staff Compensation | IP | Only a couple of teachers have had home visits. Conferences and parent contacts happen throughout the year. |
| The school will work with the district to develop and implement a systematic pyramid of interventions for targeted students that is communicated to and followed by all stakeholders. | BOTH | A fluid system of interventions will be in place at each school and will be communicated to all stakeholders. | All Staff Central Office | February, 2011- June, 2012 | Interventionist for Reading and Math | I | System is in place. Small refinements are occurring. |

ACTION COMPONENT  College and Career Readiness

District Name	Elizabethtown Independent Schools		Component Manager  	Betty Clemons

Date  			 November  2011					   Public

| Priority Needs | Measureable Goals |
| --- | --- |
| Based on our 2010 -2011 EPAS Data from TK Stone and Elizabethtown High School, the content area scores and composite scores for the EXPLORE, PLAN and ACT are as follows: EXPLORE English – 15.2 Math – 15.2 Reading – 15.2 Science – 16.8 OR Composite – 15.7 PLAN English – 17.6 Math – 18.1 Reading – 18.1 Science – 18.8 OR Composite – 18.3 ACT English – 20.9 Math – 20.2 Reading – 21.4 Science - 20.8 OR Composite – 20.9 | AP-M1. Based on results of the EPAS assessments, the 2011-2012 EPAS College Readiness Data from TK Stone and Elizabethtown High School will improve .3 points in each content area or Composite Score as follows: EXPLORE English – 15.5 Math – 15.5 Reading – 15.5 Science – 17.1 OR Composite – 16.0 PLAN English – 17.9 Math – 18.4 Reading – 18.4 Science – 19.1 OR Composite – 18.7 ACT English – 21.2 Math – 20.5 Reading – 21.7 Science - 21.1 OR Composite – 21.2 |

ACTION COMPONENT  College and Career Readiness

District Name	Elizabethtown Independent Schools		Component Manager  	Betty Clemons

Date  			November  2011					   Public

## Strategies/Activities (Activity or Strategic Sequence of Activities to Achieve Objectives)

| Objective Label/Strategy/Activity | Senate Bill 1 NCLB Connection | Expected Impact in Terms of Student Performance & Classroom Practice | Responsible Person | Start/End Date | Resources Needed/Funding Source | I IP NI | Outcomes/Report of Progress |
| --- | --- | --- | --- | --- | --- | --- | --- |
| The school will work with the district to develop and implement an EIS K-12 system of Keys to College Readiness | SB 1 | EPAS College Readiness Data from TK Stone and Elizabethtown High School will improve .5 points in each content area or Composite Score. | All Staff | April, 2011- June, 2012 |  | NI | We be developed later in year. |
| Each grade level will participate in at least 3community partner field trips/visits per year. | SB 1 | Students will have awareness of different types of Careers and the skills needed to perform in specific Career fields. | All K-5 teachers | Sept, 2011- May 2012 | Transportation Funding | IP | On-going, KLUE has started in 4th grade |

ACTION COMPONENT  Family and Community Partnerships

District Name	Elizabethtown Independent Schools		Component Manager  	Carol Ann Christian

Date  			November  2011					   Public

| Based on the 2010-2011 KCCT and NCLB Reports, Helmwood showed the following Achievement Gaps in the Percentage of Students scoring Proficient and Distinguished in Reading and Math: Helmwood Elementary School – Reading: African American Students – N/A Free and Reduced Lunch – 63% Students with Disabilities – 45% Helmwood Elementary School – Math: African American Students – 58% Free and Reduced Lunch – 53% Students with Disabilities – 32% | AP-M1. Based on results of the 2011-2012 KCCT and NCLB Reports, Helmwood will show a 3 percentage point increase in the Percentage of Students scoring Proficient and Distinguished for Achievement Gap students in the areas of Reading and Math as follows: Helmwood Elementary School – Reading: African American Students – N/A Free and Reduced Lunch – 66% Students with Disabilities – 48% Helmwood Elementary School – Math: African American Students –61 % Free and Reduced Lunch – 56% Students with Disabilities – 35% |
| --- | --- |

ACTION COMPONENT  Family and Community Partnerships

District Name	Elizabethtown Independent Schools		Component Manager  	Carol Ann Christian

Date  			November  2011					   Public

## Strategies/Activities (Activity or Strategic Sequence of Activities to Achieve Objectives)

| Objective Label/Strategy/Activity | Senate Bill 1 NCLB Connection | Expected Impact in Terms of Student Performance & Classroom Practice | Responsible Person | Start/End Date | Resources Needed/Funding Source | I IP NI | Outcomes/Report of Progress |
| --- | --- | --- | --- | --- | --- | --- | --- |
| The school will work with the district to develop and implement an ongoing system for community meetings to communicate student achievement data as well as school and district goals for improving teaching and learning. | BOTH | Each school will show a 10 percentage point increase in the Percentage of Students scoring Proficient and Distinguished for Achievement Gap students in the areas of Reading and Math. | FRYSC CO Principals Faculty Staff Community | February, 2011- On Going | Title 1 Community Sponsors | NI | No meetings set yet. |
| The school will work with the district to develop and implement a Name and Claim/Student Mentoring Program for targeted achievement gap students that will include staff members and may include community members serving as mentors to the students. | BOTH | Each school will show a 10 percentage point increase in the Percentage of Students scoring Proficient and Distinguished for Achievement Gap students in the areas of Reading and Math. | FRYSC CO Principals Faculty Staff Community | February, 2011- June, 2012 | Title 1 funds Community Sponsors | NI | No system in place. |

ACTION COMPONENT   Ensuring a Quality Teacher in Every Classroom

District Name	Elizabethtown Independent Schools		Component Manager  	Dana McCurry

Date  		November 2011						   Public

| Priority Need | Measureable Goals |
| --- | --- |
| Based on our 2011 NCLB Report, some students are scoring below proficient levels in Reading and Math. Reading - % Students reaching Proficiency at each school (10-11) Helmwood Heights Elementary – 75% Math - % Students reaching Proficiency at each school Helmwood Heights Elementary – 66% | AP-R1. Based on the 2012 K-PREP, the 2012 NCLB Scores will show a 3 percentage point increase in student proficiency for all students in the areas of Reading and Math. Reading - % Students that will reach Proficiency at each school (11-12) Helmwood Heights Elementary – 78% Math - % Students reaching Proficiency at each school Helmwood Heights Elementary – 69% |

ACTION COMPONENT   Ensuring a Quality Teacher in Every Classroom

District Name	Elizabethtown Independent Schools		Component Manager  	Dana McCurry

Date  		November 2011					   Public

## Strategies/Activities (Activity or Strategic Sequence of Activities to Achieve Objectives)

| Objective Label/Strategy/Activity | Senate Bill 1 NCLB Connection | Expected Impact in Terms of Student Performance & Classroom Practice | Responsible Person | Start/End Date | Resources Needed/Funding Source | I IP NI | Outcomes/Report of Progress |
| --- | --- | --- | --- | --- | --- | --- | --- |
| The school will work with the district to develop and implement PLC Teams that can effectively do the following: Unpack standards into daily learning targets or “I Can Statements” Develop and implement daily formative assessments to match “I Can Statements” Develop and implement a system of balanced formative and summative assessments Develop and implement congruent common assessments for monthly instructional units Develop and implement a system for common assessment data analysis to identify students needing additional time and support for mastering common core standards | SB 1 | NCLB Scores will show a 5 percentage point increase in student proficiency for all students in the areas of Reading and Math. Each EIS Teacher will have a PLC Binder with the following up to date finished products for each instructional unit that are produced as a result of PLC Team work: Unpacked/Deconstructed Standards Monthly Pacing Calendars Numerous Daily Formative Assessments Common Assessment for Unit (administered at least once every four weeks) Data disaggregation from Common Assessment Plans for Interventions/ Enrichment | Principal Teachers Interventionist C.O. | June, 2011- On Going | Measurable Assessments Professional Development - Formative Asses - Performance Calculator - Unpacking | IP IP | Math/ELA deconstructed, I can statements in place, formative assessments math learning target. Common assessments are being developed and used for monthly units. Data analysis is a learning process for staff, still need pd. |

ACTION COMPONENT   Ensuring a Quality Teacher in Every Classroom

District Name	Elizabethtown Independent Schools		Component Manager  	Dana McCurry

Date  		November 2011						   Public

## Strategies/Activities (Activity or Strategic Sequence of Activities to Achieve Objectives)

| Objective Label/Strategy/Activity | Senate Bill 1 NCLB Connection | Expected Impact in Terms of Student Performance & Classroom Practice | Responsible Person | Start/End Date | Resources Needed/Funding Source | I IP NI | Outcomes/Report of Progress |
| --- | --- | --- | --- | --- | --- | --- | --- |
| HHES will work with the district to provide all teachers with differentiation training so that teachers are effectively equipped to teach students who are heterogeneously grouped. | SB 1 | NCLB Scores will show a 5 percentage point increase in student proficiency for all students in the areas of Reading and Math. EHS teachers will be proficient at differentiated instruction in order to successfully meet the needs of heterogeneous classes. | Principal C.O. | June, 2011- June, 2012 | Professional Development -Differentiation for Special Needs - Inclusion | IP | Training is set for November for lead teachers to take back to staff. |
| The school will work with the district to develop an ongoing system for continuous improvement of teaching and learning by conducting walk-throughs and/or instructional rounds in each school. | SB 1 | NCLB Scores will show a 5 percentage point increase in student proficiency for all students in the areas of Reading and Math. All schools will be involved in ongoing district walk-throughs or instructional rounds to receive instructional feedback for the purpose of improvement. | Administration Teachers | February, 2011- On Going | Substitutes | I | Walkthroughs occurred last year and are coming this year. |