Gallatin County High School

330 Day Plan and

CSIP

Mission Statement:  Maximizing Student Learning and Achievement to Make All Students college and career ready

Needs Assessment:  Our faculty analyzed test scores from NCLB, KCCT, EXPLORE, PLAN, and ACT

Goals:  NCLB, PLAN, ACT, results were used to address high needs and to set and obtain goals.

evaluation:  Data will consistently be analyzed by conducting ePREP assessments, THINK LINK, and Benchmark assessments.  students needing help will be identified and interventions will take place during scheduled daily RTI.

stakeholders: All teachers, building  administrators, and sbdm council will analyze the data.  highly qualified teachers will provide the interventions.

gaps:  There were gaps in reading with male and female as well as free and reduced lunch.  Teachers will introduce and utilize more non fiction reading into their content areas.  By having a large population of over 70% free and reduced lunch students, we address the gaps through our regular instruction.

Big Rock : Academic Growth

| In the first 30 days, we will know we are successful when: 7/31/11 All content areas have completed their first unit plan, Pacing Guide, and assessments that incorporate Core Academic Standards Complete the final copy of the program review for Arts and Humanities and Practical Living |
| --- |
| The measures/evidence we will use are: Attendance-Sign In sheets and Agendas for each day Complete units posted on high school shared folder Program Review for Arts and Humanities and Practical Living completed. |
| First 30 days action strategies: | Who is on point? |
| Teachers complete the unit plans during end of year make-up time | Tony Jury/Roxann Booth |
| Teachers complete program reviews during end of year make-up time | PLCS and Arts/ Humanities |
| If we are not successful, we will: Teachers will complete the units prior to August 1st Teachers will complete Program Reviews prior to August 1st |
| In 60 days, we will know we are successful when: 8/31/11 District Non-Negotiables shared with all teachers Accountability Calendar determining Interim assessments developed and shared with all teachers Quality Core/Common Standards are embedded in lesson plans |
| The measures/evidence we will use are: Completed Non-Negotiables Document Completed Accountability Calendar e-Prep Scores Documentation/Agenda of August Faculty meetings |
| 60 days action strategies: | Who is on point? |
| Non-Negotiables are discussed and presented to all faculty at Faculty meeting Accountability calendar is discussed and presented to all faculty at faculty Meeting ePrep #1 assessments have been completed Each PLC will meet and discuss implementation of Calendar and submit minutes of meeting to Principal before August 31st . | Roxann Booth Roxann Booth PLC Chairs |
| If we are not successful, we will: Meet again on August 31st to complete tasks |

| In 90 days, we will know we are successful when: 9/30/11 Non-Negotiables and QualityCore/Common Standards are Continually embedded in instruction First Round of ePrep scores are documented Bench mark assessments will be given at the end of the first unit and all units after for Eng 2 , Alg 2, US Hist 2, and Biology Results are analyzed in PLCs with students being identified |
| --- |
| The measures/evidence we will use are: Unit Plans and Weekly Lesson Plans PLC Minutes First round of ePrep and result graphs Quality Core Unit I results Walkthroughs |
| 90 days action strategies: | Who is on point? |
| ePrep results and Benchmark assessments are shared with faculty and posted on data walls Walkthroughs will be conducted in each classroom | Dept. heads/Principals Booth, Jury |
| If we are not successful, we will: on September 30 meet individually with teachers who are not meeting criteria to work on and accomplish strategies | Roxann Booth/Tony Jury |

| In 120 days, we will know we are successful when: 10/31/11 Non-Negotiables and Quality Core/Common Standards are continually embedded in instruction Co-Curricular Data Teams are functioning and meeting once a month First Round of Think Link Completed by students and scores are documented Bench mark assessments continue to be given for Eng 2 , Alg 2, US Hist 2, and Biology Current Results are analyzed in PLCs with students being identified and placed in RTI |
| --- |
| The measures/evidence we will use are: Lesson Plans/Walkthroughs Action Plan from Data teams Think Link Results Benchmark Results PLC Minutes |
| 120 days action strategies: | Who is on point? |
| walkthroughs will occur, and feedback given to teachers Think Link results and Benchmark assessments are shared with faculty Ist Central Office Walkthrough on October 6 | Roxann Booth/Tony Jury Dept. heads/Principals Central Office Staff |
| If we are not successful, we will: on October 31 meet individually with teachers who are not meeting criteria to work on and accomplish strategies In 150 days, we will know we are successful when: 11/30/11 50% of 9th graders score above the benchmarks in all categories of the PLAN did not meet goals 40% met the English benchmark 11% met the math benchmark 20% met the reading benchmark 7% met the science benchmark 4% met all benchmarks 50% of 10th graders score above the benchmarks in all categories of the PLAN did not meet goals 54% met the English benchmark 23% met the math benchmark 37% met the reading benchmark 24% met the science benchmark 21% met all benchmarks |
| The measures/evidence we will use are: 9th grade PLAN Scores 10th grade PLAN Scores |
| 150 days action strategies: | Who is on point? |
| PLAN results are shared with faculty, students, and parents Continue eprep tutorials in both regular classroom and RTI | Dept. heads/Principals |
| If we are not successful, we will: Identify gaps and address in RTI and classroom instruction |

| In 180 days, we will know we are successful when: 12/31/11 Non-Negotiables and Quality Core/Common Standards are continually embedded in instruction Co-Curricular Data Teams are functioning and meeting once a month Bench mark assessments continue to be given for Eng 2 , Alg 2, US Hist 2, and Biology Current Results are analyzed in PLCs with students being identified and placed in RTI |
| --- |
| The measures/evidence we will use are: Lesson Plans/Walkthroughs Data team Action Plan Benchmark results PLC Minutes |
| 180 days action strategies: | Who is on point? |
| Lesson plans will be monitored, walkthroughs will occur, and feedback given to teachers ePrep #2 assessments have been completed Bench mark assessments will be Shared | Principals Dept. Heads/Principals |
| If we are not successful, we will: Meet with PLCs and Data teams to accomplish strategies. |
| In 210 days, we will know we are successful when: 01/31/12 Second Round of ePrep scores are documented 50% of 9th graders have scored at or above the benchmarks on Practice PLAN 50% of 10th graders have scored at or above benchmarks on Practice ACT 50% of 11th graders have scored at or above benchmarks on Practice ACT |
| The measures/evidence we will use are: ePrep scores |
| 210 days action strategies: | Who is on point? |
| Scores will be shared with faculty and RTI and Instruction will focus on results.. Instructional strategies will be in place to address students not reaching goals | Dept. heads/Principals Dept. heads/Principals |
| If we are not successful, we will: On January 31 address teachers not implementing strategies for improvement |

| In the first 240 days, we will know we are successful when: 02/29/12 Bench mark assessments continue to be given for Eng 2 , Alg 2, US Hist 2, and Biology Current Results are analyzed in PLCs with students being identified |
| --- |
| The measures/evidence we will use are: Think Link Scores Unit test scores PLC Minutes |
| First 240 days action strategies: | Who is on point? |
| Scores will be shared with faculty and put on data walls. ePrep #3 assessments have been completed Instructional Strategies will be in place to address students not reaching goals. | Dept. heads/Principals Dept. heads/Principals |
| If we are not successful, we will: On February 29 address teachers not implementing strategies for improvement |
| In 270 days, we will know we are successful when: 3/30/12 All Juniors have completed ePrep tutorials and ACT prep instruction Successfully complete the ACT on March 6 or March 20 Second Round of Think Link Completed by students and scores are documented Bench mark assessments continue to be given for Eng 2 , Alg 2, US Hist 2, and Biology |
| The measures/evidence we will use are: ePrep data Think Link Data Unit Test Scores |
| 270 days action strategies: | Who is on point? |
| Continue ACT prep until March 5 Continue Instructional Strategies | All teachers Dept. heads/Principals |
| If we are not successful, we will: On March 30 address teachers not implementing strategies for improvement |

| In the first 300 days, we will know we are successful when: April 30, 2012 Bench mark assessments continue to be given for Eng 2 , Alg 2, US Hist 2, and Biology Seniors are meeting benchmarks on COMPASS TESTING |
| --- |
| The measures/evidence we will use are: Unit test scores Compass Scores |
| First 300 days action strategies: | Who is on point? |
| Continue Unit Tests Seniors take COMPASS |  |
| If we are not successful, we will: Continue with classroom instruction, e Prep, and Compass Testing |
| In 330 days, we will know we are successful when: May 30, 2012 50% of graduating Seniors are College/Career ready EOC Assessments have been Successfully administered |
| The measures/evidence we will use are: COMPASS Scores EOC Assessment Scores |
| 330 days action strategies: | Who is on point? |
| Analyze to revise plan. |  |
| If we are not successful, we will: Develop and revise plan for upcoming year. |