Jeff Wells, LEED AP

Project Manager

Alliance Corporation

116 East College Street

Glasgow, KY 42141

270.651.8848 - o

270.651.2915 - f

270.404.0675 - m

[www.alliancecorporation.com](file:///C%3A%5CDocuments%20and%20Settings%5Cmmaples%5CLocal%20Settings%5CTemporary%20Internet%20Files%5CContent.Outlook%5C6TNO66QW%5Cwww.alliancecorporation.com)

To all, below are the Change Orders I would like to be brought up for approval at the next board meeting.  If you have any questions, let me know.  Thank you.

Preschool

CO#                                                       Contractor                                                                                          Amount                               Description

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 32 |  |  | BENNETT'S CARPETS | 1,824.25  |  | INSTALL DRYWALL IN ROOM #103 TO COVER UNACCEPTABLE BLOCK (SCO#36) |
| 33 |  |  | WESTSIDE MASONRY | (1,824.25) |  | BACKCHARGE FOR UNACCEPTABLE BLOCK (SCO#36) |
| 34 |  |  | QUALITY FIRE PROTECTION, INC. | (76,718.00) |  | DELETE FIRE PUMP HOUSE (PR#12) |
| 35 |  |  | ADVANCED ELECTRICAL SYSTEMS, INC. | 879.19  |  | DELETE ELECTRICAL DUE TO DELETION OF FIRE PUMP HOUSE (PR#12)($-1,350.89), ELECTRICAL WORK TO DEMO WALL BETWEEN RM 166 AND 167 (PR#26) ($2,230.08) |
| 36 |  |  | GRAYHAWK CORPORATION | 885.00  |  | CEILING GRID RE-WORK TO COMBINE ROOMS 166 AND 167 (PR#26) |
| 37 |  |  | GM GLASS & MIRROR | 391.00  |  | ADDITIONAL GLAZING FOR ADDED DOORS IN EXISTING BUILDING AND CHANGE CLOSER ARM ON DOOR #153 (SCO#35) |

Helmwood

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 40 |  |  | CORBETT CONSTRUCTION CO., INC. | 650.47  |  | EXTRA DUMPSTER USAGE OVER ALLOWANCE IN JANUARY (SCO#28) |
| 41 |  |  | FRANKLIN COATINGS OF KY, INC. | 1,442.00  |  | ADDITIONAL PREP WORK TO EXISTING WALLS (SCO#29) |