# THIS IS A DECISION PAPER

TO:		HARDIN COUNTY BOARD OF EDUCATION

FROM:	Nannette Johnston, Superintendent

DATE:		JUNE 21, 2012

SUBJECT:	APPROVAL OF CHANGE ORDERS 1.1 – 1.4 CENTRAL HARDIN HVAC PHASE 3

ISSUE:  The Board needs to approve change orders 1.1 – 1.4 on Central Hardin HVAC replacement

# FACTS:

The Kentucky Department of Education requires that the Local Board of Education approve Change Orders on projects prior to their approval.  Below is a listing of Change Orders 1.1 – 1.4:

|  | Item | Reason For Change | Amount |
| --- | --- | --- | --- |
| 1.1 | Modify Security Room walls per PFGW May 23 email | Three walls - This space was modified with additions and credits with a net add of $671.00. The north wall change was to remove existing pre-finished drywall materials and to replace with new drywall to match adjacent new wall. The east wall change resulted in a credit of $300.00 to change the height of the wall from going to deck above to a height of only 4” above finished ceiling. At the south wall a new metal stud wall was add to provide for a more suitable fire rated wall at this location; this resulted in an add of $500.00. | $671.00 |
| 1.2 | Relocate existing roof drain. | An existing roof drain required relocation to allow for new doors at new security area. | $1,485.00 |
| 1.3 | Demo of existing electrical and installation of required electrical work in security area. | Electrical provisions were not provided for in contract documents. | $2,350.66 |
| 1.4 | Reroute electrical feeder to panel H2 | During construction the electrical engineer and electrical contractor determined that a savings could be made by changing electrical feeds. | Credit of ($3,246.84) |
| Total Add | $1,259.82 |

(See attached documentation)

# RECOMMENDATION

# I RECOMMEND THE HARDIN COUNTY BOARD OF EDUCATION APPROVE CHANGE ORDERS 1.1-1.4 FOR THE HARDIN CENTRAL HVAC REPLACEMENT PHASE 3 PROJECT IN THE TOTAL AMOUNT OF $1,259.82.

RECOMMENDED MOTION

# I MOVE THE HARDIN COUNTY BOARD OF EDUCATION APPROVE CHANGE ORDERS 1.1-1.4 FOR THE HARDIN CENTRAL HVAC REPLACEMENT PHASE 3 PROJECT IN THE TOTAL AMOUNT OF $1,259.82.