Jim:

Please see the following tentative schedule for modifying your DFP, for your review and comment:

* Superintendent selects LPC members
* February 14th meeting – Board approves LPC and required information is sent to KDE
* 4th week of February – 1st LPC / Public Forum
* 2nd week of March – 2nd LPC / Public Forum
* Send draft DFP to KDE for comment
* 4th week of March – 3rd LPC / Public Forum
* April 11th – Board approval of DFP
* Last week of April / first week of May – Public Hearing
* May 9th meeting – Board approval of Public Hearing report

I’m proposing a fee of $1,000 – our cost and the state fee schedule both exceed this, however, I’d like to do this as a favor for further relationship building.  I am also happy to provide assistance with the technical inventory, interacting with the state department, as well as have a representative from our office attend meetings as needed.

Ehmet Hayes/aes

Robert Ehmet Hayes & Associates, PLLC

2512 Dixie Highway

Fort Mitchell, Kentucky 41017

p: 859-331-3121

f: 859-331-3332