# THIS IS A DECISION PAPER

TO:		HARDIN COUNTY BOARD OF EDUCATION

FROM:	Nannette Johnston, Superintendent

# DATE:	November 20, 2014

SUBJECT:	approve of change orders 2.1 – 2.11 for HVAc Improvements at Meadowview Elementary School

ISSUE

The Board needs to approve the Change Orders 2.1 – 2.11 for HVAC Improvements at Meadowview Elementary School.

# FACTS:

The Kentucky Department of Education requires that the Local Board of Education approve Change Orders on projects prior to their approval.  A summary of change orders 1.1 – 2.11 are listed below and supporting documentation is attached.

|  | Item | Reason For Change | Amount |
| --- | --- | --- | --- |
| 2.1 | Re-grade, seed and straw area behind playground. | Erosion of existing condition to be corrected. Was not included in contract. | $1,159.00 |
| 2.2 | Install sprinkler head guards in gymnasium. | Sprinkler heads in gym were exposed. The guards protect the heads from stray balls. | $1,089.00 |
| 2.3 | Delete installation of wood flooring in classroom closets. | Not needed. | ($2,432.00) |
| 2.4 | Time-and-materials cost to remove existing limited area sprinkler lines. | Existing sprinkler lines in records room had to be removed because they were not part of the new system. | $1,266.00 |
| 2.5 | Delete casework from the scope of work. | School wanted to delete the casework to get furniture for lobby. Owner agreed to use existing casework. | ($4,850.00) |
| 2.6 | Credit for electrical work not required due to deletion of casework. | School wanted to delete the casework to get furniture for lobby. Owner agreed to use existing casework. | ($758.00) |
| 2.7 | Credit for difference between the scheduled cost and actual cost of geothermal well casing. | Some proposed casing was not needed for the project. | ($11,576.00 |
| 2.8 | Remove existing mechanical louver and install brick veneer | Owner requested to remove unsightly louvers and install matching brick. | $4,669.00 |
| 2.9 | Credit for the cost of two Smart boards damaged during construction | Items damaged by subcontractors during construction. | ($4,004.00) |
| 2.10 | Credit for replacement parts for a clock damaged during construction. | Items damaged by subcontractors during construction. | ($184.00) |
| 2.11 | Add 2" circuits for ERU#1 and ERU#2. | These were left out of design by mechanical engineer. Owner is only paying for labor to install not the total costs of materials and labor to drain system. | $2,643.00 |
| TOTAL | ($12,978.00) |

RECOMMENDATION

I RECOMMEND THAT THE HARDIN COUNTY BOARD OF EDUCATION APPROVE change orders 2.1 – 2.11 for the HVAC improvements to Meadowview elementary school total decuct of $12,978.40.

RECOMMENDED MOTION

I MOVE THAT THE HARDIN COUNTY BOARD OF EDUCATION APPROVE change orders 2.1 – 2.11 for the HVAC improvements to Meadowview elementary school total deduct $12,978.40.