## BG-4 Per Contract
KENTUCKY DEPARTMENT OF EDUCATION | [13 empty] | BG-4
702 KAR 4:160 | [13 empty] | CONTRACT CLOSEOUT FORM
District Name: |  | Hardin County |  |  | District Code: | 231 | Facility Name: |  | NPES, WHMS, Central Office |  |  | School Code: | 021, 168, 000
BG #: |  | 15-208 |  | Project Name: |  | 2015 Asphalt Resurfacing (Multiple Locations)
Contractor: |  |  | Hall Contracting |  | Bid Package: |  | 339082.21
A. Project Construction Cost:
|  | 1. Original Contract Amount | [7 empty] | $ | 335582.21
|  | 2. Net Total of Change Orders to Contract | [7 empty] | $ | 3600
|  | 3. Original Purchase Order Summary Amount | [7 empty] | $ | 0
|  | 4. Net Total of Change Orders to Purchase Orders | [7 empty] | $ | 0
|  | 5. Total Cost of Construction (sum of lines 1 - 4) | [7 empty] | $ | 339182.21
B. Verification of required approvals by other regulatory agencies:
1. Office of Housing, Buildings and Construction
|  | a. Certificate of Occupancy |  |  | DATE: | NA |  | e. Sprinkler Certificate |  |  |  | DATE: | NA
|  | b. Plumbing Certificate |  |  | DATE: | NA |  | f. Boiler Certificate |  |  |  | DATE: | NA
|  | c. Electrical Certificate: |  |  | DATE: | NA |  | g. Range Hood Suppression |  |  |  | DATE: | NA
|  | d. Fire Alarm Certificate: |  |  | DATE: | NA |  | h. Other |  |  |  | DATE:
2. Natural Resources and Environmental Protection Cabinet
|  | a. Sewage Disposal Certificate | [6 empty] | DATE:
|  | b. Other | [6 empty] | DATE: | NA
C. Close Out:
| 1. Punch List Completed |  |  |  | DATE: | 2015-11-20 |  | 4. Owner Training on Systems |  |  |  | DATE:
| 2. Record Drawings Completed |  |  |  | DATE: |  |  | 5. Verification of Payment of
| 3. Warranty & Guarantees | [6 empty] | Debts and Claims to Date | Debts and Claims to Date |  |  | DATE:
| Information Provided |  |  |  | DATE: |  |  | 6. Other |  |  |  | DATE:
The work performed under this contract has been reviewed and found to be substantially complete, according to the
plans and specifications approved by the Kentucky Department of Education.
|  | Architect: __________________________________________________________ | [9 empty] | DATE:
|  | Engineer: __________________________________________________________ | [9 empty] | DATE:
Contractor/
|  | Construction Manager: | [9 empty] | DATE:
|  | The Hardin County |  |  |  |  | Board of Education accepts this contract as being complete
subject to the review of the Kentucky Department of Education.
|  | Local Board of Education Designee: | [9 empty] | DATE:
LOCAL BOARD ORDER MUST BE ON FILE WITH DISTRICT
Submit one complete copy to KDE for each contract and purchase order summary, if utilized.
BG-4 Date:
Board Order Date: