## BG-5 Project
KENTUCKY DEPARTMENT OF EDUCATION | [19 empty] | BG-5
702 KAR 4:160 | [19 empty] | PROJECT CLOSEOUT FORM
District: | [5 empty] | District |  |  |  | Facility | [6 empty] | School Code:
Name: |  | Hardin |  |  |  | Code: | 231 |  |  | Name: | North Middle School | [7 empty] | 080
BG #: |  | 15-289 |  |  | Project Name: |  |  | Sign for North Middle School
A. PROJECT COMPLETION & INVENTORY UPDATE
| Project Total Gross Square Footage: | [5 empty] | n/a
| The work performed under this project has been reviewed and found to be substantially complete, according to the KDE approved Construction Documents. | [12 empty] | Date of Project Substantial Completion :
45 days from contract execution
| Upon project completion, submit a revised total building inventory file, per 702 KAR 4:180, for building(s) modified or newly constructed during the project. | [12 empty] | Date of Inventory Update:
B. RECONCILIATION OF FINAL PROJECT COST
|  |  |  | C |  | CURRENT BG-1 COSTS (reconciled with bid amts.) |  |  | FINAL PROJECT COSTS |  |  |  | CURRENT BG-1 FUNDS AVAILABLE (reconciled with bid amounts) |  |  |  | FINAL FUND SOURCES UTILIZED
1. Total Construction Cost | [5 empty] | 39965.52 |  |  | 22805.7 |  |  | 1. SFCC Cash Req. |  | 0 |  |  | 0
2. Architect/Engineer Fee | [5 empty] | 5000 |  |  | 5101.83 |  |  | 2. SFCC Bond Req. |  | 0 |  |  | 0
3. Construction Manager Fee | [5 empty] | 0 |  |  | 0 |  |  | 3. SFCC Bond Sale |  | 0 |  |  | 0
4. Bond Discount | [5 empty] | 0 |  |  | 0 |  |  | 4. Local FSPK Bond Sale |  | 0 |  |  | 0
5. Fiscal Agent Fee | [5 empty] | 0 |  |  | 0 |  |  | 5. Local Gen Fund Bond Sale |  | 0 |  |  | 0
6. Construction Contingencies | [5 empty] | 2000 |  |  | 0 |  |  | 6. Cash - General Fund |  | 47965.52 |  |  | 27907.53
7. Site Acquisition | [5 empty] | 0 |  |  | 0 |  |  | 7. Cash - Capital Outlay |  | 0 |  |  | 0
8. Equipment/Furnishings | [5 empty] | 0 |  |  | 0 |  |  | 8. Cash - Building Fund |  | 0 |  |  | 0
9. Equipment/Computers | [5 empty] | 0 |  |  | 0 |  |  | 9. Cash - Inv. Earnings |  | 0 |  |  | 0
10. Tech. Network Sys. (KETS) | [5 empty] | 0 |  |  | 0 |  |  | 10. KETS |  | 0 |  |  | 0
11. Other* |  |  | Plan review |  |  | 0 |  |  | 0 |  |  | 11. KYTC Reimbursement |  | 0 |  |  | 0
12. Other* |  |  | Printing |  |  | 1000 |  |  | 0 |  |  | 12. Other* |  | 0 |  |  | 0
13. Other* | [5 empty] | 0 |  |  | 0 |  |  | 13. Other* |  | 0 |  |  | 0
14. Other* | [5 empty] | 0 |  |  | 0 |  |  | 14. Other* |  | 0 |  |  | 0
Total Costs: | [5 empty] | 47965.52 |  |  | 27907.53 |  |  | Total Funds: |  | 47965.52 |  |  | 27907.53
* Define
The expense totals reflected on this form were incurred as a result of the construction for the above reference project.
An accounting of the expenses was presented to the board for review and approval prior to payment.
|  | The | Hardin | [5 empty] | Board of Education accepts this project as being complete subject to the review of KDE.
[7 empty] | Local Board of Education Designee: | [7 empty] | DATE:
LOCAL BOARD ORDER MUST BE ON FILE WITH DISTRICT
Submit one complete copy to KDE for each completed project.
SUBMIT AN INVENTORY UPDATE - PER 702 KAR 4:180
BG-5 Date:
Board Order Date: