## BOSTONAP
RECAP SHEET OF CONTRACTS AND PURCHASE ORDERS | [7 empty] | APPLICATION NO: |  | NO: |  | 5
NELSON COUNTY EARLY CHILDHOOD PHASE 2 | [7 empty] | APPLICATION DAT: | DATE: |  |  | 2016-07-25
BARDSTOWN, KY | [7 empty] | PERIOD TO: |  |  |  | 2016-07-25
------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | ------------------------------------------------------------------------------------------------------------------------------- | ------------------------------------------------------------------------------------------------------------------------------- | ------------------------------------------------------------------------------------------------------------------------------- | ------------------------------------------------------------------------------------------------------------------------------- | ------------------------------------------------------------------------------------------------------------------------------- | ------------------------------------------------------------------------------------------------------------------------------- | ------------------------------------------------------------------------------------------------------------------------------- | ------------------------------------------------------------------------------------------------------------------------------- | ---------------------- |  | ---------------------- |  | -------------------------------------------------------------------------------------------------------------------------------
BP | ¦ | DESCRIPTION OF WORK | ¦ | ORIGINAL | ¦ | CHANGE | ¦ | CONTRACT | ¦ |  | ¦ | TOTAL | ¦ | % | ¦ | RETAINAGE | ¦ | TOTAL | ¦ | PREVIOUS | ¦ | PAYMENT | ¦ | BALANCE | ¦
# | ¦ |  | ¦ | CONTRACT | ¦ | ORDERS | ¦ | SUM TO | ¦ |  | ¦ | COMPLETED | ¦ | COMP | ¦ |  | ¦ | COMPLETE | ¦ | PAYMENTS | ¦ | DUE | ¦ | TO | ¦
| ¦ |  | ¦ | SUM | ¦ |  | ¦ | DATE | ¦ | # | ¦ | & STORED | ¦ |  | ¦ |  | ¦ | LESS | ¦ |  | ¦ |  | ¦ | FINISH | ¦
| ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ | TO DATE | ¦ |  | ¦ |  | ¦ | RETAINAGE | ¦ |  | ¦ |  | ¦ |  | ¦
------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | ------------------------------------------------------------------------------------------------------------------------------- | [9 empty] | ------------------------------------------------------------------------------------------------------------------------------- |  | -------------------------------------------------------------------------------------------------------------------------------
1 | ¦ | EXCAVATION/ASPHALT | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦
| ¦ | M J CONSTRUCTION | ¦ | 168000 | ¦ | 0 | ¦ | 168000 | ¦ | 3 | ¦ | 59462.5 | ¦ | 35.39% | ¦ | 5946.25 | ¦ | 53516.25 | ¦ | 53516.25 | ¦ | 0 | ¦ | 108537.5 | ¦
------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | ------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | -------------------------------------------------------------------------------------------------------------------------------
2 | ¦ | GENERAL TRADES | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦
| ¦ | M J CONSTRUCTION | ¦ | 358000 | ¦ | 0 | ¦ | 358000 | ¦ | 5 | ¦ | 165600.14 | ¦ | 46.26% | ¦ | 16560.014 | ¦ | 149040.126 | ¦ | 107527.63 | ¦ | 41512.496 | ¦ | 192399.86 | ¦
| ¦ | IMI | ¦ | 34000 | ¦ |  | ¦ | 34000 | ¦ |  | ¦ | 33951 | ¦ | 99.86% | ¦ | 0 | ¦ | 33951 | ¦ | 25603 | ¦ | 8348 | ¦ | 49 | ¦
| ¦ | MILLS SUPPLY | ¦ | 30000 | ¦ |  | ¦ | 30000 | ¦ |  | ¦ | 22083.53 | ¦ | 73.61% | ¦ | 0 | ¦ | 22083.53 | ¦ | 17554.28 | ¦ | 4529.25 | ¦ | 7916.47 | ¦
| ¦ | HAYDON MATERIALS | ¦ | 8000 | ¦ |  | ¦ | 8000 | ¦ |  | ¦ | 7775.13 | ¦ | 97.19% | ¦ | 0 | ¦ | 7775.13 | ¦ | 7532.59 | ¦ | 242.54 | ¦ | 224.87
| ¦ | PARKVIEW HOME CENTER | ¦ | 52000 | ¦ |  | ¦ | 52000 | ¦ |  | ¦ | 1052.07 | ¦ | 2.023% | ¦ | 0 | ¦ | 1052.07 | ¦ | 336.57 | ¦ | 715.5 | ¦ | 50947.93
------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | ------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | -------------------------------------------------------------------------------------------------------------------------------
3 | ¦ | STRUCTURAL STEEL | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦
| ¦ | STRUCTURAL STEEL SER. | ¦ | 77000 | ¦ | 0 | ¦ | 77000 | ¦ | 1 | ¦ | 70720 | ¦ | 91.84% | ¦ | 7072 | ¦ | 63648 | ¦ | 0 | ¦ | 63648 | ¦ | 6280 | ¦
| ¦ | MARION STEEL FAB. | ¦ | 76035 | ¦ |  | ¦ | 76035 | ¦ | 1 | ¦ | 66949.7 | ¦ | 88.05% | ¦ | 0 | ¦ | 66949.7 | ¦ | 13436.6 | ¦ | 53513.1 | ¦ | 9085.3
| ¦ | GOODER-HENRICHSEN CO. | ¦ | 27620 | ¦ |  | ¦ | 27620 | ¦ |  | ¦ | 27620 | ¦ | 100% | ¦ | 0 | ¦ | 27620 | ¦ | 0 | ¦ | 27620 | ¦ | 0 | ¦
------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | ------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | -------------------------------------------------------------------------------------------------------------------------------
4 | ¦ | ROOFING/SHEET METAL | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦
| ¦ | NU-WAY ROOFING | ¦ | 115913.1 | ¦ | 0 | ¦ | 115913.1 | ¦ |  | ¦ | 0 | ¦ | 0% | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 115913.1 | ¦
|  | MUELLER ROOFING SUP. |  | 29485.9 |  |  |  | 29485.9 |  |  |  | 0 |  | 0% | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 0 |  | 29485.9
| ¦ | NORRENBROCK | ¦ | 17156 | ¦ |  | ¦ | 17156 | ¦ |  | ¦ | 0 | ¦ | 0% | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 17156 | ¦
------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | ------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | -------------------------------------------------------------------------------------------------------------------------------
5 | ¦ | DOORS/FRAMES/HDWE | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦
| ¦ | ATLAS METAL PRODUCTS | ¦ | 0 | ¦ |  | ¦ | 0 | ¦ |  | ¦ | 0 | ¦ | 0% | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦
| ¦ | ATLAS ENTERPRISES | ¦ | 36400 | ¦ | 0 | ¦ | 36400 | ¦ | 3 | ¦ | 25500 | ¦ | 70.05% | ¦ | 0 | ¦ | 25500 | ¦ | 25500 | ¦ | 0 | ¦ | 10900 | ¦
------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | ------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | -------------------------------------------------------------------------------------------------------------------------------
6 | ¦ | ALUMINUM ENTRANCES | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦
| ¦ | W R COLE & ASSOCIATES | ¦ | 30900 | ¦ | 0 | ¦ | 30900 | ¦ |  | ¦ | 0 | ¦ | 0% | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 30900 | ¦
| ¦ | C. I. M. | ¦ | 28000 | ¦ |  | ¦ | 28000 | ¦ |  | ¦ | 0 | ¦ | 0% | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 28000 | ¦
------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | ------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | -------------------------------------------------------------------------------------------------------------------------------
7 | ¦ | ACOUSTICAL/DRYWALL | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦
| ¦ | M & J CONSTRUCTION | ¦ | 243375 | ¦ | 0 | ¦ | 243375 | ¦ | 2 | ¦ | 20050 | ¦ | 8.238% | ¦ | 2005 | ¦ | 18045 | ¦ | 3960 | ¦ | 14085 | ¦ | 223325 | ¦
| ¦ | SERVICE PARTNERS | ¦ | 6000 | ¦ |  | ¦ | 6000 | ¦ |  | ¦ | 0 |  | 0% | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 6000
| ¦ | NEXGEN | ¦ | 39800 | ¦ |  | ¦ | 39800 | ¦ |  | ¦ | 2731.39 |  | 6.863% | ¦ | 0 | ¦ | 2731.39 | ¦ | 0 | ¦ | 2731.39 | ¦ | 37068.61
| ¦ | TRI-STATE | ¦ | 5825 | ¦ |  | ¦ | 5825 | ¦ |  | ¦ | 5825 | ¦ | 100% | ¦ | 0 | ¦ | 5825 | ¦ | 0 | ¦ | 5825 | ¦ | 0 | ¦
------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | ------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | -------------------------------------------------------------------------------------------------------------------------------
8 | ¦ | FLOOR COVERING | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦
| ¦ | CDI | ¦ | 26659 | ¦ | 0 | ¦ | 26659 | ¦ | 1 | ¦ | 1296 | ¦ | 4.861% | ¦ | 129.6 | ¦ | 1166.4 | ¦ | 1166.4 | ¦ | 0 | ¦ | 25363
| ¦ | KY FLOORING DIST. | ¦ | 15211 | ¦ |  | ¦ | 15211 | ¦ |  | ¦ | 1454 | ¦ | 9.559% | ¦ | 0 | ¦ | 1454 | ¦ | 0 | ¦ | 1454 | ¦ | 13757 | ¦
------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | ------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | -------------------------------------------------------------------------------------------------------------------------------
9 | ¦ | PAINTING | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦
| ¦ | CHAMBERS PAINTING | ¦ | 33635 | ¦ | 0 | ¦ | 33635 | ¦ |  | ¦ | 0 | ¦ | 0% | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 33635 | ¦
------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | ------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | -------------------------------------------------------------------------------------------------------------------------------
10 | ¦ | MISC SPECIALTIES | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦
| ¦ | U S SPECIALTIES | ¦ | 0 | ¦ |  | ¦ | 0 | ¦ |  | ¦ | 0 | ¦ | 0% | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦
| ¦ | U S SPECIALTIES HOLDING | ¦ | 17500 | ¦ | 0 | ¦ | 17500 | ¦ |  | ¦ | 0 | ¦ | 0% | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 17500 | ¦
------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | ------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | -------------------------------------------------------------------------------------------------------------------------------
11 | ¦ | FOOD SERVICE EQUIP. | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦
| ¦ | C & T DESIGN | ¦ | 5750.03 | ¦ | 0 | ¦ | 5750.03 | ¦ |  | ¦ | 0 | ¦ | 0% | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 5750.03 | ¦
| ¦ | BLUE MOUNTAIN | ¦ | 37380.3 | ¦ |  | ¦ | 37380.3 | ¦ |  | ¦ | 0 | ¦ | 0% | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 37380.3
------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | ------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | -------------------------------------------------------------------------------------------------------------------------------
12 | ¦ | PLUMBING & HVAC | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦
| ¦ | G. B. M. C. INC. | ¦ | 430602 | ¦ | 0 | ¦ | 430602 | ¦ | 4 | ¦ | 210344.5 | ¦ | 48.85% | ¦ | 21034.45 | ¦ | 189310.05 | ¦ | 146475 | ¦ | 42835.05 | ¦ | 220257.5 | ¦
| ¦ | THERMAL EQUIPMENT | ¦ | 10756 | ¦ |  | ¦ | 10756 | ¦ |  | ¦ | 0 | ¦ | 0% | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 10756 | ¦
| ¦ | DAIKEN C/O THERMAL EQ. | ¦ | 46244 | ¦ |  | ¦ | 46244 | ¦ |  | ¦ | 0 | ¦ | 0% | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 46244 | ¦
| ¦ | FERGUSON | ¦ | 55135 | ¦ |  | ¦ | 55135 | ¦ |  | ¦ | 14252.61 | ¦ | 25.85% | ¦ | 0 | ¦ | 14252.61 | ¦ | 6872.85 | ¦ | 7379.76 | ¦ | 40882.39
| ¦ | ALLIED TECHNOLOGY | ¦ | 15040 | ¦ |  | ¦ | 15040 | ¦ |  | ¦ | 5110 | ¦ | 33.98% | ¦ | 0 | ¦ | 5110 | ¦ | 0 | ¦ | 5110 | ¦ | 9930
------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | ------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | -------------------------------------------------------------------------------------------------------------------------------
13 | ¦ | FIRE PROTECTION | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦
| ¦ | LANDMARK SPRINKLER | ¦ | 29200 | ¦ | 0 | ¦ | 29200 | ¦ |  | ¦ | 0 | ¦ | 0% | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 29200 | ¦
| ¦ | PLUMBERS SUPPLY | ¦ | 5000 |  |  | ¦ | 5000 | ¦ |  | ¦ | 0 | ¦ | 0% | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 5000
------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | ------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | -------------------------------------------------------------------------------------------------------------------------------
14 | ¦ | ELECTRICAL | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦
| ¦ | DIXON ELECTRIC | ¦ | 156165 | ¦ | 0 | ¦ | 156165 | ¦ | 3 | ¦ | 72480.35 | ¦ | 46.41% | ¦ | 7248.035 | ¦ | 65232.315 | ¦ | 43401.02 | ¦ | 21831.295 | ¦ | 83684.65 | ¦
| ¦ | GRAYBAR | ¦ | 70195 | ¦ |  | ¦ | 70195 | ¦ |  | ¦ | 0 | ¦ | 0% | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 70195 | ¦
| ¦ | SIMPLEX | ¦ | 18385 | ¦ |  | ¦ | 18385 | ¦ |  | ¦ | 0 | ¦ | 0% | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 18385 | ¦
| ¦ | NEWTECH | ¦ | 28555 | ¦ |  | ¦ | 28555 | ¦ |  | ¦ | 0 | ¦ | 0% | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 0 | ¦ | 28555 | ¦
------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | ------------------------------------------------------------------------------------------------------------------------------- | [11 empty] | -------------------------------------------------------------------------------------------------------------------------------
|  | TOTAL |  | 2384922.33 |  | 0 |  | 2384922.33 |  |  |  | 814257.92 |  | 34.14% |  | 59995.349 |  | 754262.571 |  | 452882.19 |  | 301380.391 |  | 1570664.41
It is hereby certified that the above listed contractors and material suppliers are due the payment shown, which represents amounts
duly earned by and payable to said parties, their successors or assigns for labor, materials, work or services furnished under an
existing contract with the Board of Education of the Nelson County School District ("Board") relating to the construction of a new school
for the Board.
It is certified that this Requisition for Funds does not cause payments to the party receiving same to exceed the retainage
requirements of the Commission set forth in the Participation Agreement
_______________________________Date_____, 20_____ |  |  |  | Date_____, 20_____ |  |  |  | _______________________________Date_____, 20_____ |  |  | _______________________________Date_____, 19_____ |  | Date_____, 20_____
BCD, Inc. Construction Manager | [7 empty] | Superintendent, Nelson County Board of Education
_______________________________Date_____, 19_____ |  |  |  | Date_____,20_____ |  |  |  | _______________________________Date_____, 19_____ |  |  | _______________________________Date_____, 19_____ |  | Date_____, 20_____
Studio Kremer Architects
.