Peck Flannery Gream Warren Architects, LLC

112 North Main St.		Elizabethtown, Kentucky 42701

Phone: 270-765-2147		Fax: 270-765-2148

Email: lgream@pfgw.org		Website: www.pfgw.net

May 6, 2008

# Ms. Nannette Johnston

Hardin County Board of Education

65 W.A. Jenkins Rd.

Elizabethtown, KY 42701

RE:	Hardin County Schools

(Report of Projects in Progress)

Dear Nannette:

Please consider the following as a report on projects which our firm is presently providing Architecture/Engineering services.

I have 3 action items for the Hardin County School Board’s consideration/approval in their May 15th meeting as follows:

> Review and/or approval of bids on Phase 2 and 3 on North Hardin High School.

> Two change order items on Rineyville Elementary School.

1.    CREEKSIDE ELEMENTARY SCHOOL:

Site Work Bid Package “A” (Phillips Brothers Construction):     Work not presently complete under this contract consists of verification of stand of grass growth. Larry Rice of Phillips Brothers reports they overseeded earlier in season; he stated also that it looks like he will need to power seed.

- RINEYVILLE ELEMENTARY SCHOOL:

Building Bid Package “A” (Whittenberg Construction):  Whittenberg is progressing toward completion of Phase Two.  Charlie Jones will present construction progress during the May 15th Board meeting.

Board Action Items:

The following change order items are presented to the board for consideration.

|  | Item | Reason for Change | Amount of Change |
| --- | --- | --- | --- |
| 3.1 | Resurface existing Gymnasium roof. | Reroofing or roofing repairs were not addressed under contract documents. Upon review of gymnasium roof recently by David Wyatt it was determined that providing a new coating of roofing granules would be desirable at this time. | $15,229.00 |
| 3.2 | Add sprinkler heads throughout Areas C (existing classroom building) above ceilings. | The form material used for the concrete decking in the existing building years ago is combustible. Adding sprinkler heads above ceilings provides protection for these areas. | $13,125.00 |
|  |  | Add of | $28,354.00 |

Bid Package “C”, Division 17 (Marine Electric):   Marine Electric’s work under this contract is ongoing and concurrent with Whittenberg Construction’s progress.

3.    HEARTLAND ELEMENTARY SCHOOL:

Building Bid Package “A” (Morel Construction Company):   Charlie Jones will present construction progress this project during the May 15th Board meeting.

Bid Package “B”, Division 17:  Bonds, insurance documents and owner/contractor agreement has been sent to Department of Education for their review/approval. A pre-construction conference is scheduled for Friday, May 9.

- NORTH HARDIN HIGH SCHOOL PHASE ONE RENOVATIONS (2007):

McNutt Construction is in the process of resolving flooring maintenance issues on this project.

- NORTH HARDIN HIGH SCHOOL PHASE TWO and THREE RENOVATIONS

(2008- 2009):

Board Action Items:

This project is to bid on Wednesday, May 7.  I plan to present bids for the Hardin County School Board review and/or approval in their monthly board meeting on May 15th.

- HARDIN COUNTY SCHOOLS PERFORMING ARTS CENTER-ORCHESTRA         SHELL:

Remaining work on this project consist of StageRight forwarding of close out documents.  A Bg-4 on this project will be forwarded shortly.

7.    CENTRAL OFFICE ANNEX:

I am working with Gary Milby regarding options to modify plans and specifications and/or scope of project to accommodate available funds.

8.    TORNADO DAMAGES TO CENTRAL HARDIN HIGH SCHOOL AND BUILDINGS AND GROUDS FACILITIES:

We are providing Architectural services for :

  - Replacement of the Main Student Entry @Central Hardin High School.

  - Ninth Grade Center and Gymnasium Roof Replacements @ Central Hardin High School.

  - Replacement of Walls, Windows and Roof of Football Practice Press Box @ Central Hardin High School.

  - Replacement of Buildings and Grounds Facility.

Please give me a call if you have questions regarding any of the projects.

Sincerely,

Larry Gream

C:  	 Gary Milby

David Wyatt