## Sheet1
Change Orders
2016-08-08
Subcontractor Name: | KNIGHT'S MECHANICAL LLC.
Work Description: | Relocated Sprinklers, Frost Ceiling Tile in Corridor, Credit for Casing, Work for Truss repair and Additional Fencing
Project Name: | James T. Alton Middle School
Knight's Job # | 160315
Change Orders
| C.O. #1 - Relocate Sprinkler main to make room for installation of new |  | 3492
Heat Pumps.
| C.O. #2 - Replace all Corridor Ceiling Tile |  | 18185
| C.O. #3 - Credit for Casing not used in Geothermal Well Field |  | -17080
| C.O. #4 - Work associated with truss damage to date (more to come |  | 95470
as they continue work)
| C.O. #5 - Additional Fencing for VRF units in Admin area, and to protect |  | 11148.5
duct from ERU-2.
|  | Change Order Total = | 111215.5