## BG-5 Project
KENTUCKY DEPARTMENT OF EDUCATION | [16 empty] | BG-5
702 KAR 4:160 | [16 empty] | PROJECT CLOSEOUT FORM
District: |  |  |  |  | District |  |  |  | Facility | [5 empty] | School Code:
Name: |  | Hardin |  |  | Code: |  |  |  | Name: | Hardin County Early College & Career Center
BG #: |  | 13-157 |  | Project Name: |  |  | Hardin County Early College & Career Center
A. PROJECT COMPLETION & INVENTORY UPDATE
Project Total Gross Square Footage:
| The work performed under this project has been reviewed and found to be substantially complete, according to the KDE approved Construction Documents. | [11 empty] | Date of Project Substantial Completion :
| Upon project completion, submit a revised total building inventory file, per 702 KAR 4:180, for building(s) modified or newly constructed during the project. | [11 empty] | Date of Inventory Update:
B. RECONCILIATION OF FINAL PROJECT COST
|  |  | C |  | CURRENT BG-1 COSTS (reconciled with bid amts.) |  |  | FINAL PROJECT COSTS |  |  |  | CURRENT BG-1 FUNDS AVAILABLE (reconciled with bid amounts) |  |  | FINAL FUND SOURCES UTILIZED
1. Total Construction Cost |  |  |  |  | 15362000 |  |  | 15603192.42 |  |  | 1. SFCC Cash Req. |  | 0 |  | 0
2. Architect/Engineer Fee |  |  |  |  | 783462 |  |  | 801985.58 |  |  | 2. SFCC Bond Req. |  | 0 |  | 0
3. Construction Manager Fee |  |  |  |  | 0 |  |  | 0 |  |  | 3. SFCC Bond Sale |  | 0 |  | 0
4. Bond Discount |  |  |  |  | 332200 |  |  | 332200 |  |  | 4. Local FSPK Bond Sale |  | 16610000 |  | 16610000
5. Fiscal Agent Fee |  |  |  |  | 76695.26 |  |  | 76052 |  |  | 5. Local Gen Fund Bond Sale |  | 0 |  | 0
6. Construction Contingencies |  |  |  |  | 768100 |  |  | - |  |  | 6. Cash - General Fund |  | 818232.26 |  | 544267.94
7. Site Acquisition |  |  |  |  | 0 |  |  | 0 |  |  | 7. Cash - Capital Outlay |  | 0 |  | 0
8. Equipment/Furnishings |  |  |  |  | 26401.98 |  |  | 25562.85 |  |  | 8. Cash - Building Fund |  | 0 |  | 0
9. Equipment/Computers |  |  |  |  | 0 |  |  | 190631.86 |  |  | 9. Cash - Inv. Earnings |  | 0 |  | 0
10. Tech. Network Sys. (KETS) |  |  |  |  | 0 |  |  | 0 |  |  | 10. KETS |  | 0 |  | 0
11. Other* |  |  |  |  | 8775 |  |  | 28448.15 |  |  | 11. KYTC Reimbursement |  | 0 |  | 0
12. Other* |  |  |  |  | 70000 |  |  | 122597.06 |  |  | 12. Other* |  | 26401.98 |  | 26401.98
13. Other* |  |  |  |  | 12000 |  |  | 0 |  |  | 13. Other* |  | 0 |  | 0
14. Other* |  |  |  |  | 15000 |  |  | 0 |  |  | 14. Other* |  | 0 |  | 0
Total Costs: |  |  |  |  | 17454634.24 |  |  | 17180669.92 |  |  | Total Funds: |  | 17454634.24 |  | 17180669.92
* Define
The expense totals reflected on this form were incurred as a result of the construction for the above reference project.
An accounting of the expenses was presented to the board for review and approval prior to payment.
|  | The | [5 empty] | Board of Education accepts this project as being complete subject to the review of KDE.
[6 empty] | Local Board of Education Designee: | [7 empty] | DATE:
LOCAL BOARD ORDER MUST BE ON FILE WITH DISTRICT
Submit one complete copy to KDE for each completed project.
SUBMIT AN INVENTORY UPDATE - PER 702 KAR 4:180
BG-5 Date:
Board Order Date: