Project Construction Field Report

Project Name: Nelson County Schools – Guaranteed Energy Savings Contract – Bloomfield Middle, Bloomfield Elementary, and Nelson County High School.

Date: 04/27/2017

Contractor:  Intertech Mechanical, Freedom Electric, ECT Controls, Blanton Electrical

Distribution: Kevin Mattingly; Vince Paul; Troy Blanton; Tony Humphrey; Adam Pierce; Jon Gasser

Work Completed (04/17 – 04/21):

Freedom- (Electrical)

Middle School:

- LED tube installations and ballast removals (4 lamp fixtures) were performed and completed for Science and Computer Classrooms, Library, Office Area, Cafeteria and Kitchen Areas.

- Repairs were made to broken football field scoreboard ciruit.

Intertech Mechanical:

Bloomfield Middle School:

- Installed geothermal piping tracer wire.

- Backfilled sand bedding.

- Installed caution tape on top of sand bedding.

- Completed back filling of geothermal lateral piping trench.

- Buried piping connection points were identified with wood post on each end of piping runs.

Work to be completed (05/01 – 05/04):

Freedom – (Electrical)

- To continue after hours work for Bloomfield Middle and Elementary Schools (lighting).

Blanton Electric:

- To begin lighting lamp change outs and ballast removal at Nelson County High School; Monday evening after hours (5/1).

Safety Items:

Site Review:

- Daily site review walk through were completed; no hazardous conditions to report.

- Contractors were wearing appropriate PPE for their assigned task, and hard hats were worn at all times.

Weekly Tool Box Safety Talks:

- Top Four Construction Hazards (OSHA Quick Card) was read to all onsite members for Freedom Electrical and Intertech Mechanical, and was documented to the Project Safety Manual.

Other items:

- Mike King Landscaping was onsite (04/27) at Middle School to provide a quote for final grading, seeding, and replacement of gravel area around mechanical fencing.

End of report.

Mike McNair

Construction Project Manager

CMTA Energy Solution