**C:\Users\jeremy\AppData\Local\Microsoft\Windows\Temporary Internet Files\Content.Word\CMTA logo_Energy Solutions New.tif**

**Project Construction Field Report**

Project Name: Nelson County Schools – Guaranteed Energy Savings Contract – Bloomfield Middle, Bloomfield Elementary, and Nelson County High School.

Date: 04/27/2017

Contractor: Intertech Mechanical, Freedom Electric, ECT Controls, Blanton Electrical

Distribution: Kevin Mattingly; Vince Paul; Troy Blanton; Tony Humphrey; Adam Pierce; Jon Gasser

**Work Completed (04/17 – 04/21):**

*Freedom- (Electrical)*

*Middle School:*

* LED tube installations and ballast removals (4 lamp fixtures) were performed and completed for Science and Computer Classrooms, Library, Office Area, Cafeteria and Kitchen Areas.
* Repairs were made to broken football field scoreboard ciruit.









*Intertech Mechanical:*

*Bloomfield Middle School:*

* Installed geothermal piping tracer wire.
* Backfilled sand bedding.
* Installed caution tape on top of sand bedding.
* Completed back filling of geothermal lateral piping trench.
* Buried piping connection points were identified with wood post on each end of piping runs.







**Work to be completed (05/01 – 05/04):**

*Freedom – (Electrical)*

* To continue after hours work for Bloomfield Middle and Elementary Schools (lighting).

*Blanton Electric:*

* To begin lighting lamp change outs and ballast removal at Nelson County High School; Monday evening after hours (5/1).

**Safety Items:**

*Site Review:*

* Daily site review walk through were completed; no hazardous conditions to report.
* Contractors were wearing appropriate PPE for their assigned task, and hard hats were worn at all times.

*Weekly Tool Box Safety Talks:*

* Top Four Construction Hazards (OSHA Quick Card) was read to all onsite members for Freedom Electrical and Intertech Mechanical, and was documented to the Project Safety Manual.

**Other items:**

* Mike King Landscaping was onsite (04/27) at Middle School to provide a quote for final grading, seeding, and replacement of gravel area around mechanical fencing.

End of report.

Mike McNair

Construction Project Manager

CMTA Energy Solution