## Sheet1
THOMAS NELSON HIGH SCHOOL AUDITORIUM
CHANGE ORDER REQUESTS/Status
Log as of 8/3/17
NO. | DESCRIPTION | ADD | DEDUCT | TOTAL C/O | STATUS | C/O NUMBER | Approval Date
1 | Proposal Request 2 for turndown sidewalk - Chambers Painting & Structural Steel | $520.00 $6,390.00 |  | 6910 | PENDING | 7,8
2 | Proposal Request 3 to remove and relay brick in area 25 x 3 bricks high | 2214.26 |  | 2214.26 | ACCEPTED | 1 | 2017-01-17
3 | Delete brick on west wall and install horizontal metal siding. Swift Roofing and EdgarBelle | 4738 | 653.33 | 4084.67 | ACCEPTED | 2,3 | 2017-04-25
4 | Fire treated plywood with paint finish RFP 6 | $3,743.25 $170.00 |  | 3913.25 | ACCEPTED | 4,5 | 2017-04-25
5 | Install aluminum and paint per RFP 7 | $363.00 $85.00 |  | 448 | Verbally approved, but may delete paint scope upon review in field.
6 | Conceal pendant sprinklers per RFP 4 | 978 |  | 978 | ACCEPTED | 6
7 | Change projection screen from front projection screen to rear projection screen per RFP 10 | $1,764.54 $2,614.00 |  | 4378.54 | Recommend approval if amount remains the same; conditions found in field during installation may require some additional cost | 11, 12 | 2017-07-18
8 | RFP 9 install owner provided ceramic tile | 582 |  | 582 | Fixes unfinished condition at cafeteria door; recommend approval | 10 | 2017-07-18
9 | RFP 11 Install emergency egress fixtures | 2955 |  | 2955 | Required by building inspector; recommend approval | 9
10 | Replace pea gravel with concrete | 953.06 |  | 953.06 | Recommend approval |  | 2017-07-18
12 | Frame and drywall at new Wash Room 214 | 350 |  | 350 | Incorrectly attributed to TNHS, see #11 | 1A
11 | Credit change order 1A - applied to wrong job | -350 |  | -350 | Recommend approval | 13 | 2017-07-18
12 | Floor prep for floor-mounted egress lightng | $775 (estimated; no COR yet) |  | 775 | Will likely recommend approval, pending review of COR
|  |  | Total: | 28191.78 | 1% of contract value of $2,819,045.53