## Sheet1
NELSON COUNTY EARLY LEARNING CENTER PHASE 2
CHANGE ORDER REQUEST
Log as of 8/3/17
NO. | DESCRIPTION | ADD | DEDUCT | TOTAL C/O | STATUS | C/O NUMBER | Approval Date
1 | Credit to remove 5/8" plywood and sleepers over the shingle roof area and Add to install new wood blocking to the vented nail base | 4096.53 | -8240 | -4143.47 | ACCEPTED | 1 & 2 | 2016-08-16
2 | Hardie plank custom color - 2 Options per Proposal Request #1 | $39,213.00 $45,351.00 |  |  | DECLINED | DECLINED | N/A
3 | Relocate power and data for new window Proposal Request #3 | 1350 |  | 1350 | ACCEPTED | 16
4 | Remove existing gutters, extend the T.P.O. single ply roofing membrane up to the existing metal roof panels. | 4995 |  | 4995 | ACCEPTED | 6 | 2017-02-22
5 | Proposal Request #2 Casework changes- Three Options | 345.75 |  | 345.75 | ACCEPTED | 4 | 2017-01-17
6 | New telephone conduit at parking lot | 5811.74 |  | 5811.74 | ACCEPTED | 5 | 2017-01-17
7 | Install new 3" x 4" downspout from existing downspout out to corner of the building per Proposal Request #4 | 1066.34 |  | 1066.34 | ACCEPTED | 3 | 2017-01-17
8 | Credit for removal of VCT per ASI 3 | 888.26 |  | 888.26 | ACCEPTED | 8,9 | 2017-04-25
9 | RFP 8 - Demo existing floor tile, install new VCT and base | $2,208.75 $3,038.00 |  | 5246.75 | ACCEPTED | 8,9 | 2017-04-25
10 | Work in 3 mechanical closets | $581.13 $932.00 $1,619.00 |  | 3132.13 | Verbal approval; COs prepared for board review | 7,10, 11 | 2017-06-20
11 | Eliminate window film |  | -500 | -500 | Recommend approval
12 | RFP 10 - Modification of steel rail design | $7,166.00 $1,700.00 |  | 8866 | Recommend approval | 12, 13 | 1700 app 6/20/17
13 | RFP 11- RIP RAP at the end of splash block | 3663.9 |  | 3663.9 | Recommend approval | 15 | 2017-06-20
14 | Frame and drywall at new Wash Room 214 | 350 |  | 350 | Due to paperwork error this was originally attributed to TNHS; will be credited there. | 14 | 2017-06-20
|  |  | Total: | 31072.4 | 1.3%of contract value of $2,384,922.33