## Sheet1
Nelson County Superintendent Search Timeline
Dates | All dates subject to change
2017-10-17 | Organizational meeting
2017-11-13 | Staff, Parent, Community Survey window opens
2017-11-30 | Community Forum 6 - 7:30 - Nelson County High School
2017-12-08 | Survey window closes
2017-12-19 | Board Work Session: Establish candidate criteria and desired qualities
2018-01-02 | Position posted - Advertisement begins
2018-02-26 | Application deadline/Screening Committee work begins
2018-03-16 | Screening committee recommendations due to BOE
2018-03-20 | Board Work Session: Finalists selected
2018-03-21 | Finalist names made public
3/26-29/2018 | Interviews/finalists showcase
4/9-13/2018 | Board Work Session(s): Deliberation / decision / contract negotiations
2018-04-17 | Appointment of Superintendent.