## Understanding Continuous Improvement: Goals, Objectives, Strategies and Activities

**Rationale**: The development of goals and objectives to be obtained through strategies and activities is an essential component of executing a continuous improvement plan. In short, the Needs Assessment completed during Phase II expresses the school or district’s CURRENT STATE, while goals, objectives, strategies and activities should succinctly plot the school or district’s course to their DESIRED STATE. Here are the operational definitions of each:

**Goal**: Long-term target based on Kentucky Board of Education Goals. Schools may supplement with individual or district goals.

**Objective**: Short-term target to be attained by the end of the current school year.

**Strategy**: Research-based approach based on the 6 Key Core Work Processes designed to systematically address the process, practice or condition that the school/district will focus its efforts upon in order to reach its goals/objectives.

**Activity**: The actionable steps used to deploy the chosen strategy.

**Key Core Work Processes**: A series of processes that involve the majority of an organization’s workforce and relate to its core competencies. These are the factors that determine an organization’s success and help it prioritize areas for growth.

Guidelines for Building an Improvement Plan

* There are 5 required District Goals: Proficiency, Gap, Graduation rate, Growth, and Transition readiness.
* There are 4 required school-level goals:   
  For elementary/middle school: Proficiency, Gap, Growth, and Transition readiness.  
  For high school: Proficiency, Gap, Graduation rate, and Transition readiness.
* There can be multiple objectives for each goal.
* There can be multiple strategies for each objective.
* There can be multiple activities for each strategy.

## 1: Proficiency

State your *Proficiency* **Goal**

| Goal 1: By 2020, Vine Grove Elementary will increase the combined (reading and math) percentage of proficient/distinguished students to 79%. | | | | | |
| --- | --- | --- | --- | --- | --- |
| Which **Strategy** will the school/district use to address this goal? *(The Strategy can be based upon the six Key Core Work Processes listed below or another research-based approach. Provide justification and/or attach evidence for why the strategy was chosen.)*   * [KCWP 1: Design and Deploy Standards](http://education.ky.gov/school/csip/Documents/KCWP%201%20DesignandDeployStandards.pdf) * [KCWP 2: Design and Deliver Instruction](http://education.ky.gov/school/csip/Documents/KCWP%202%20DesignandDeliverInstruction.pdf) * [KCWP 3: Design and Deliver Assessment Literacy](http://education.ky.gov/school/csip/Documents/KCWP%203%20DesignandDeliverAssessmentLiteracy.pdf) * [KCWP 4: Review, Analyze and Apply Data](http://education.ky.gov/school/csip/Documents/KCWP%204%20ReviewAnalyzeApplyData.pdf) * [KCWP 5: Design, Align and Deliver Support](http://education.ky.gov/school/csip/Documents/KCWP%205%20DesignAlignDeliverSupport.pdf) * [KCWP 6: Establishing Learning Culture and Environment](http://education.ky.gov/school/csip/Documents/KCWP%206%20EstablishingLearningCultureandEnvironment.pdf) | | Which **Activities** will the school/district deploy based on the strategy or strategies chosen? *(The links to the Key Core Work Processes activity bank below may be a helpful resource. Provide a brief explanation or justification for the activity.*   * [KCWP1: Design and Deploy Standards - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%201%20DesignandDeployStandards_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP2: Design and Deliver Instruction - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%202%20DesignandDeliverInstruction_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP3: Design and Deliver Assessment Literacy - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%203%20DesignandDeliverAssessmentLiteracy_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP4: Review, Analyze and Apply Data - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%20%204%20Review%2c%20Analyze%2c%20and%20Apply%20Data_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP5: Design, Align and Deliver Support - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%205%20DesignAlignDeliverSupport_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP6: Establishing Learning Culture and Environment - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%206%20EstablishingLearningCultureandEnvironment_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) | Identify the timeline for the activity or activities, the person(s) responsible for ensuring the fidelity of the activity or activities, and necessary funding to execute the activity or activities. | | |
| Objective | Strategy | Activities to deploy strategy | Measure of Success and Responsible Person(s) | Progress Monitoring Date & Notes | Funding |
| Objective 1:  By 2019, 77 % of Vine Grove students will score at or above proficiency in combined reading and math. | [KCWP 2: Design and Deliver Instruction](http://education.ky.gov/school/csip/Documents/KCWP%202%20DesignandDeliverInstruction.pdf) | Ensure that curricular delivery and assessment measures provide for all pertinent information needs for students.   * *Literacy First* (Literacy Process for Grades 1-2) * *iRead* (Supplemental individualized phonics for 1-2) * *Triumph Learning* (Supplemental ELA Instruction) * *LEAD 21*(Reading Program for 2-5) * Curriculum Associates: *Ready Common Core* (Supplemental ELA Program for 2-5) * *Edgenuity: Pathblazer* (Online differentiated program for 1-5) * *Measures of Academic Progress* (Assessment for 1-5) * *Triand* (Online resource tool for Common Assessments) * *REFLEX* (Supplemental online math resource for 1-5) * *Everyday Math* (Core Math Program for 1-5) * *Teachtci* (Online accompaniment to integrated curriculum) | ***Measure of Success***  Walk-throughs  Lesson Plans  Curriculum Guides  My Data First  *MAP Results*  Benchmark Data  ***Responsible Persons***  Leadership Team  Teachers | May 2018  December 2018 | Title I  Textbook/  Instructional  PPA  District  Funds |

## 2: Gap

State your *Gap* **Goal**

| Goal 2: By 2020, Vine Grove Elementary School will increase the combined (reading and math) proficiency ratings of the non-duplicated gap students to 76%. | | | | | |
| --- | --- | --- | --- | --- | --- |
| Which **Strategy** will the school/district use to address this goal? *(The Strategy can be based upon the six Key Core Work Processes listed below or another research-based approach. Provide justification and/or attach evidence for why the strategy was chosen.)*   * [KCWP 1: Design and Deploy Standards](http://education.ky.gov/school/csip/Documents/KCWP%201%20DesignandDeployStandards.pdf) * [KCWP 2: Design and Deliver Instruction](http://education.ky.gov/school/csip/Documents/KCWP%202%20DesignandDeliverInstruction.pdf) * [KCWP 3: Design and Deliver Assessment Literacy](http://education.ky.gov/school/csip/Documents/KCWP%203%20DesignandDeliverAssessmentLiteracy.pdf) * [KCWP 4: Review, Analyze and Apply Data](http://education.ky.gov/school/csip/Documents/KCWP%204%20ReviewAnalyzeApplyData.pdf) * [KCWP 5: Design, Align and Deliver Support](http://education.ky.gov/school/csip/Documents/KCWP%205%20DesignAlignDeliverSupport.pdf) * [KCWP 6: Establishing Learning Culture and Environment](http://education.ky.gov/school/csip/Documents/KCWP%206%20EstablishingLearningCultureandEnvironment.pdf) | | Which **Activities** will the school/district deploy based on the strategy or strategies chosen? *(The links to the Key Core Work Processes activity bank below may be a helpful resource. Provide a brief explanation or justification for the activity.*   * [KCWP1: Design and Deploy Standards - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%201%20DesignandDeployStandards_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP2: Design and Deliver Instruction - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%202%20DesignandDeliverInstruction_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP3: Design and Deliver Assessment Literacy - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%203%20DesignandDeliverAssessmentLiteracy_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP4: Review, Analyze and Apply Data - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%20%204%20Review%2c%20Analyze%2c%20and%20Apply%20Data_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP5: Design, Align and Deliver Support - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%205%20DesignAlignDeliverSupport_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP6: Establishing Learning Culture and Environment - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%206%20EstablishingLearningCultureandEnvironment_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) | Identify the timeline for the activity or activities, the person(s) responsible for ensuring the fidelity of the activity or activities, and necessary funding to execute the activity or activities. | | |
| Objective | Strategy | Activities to deploy strategy | Measure of Success and Responsible Person(s) | Progress Monitoring Date & Notes | Funding |
| Objective 1:  By 2019, Vine Grove Elementary’s non-duplicated gap group will increase the reading proficiency ratings from 58.1% to 68.9%.  Objective 2:  By 2019, Vine Grove Elementary’s non-duplicated gap group will increase the math proficiency ratings from 56.5% to 71.2%. | [KCWP 2: Design and Deliver Instruction](http://education.ky.gov/school/csip/Documents/KCWP%202%20DesignandDeliverInstruction.pdf)  [KCWP 4: Review, Analyze and Apply Data](http://education.ky.gov/school/csip/Documents/KCWP%204%20ReviewAnalyzeApplyData.pdf)  [KCWP 2: Design and Deliver Instruction](http://education.ky.gov/school/csip/Documents/KCWP%202%20DesignandDeliverInstruction.pdf)  [KCWP 4: Review, Analyze and Apply Data](http://education.ky.gov/school/csip/Documents/KCWP%204%20ReviewAnalyzeApplyData.pdf) | Ensure ongoing professional development in the area of best practice/ high yield instructional strategies to aid in curricular  adjustments when students fail to meet mastery. [*Green River Regional Educational Cooperative*](https://www.google.com/url?sa=t&rct=j&q=&esrc=s&source=web&cd=1&cad=rja&uact=8&ved=0ahUKEwj87PSa2fjXAhXMPCYKHdhqDKAQFggnMAA&url=http%3A%2F%2Fwww.grrec.org%2F&usg=AOvVaw1qrMHQDUTKq--KmFtwQEAW)  * Professional Learning Communities * Curriculum Planning * *Kagan* (Engagement) * Character Education   Ensure that formative assessment practices allow students to understand where they are going, where they currently are, and how they can close the gap.   * *Measures of Academic Progress* (Assessment for 1-5) * Literacy First (Literacy Process for 1-2) * Curriculum Associates: *i-Ready* (Reading Diagnostic) * *Triand* (Online resource tool for Common Assessments) * Benchmark Assessments (LEAD 21) * Thoughtful Education (Best practice tools and strategies) * Enrichment-Differentiated Instruction in Flexible Groups (1-3) * ESS Daytime Waiver (Reading ) * KSI Specialist (Targeting students 1-5 in Tier 2 and 3) * Data Binders for Goal Setting * Title I Extension After-school Reading and Homework Program (3-5)   Ensure ongoing professional development in the area of best practice/ high yield instructional strategies to aid in curricular  adjustments when students fail to meet mastery. [*Green River Regional Educational Cooperative*](https://www.google.com/url?sa=t&rct=j&q=&esrc=s&source=web&cd=1&cad=rja&uact=8&ved=0ahUKEwj87PSa2fjXAhXMPCYKHdhqDKAQFggnMAA&url=http%3A%2F%2Fwww.grrec.org%2F&usg=AOvVaw1qrMHQDUTKq--KmFtwQEAW)  * PLC Training * Curriculum Planning * *Kagan* (Engagement) * *Character Education*   Ensure that formative assessment practices allow students to understand where they are going, where they currently are, and how they can close the gap.   * *Measures of Academic Progress* (Assessment for 1-5) * *Triand* (Common Assessments) * Thoughtful Education (Best practice tools and strategies) * Enrichment-Differentiated Instruction in Flexible Groups (1-3) * ESS Daytime Waiver (Math) * KSI Specialist (Targeting students in 1-5 in Tier 2 and Tier 3) * Data Binders for Goal Setting | ***Measure of Success***  PLC Agenda  Professional Learning Plan  Walkthroughs  ***Responsible Persons***  Leadership Team  Teachers  ***Measure of Success***  Walk-throughs  Lesson Plans  Curriculum Guides  My Data First  MAP Data  Benchmark Data  ESS Progress Reports  ***Responsible Persons***  Leadership Team  Teachers  ***Measure of Success***  PLC Agenda  Professional Learning Plan  Walkthroughs  ***Responsible Persons***  Leadership Team  Teachers  ***Measure of Success***  Walk-throughs  Lesson Plans  Curriculum Guides  MAP Data  Benchmark Data  ESS Progress Reports  ***Responsible Persons***  Leadership Team  Teachers | February 2018  April 2018  September 2018  February 2018  April 2018  September 2018 | District  Funds  Title I  ESS  Professional  Learning  District  Funds  Title I  ESS  Professional  Learning |

## 3: Graduation rate

State your *Graduation rate* **Goal**

| Goal 3: N/A | | | | | |
| --- | --- | --- | --- | --- | --- |
| Which **Strategy** will the school/district use to address this goal? *(The Strategy can be based upon the six Key Core Work Processes listed below or another research-based approach. Provide justification and/or attach evidence for why the strategy was chosen.)*   * [KCWP 1: Design and Deploy Standards](http://education.ky.gov/school/csip/Documents/KCWP%201%20DesignandDeployStandards.pdf) * [KCWP 2: Design and Deliver Instruction](http://education.ky.gov/school/csip/Documents/KCWP%202%20DesignandDeliverInstruction.pdf) * [KCWP 3: Design and Deliver Assessment Literacy](http://education.ky.gov/school/csip/Documents/KCWP%203%20DesignandDeliverAssessmentLiteracy.pdf) * [KCWP 4: Review, Analyze and Apply Data](http://education.ky.gov/school/csip/Documents/KCWP%204%20ReviewAnalyzeApplyData.pdf) * [KCWP 5: Design, Align and Deliver Support](http://education.ky.gov/school/csip/Documents/KCWP%205%20DesignAlignDeliverSupport.pdf) * [KCWP 6: Establishing Learning Culture and Environment](http://education.ky.gov/school/csip/Documents/KCWP%206%20EstablishingLearningCultureandEnvironment.pdf) | | Which **Activities** will the school/district deploy based on the strategy or strategies chosen? *(The links to the Key Core Work Processes activity bank below may be a helpful resource. Provide a brief explanation or justification for the activity.*   * [KCWP1: Design and Deploy Standards - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%201%20DesignandDeployStandards_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP2: Design and Deliver Instruction - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%202%20DesignandDeliverInstruction_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP3: Design and Deliver Assessment Literacy - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%203%20DesignandDeliverAssessmentLiteracy_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP4: Review, Analyze and Apply Data - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%20%204%20Review%2c%20Analyze%2c%20and%20Apply%20Data_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP5: Design, Align and Deliver Support - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%205%20DesignAlignDeliverSupport_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP6: Establishing Learning Culture and Environment - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%206%20EstablishingLearningCultureandEnvironment_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) | Identify the timeline for the activity or activities, the person(s) responsible for ensuring the fidelity of the activity or activities, and necessary funding to execute the activity or activities. | | |
| Objective | Strategy | Activities to deploy strategy | Measure of Success and Responsible Person(s) | Progress Monitoring Date & Notes | Funding |
| Objective 1: |  |  |  |  |  |
|  |  |  |  |
|  |  |  |  |
| Objective 2: |  |  |  |  |  |
|  |  |  |  |
|  |  |  |  |

## 4: Growth

State your *Growth* **Goal**

| Goal 4: By 2020, Vine Grove Elementary will increase the average combined reading and math growth in grades 3–5 from to 77%. | | | | | |
| --- | --- | --- | --- | --- | --- |
| Which **Strategy** will the school/district use to address this goal? *(The Strategy can be based upon the six Key Core Work Processes listed below or another research-based approach. Provide justification and/or attach evidence for why the strategy was chosen.)*   * [KCWP 1: Design and Deploy Standards](http://education.ky.gov/school/csip/Documents/KCWP%201%20DesignandDeployStandards.pdf) * [KCWP 2: Design and Deliver Instruction](http://education.ky.gov/school/csip/Documents/KCWP%202%20DesignandDeliverInstruction.pdf) * [KCWP 3: Design and Deliver Assessment Literacy](http://education.ky.gov/school/csip/Documents/KCWP%203%20DesignandDeliverAssessmentLiteracy.pdf) * [KCWP 4: Review, Analyze and Apply Data](http://education.ky.gov/school/csip/Documents/KCWP%204%20ReviewAnalyzeApplyData.pdf) * [KCWP 5: Design, Align and Deliver Support](http://education.ky.gov/school/csip/Documents/KCWP%205%20DesignAlignDeliverSupport.pdf) * [KCWP 6: Establishing Learning Culture and Environment](http://education.ky.gov/school/csip/Documents/KCWP%206%20EstablishingLearningCultureandEnvironment.pdf) | | Which **Activities** will the school/district deploy based on the strategy or strategies chosen? *(The links to the Key Core Work Processes activity bank below may be a helpful resource. Provide a brief explanation or justification for the activity.*   * [KCWP1: Design and Deploy Standards - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%201%20DesignandDeployStandards_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP2: Design and Deliver Instruction - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%202%20DesignandDeliverInstruction_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP3: Design and Deliver Assessment Literacy - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%203%20DesignandDeliverAssessmentLiteracy_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP4: Review, Analyze and Apply Data - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%20%204%20Review%2c%20Analyze%2c%20and%20Apply%20Data_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP5: Design, Align and Deliver Support - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%205%20DesignAlignDeliverSupport_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP6: Establishing Learning Culture and Environment - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%206%20EstablishingLearningCultureandEnvironment_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) | Identify the timeline for the activity or activities, the person(s) responsible for ensuring the fidelity of the activity or activities, and necessary funding to execute the activity or activities. | | |
| Objective | Strategy | Activities to deploy strategy | Measure of Success and Responsible Person(s) | Progress Monitoring Date & Notes | Funding |
| Objective 1: By 2019, Vine Grove Elementary will increase the combined reading and math growth in grades 3-5 from 71.1% to 74%. | [KCWP 5: Design, Align and Deliver Support](http://education.ky.gov/school/csip/Documents/KCWP%205%20DesignAlignDeliverSupport.pdf) | Utilize daily formative data collection tools, benchmark data, summative data, non‐academic data, formative and summative teacher observations, and/or learning walk details to ensure high levels of teacher effectiveness and student achievement.   * KSI Specialist (Targeting 1-5 students in Tier 2 and Tier 3) * ESS Daytime Waiver (Reading and Math) * Math 180 (Intervention program for 5th grade) * Dreambox (Intervention math program for 1-5) * Gifted and Talented * ELL * Technology Integration (1:1 Classrooms) * Professional Learning Communities * Title I Extension After-school Homework and Reading Program (3-5) * *Learning A to Z* (Supplemental resource to core programs) * Assessments (*MAP,* Benchmarks, Literacy First, i-Ready) | ***Measure of Success***  Walk-throughs  Lesson Plans  MAP Data  Benchmark Data  ESS Progress Reports  KSI Monitoring  ***Responsible Persons***  Leadership Team  Teachers  ESS Coordinator  Title I Coordinator  ELL Staff  GT Teacher | February 2018  April 2018  September 2018 | District  Funds  Title I  ESS  Professional  Learning |

## 5: Transition readiness

State your *Transition readiness* **Goal**

| Goal 5: By 2020, Vine Grove Elementary School will increase the percentage of students successfully transitioning at entry/exit points. | | | | | |
| --- | --- | --- | --- | --- | --- |
| Which **Strategy** will the school/district use to address this goal? *(The Strategy can be based upon the six Key Core Work Processes listed below or another research-based approach. Provide justification and/or attach evidence for why the strategy was chosen.)*   * [KCWP 1: Design and Deploy Standards](http://education.ky.gov/school/csip/Documents/KCWP%201%20DesignandDeployStandards.pdf) * [KCWP 2: Design and Deliver Instruction](http://education.ky.gov/school/csip/Documents/KCWP%202%20DesignandDeliverInstruction.pdf) * [KCWP 3: Design and Deliver Assessment Literacy](http://education.ky.gov/school/csip/Documents/KCWP%203%20DesignandDeliverAssessmentLiteracy.pdf) * [KCWP 4: Review, Analyze and Apply Data](http://education.ky.gov/school/csip/Documents/KCWP%204%20ReviewAnalyzeApplyData.pdf) * [KCWP 5: Design, Align and Deliver Support](http://education.ky.gov/school/csip/Documents/KCWP%205%20DesignAlignDeliverSupport.pdf) * [KCWP 6: Establishing Learning Culture and Environment](http://education.ky.gov/school/csip/Documents/KCWP%206%20EstablishingLearningCultureandEnvironment.pdf) | | Which **Activities** will the school/district deploy based on the strategy or strategies chosen? *(The links to the Key Core Work Processes activity bank below may be a helpful resource. Provide a brief explanation or justification for the activity.*   * [KCWP1: Design and Deploy Standards - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%201%20DesignandDeployStandards_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP2: Design and Deliver Instruction - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%202%20DesignandDeliverInstruction_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP3: Design and Deliver Assessment Literacy - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%203%20DesignandDeliverAssessmentLiteracy_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP4: Review, Analyze and Apply Data - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%20%204%20Review%2c%20Analyze%2c%20and%20Apply%20Data_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP5: Design, Align and Deliver Support - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%205%20DesignAlignDeliverSupport_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP6: Establishing Learning Culture and Environment - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%206%20EstablishingLearningCultureandEnvironment_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) | Identify the timeline for the activity or activities, the person(s) responsible for ensuring the fidelity of the activity or activities, and necessary funding to execute the activity or activities. | | |
| Objective | Strategy | Activities to deploy strategy | Measure of Success and Responsible Person(s) | Progress Monitoring Date & Notes | Funding |
| Objective 1:  By 2019, Vine Grove Elementary will have 90% of entry level students who successfully transition into first grade.  Objective 2:  By 2019, Vine Grove Elementary will have 85% of students who successfully transition into middle school. | [KCWP 5: Design, Align and Deliver Support](http://education.ky.gov/school/csip/Documents/KCWP%205%20DesignAlignDeliverSupport.pdf) | Develop school culture supports, both academic and behavioral, to promote and support learning for all.   * Kindergarten Transition Day * Open-House * Title I Parent Engagement Nights * FOR-YOU Resource Center * Classroom Guidance * Brag Tags * Parent Institute Newsletters (Tips for student success) | ***Measure of Success***  Transition Schedules  Sign-in Sheets  Classroom Guidance Schedules  ***Responsible Persons***  Leadership Team  FRYSC Director  Title I Coordinator | March 2018-May 2018 (Transitions)  August 2018 (Open-House) | Title I  PPA  FRYSC |
| Develop school culture supports, both academic and behavioral, to promote and support learning for all.   * JTA Transition Day (Middle School transition) * EC3 Field Trip (Explore pathways) * Open-House * Title I Parent Engagement Nights * FOR-YOU Resource Center * Classroom Guidance * Brag Tags * Parent Institute Newsletters (Tips for student success) | ***Measure of Success***  Transition Schedules  Sign-in Sheets  Classroom Guidance Schedules  ***Responsible Persons***  Leadership Team  FRYSC Director  Title I Coordinator | March 2018-May 2018 (Transitions)  August 2018 (Open-House) | Title I  PPA  FRYSC |

## 6: Other (optional)

State your *Other* **Goal** (optional)

| Goal 6: | | | | | |
| --- | --- | --- | --- | --- | --- |
| Which **Strategy** will the school/district use to address this goal? *(The Strategy can be based upon the six Key Core Work Processes listed below or another research-based approach. Provide justification and/or attach evidence for why the strategy was chosen.)*   * [KCWP 1: Design and Deploy Standards](http://education.ky.gov/school/csip/Documents/KCWP%201%20DesignandDeployStandards.pdf) * [KCWP 2: Design and Deliver Instruction](http://education.ky.gov/school/csip/Documents/KCWP%202%20DesignandDeliverInstruction.pdf) * [KCWP 3: Design and Deliver Assessment Literacy](http://education.ky.gov/school/csip/Documents/KCWP%203%20DesignandDeliverAssessmentLiteracy.pdf) * [KCWP 4: Review, Analyze and Apply Data](http://education.ky.gov/school/csip/Documents/KCWP%204%20ReviewAnalyzeApplyData.pdf) * [KCWP 5: Design, Align and Deliver Support](http://education.ky.gov/school/csip/Documents/KCWP%205%20DesignAlignDeliverSupport.pdf) * [KCWP 6: Establishing Learning Culture and Environment](http://education.ky.gov/school/csip/Documents/KCWP%206%20EstablishingLearningCultureandEnvironment.pdf) | | Which **Activities** will the school/district deploy based on the strategy or strategies chosen? *(The links to the Key Core Work Processes activity bank below may be a helpful resource. Provide a brief explanation or justification for the activity.*   * [KCWP1: Design and Deploy Standards - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%201%20DesignandDeployStandards_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP2: Design and Deliver Instruction - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%202%20DesignandDeliverInstruction_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP3: Design and Deliver Assessment Literacy - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%203%20DesignandDeliverAssessmentLiteracy_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP4: Review, Analyze and Apply Data - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%20%204%20Review%2c%20Analyze%2c%20and%20Apply%20Data_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP5: Design, Align and Deliver Support - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%205%20DesignAlignDeliverSupport_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) * [KCWP6: Establishing Learning Culture and Environment - Continuous Improvement Activities](http://education.ky.gov/school/csip/Documents/KCWP%206%20EstablishingLearningCultureandEnvironment_CONTINUOUS%20IMPROVEMENT%20Activities.pdf) | Identify the timeline for the activity or activities, the person(s) responsible for ensuring the fidelity of the activity or activities, and necessary funding to execute the activity or activities. | | |
| Objective | Strategy | Activities to deploy strategy | Measure of Success and Responsible Person(s) | Progress Monitoring Date & Notes | Funding |
| Objective 1: |  |  |  |  |  |
|  |  |  |  |
|  |  |  |  |
| Objective 2: |  |  |  |  |  |
|  |  |  |  |
|  |  |  |  |