Peck Flannery Gream Warren Architects, LLC

112 North Main St.		Elizabethtown, Kentucky 42701

Phone: 270-765-2147		Fax: 270-765-2148

Email: lgream@pfgw.org		Website: www.pfgw.net

March 10, 2009

# Ms. Nannette Johnston

Hardin County Board of Education

65 W.A. Jenkins Rd.

Elizabethtown, KY 42701

RE:	Hardin County Schools

(Report of Projects in Progress)

Dear Nannette:

Please consider the following as a report on projects which our firm is presently providing Architecture/Engineering services.

I have one action item (a BG-4) for the Hardin County School Board’s consideration/approval this month.

1.    CREEKSIDE ELEMENTARY SCHOOL:

Site Work Bid Package “A” (Phillips Brothers Construction):     Work not presently complete under this contract consists of verification of stand of grass growth.

* An agenda item since December 2005

- RINEYVILLE ELEMENTARY SCHOOL:

Building Bid Package “A” (Whittenberg Construction):   Remaining work consists of completion of punch list.  The bulk of the remaining work consists of site work that will be performed in early spring.

3.    HEARTLAND ELEMENTARY SCHOOL:

Building Bid Package “A” (Morel Construction Company) :  Remaining work on this project consists of completion of site punch list items. (verification of grass growth, erosion control and drainage issues) to be addressed as weather conditions permit.

- NORTH HARDIN HIGH SCHOOL PHASE TWO and THREE RENOVATIONS

(2008- 2009):

McNutt Construction:  Work is progressing on phase two portions of the project. Charlie Jones will present construction progress during the March 19th Board meeting.

5.    CENTRAL OFFICE ANNEX (Renovation of B & W Metals Building):

BCD Inc: BCD and its sub-contractors are working on architect/engineer punch list for the HCEC-TV area.

6.    TORNADO DAMAGES TO CENTRAL HARDIN HIGH SCHOOL

Main Student Entry (McNutt Construction):  Mark McNutt reports that this project will be complete by March 24.

7.    TORNADO DAMAGES TO CENTRAL HARDIN HIGH SCHOOL

Print Shop and Buildings & Grounds Maintenance Work Area (McNutt Construction):

Mark McNutt reports that this project will be complete near the end of May. At present the demolition work has been performed, the footings and foundation grade beams have been poured and the rock base is in place.

8. REPAIRS TO FREEZER BUILDING FLOOR FOR DIVISION OF CHILD NUITRITION.

Board Action Item:

A BG-4 is being forwarded for board approval in the March Board meeting.

Please give me a call if you have questions regarding this report.

Sincerely,

Larry Gream

c: 	 Gary Milby

David Wyatt