| Priority Need | Goal (Addresses the Priority Need) |
| --- | --- |
| To develop and implement a systematic process for monitoring district and school improvement efforts and performance. To facilitate the development of professional learning communities beyond the learning club model established through Thoughtful Education. To develop a process with procedures that outline show schools should identify needs and request additional resource allocations. | The district will develop a systematic process for monitoring school and district improvement efforts in the following areas: professional development and evaluation, implementation of research-based instructional practices, implementation of school-wide instructional discipline programs, successful school council implementation, provision of equitable access to a common academic core, effective lesson planning, and school/district improvement planning. Each school will a professional learning community model that allows for discussion of student needs, analysis and exploration of curriculum, instructional practices and assessment, and interventions for students at-risk of not meeting proficiency. District and school leadership will develop a deeper understanding of all available resources and apply this knowledge for more efficient and effective decision-making practices. |
| Causes and Contributing Factors | Objectives with Measures of Success |
| The district has not developed nor implemented a systematic process for monitoring district initiatives, instructional practices, and overall performance of schools. The district has not provided adequate support in the development of professional learning communities. A systematic process with procedures outlining how schools identify needs and request resources to equitably support school initiatives not covered by basic allocations are not in place. | By January 2009, district leadership will have developed, communicated and implemented procedures for monitoring professional development and evaluation, implementation of research-based instructional practices, implementation of school-wide instructional discipline programs, successful school council implementation, provision of equitable access to a common academic core, effective lesson planning, and school/district improvement planning. By March 2009, each school will have developed a model for implementing professional learning communities wherein 100% of instructional staff are active members. By February 2009, a plan for requesting additional allocations/resources at the school-level will be developed, communicated to stakeholders, and implemented by district leadership. |

Strategies/Activities

| Obj. Label | SISI Standard | Strategy/Activity | Expected Impact in Terms of Progress and Success | Critical Person(s) Involved | Start Date | End Date | Estimated Resources and Costs | I & I Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| E1.a |  | The superintendent will meet monthly with all principals to ensure: All evaluations are completed according to the district evaluation plan; All principals are monitoring teacher performance and student achievement through classroom walk-throughs; All schools are using data to drive decision-making through the review of progress monitoring data, instructional discipline data, attendance data, walk-through data, and other data points; All principals have an understanding of resource allocation; and, All principals are monitoring the efficient and effective use of Early Release Friday time. | Student achievement will increase as greater accountability occurs at both the district and school level; decisions will be data-driven. | Mike Kenner | Aug. 2008 | May 2009 |  |  |
| E1.b |  | District leadership will bring together representatives from all stakeholder groups to review the vision, mission, and belief statements annually. | All decisions made within the district stay focused on the vision. | Mike Kenner | Aug. 2009 | July 2009 | $200 – General Fund |  |
| E1.c |  | District leadership will attend SBDM meetings in schools and serve as a resource to councils in areas such as: Review of assessment data on a continuous basis Compliance with all state and federal standards Best practice programs Equity of all programs Resource allocation to meet the unique needs of individual students | School councils will function more efficiently and effectively with support from the district level. | District leadership | Aug. 2008 | June 2009 | $500 – General Fund |  |
| E1.d |  | District leadership will facilitate biannual meetings of a Council of Councils with representation from all schools’ councils and the board of education to discuss assessment data, school/district improvement plans, effective allocation of resources, and improvement of student achievement. | Decisions will be grounded in the district mission and vision statements as all stakeholders gain greater awareness of district and school operations. | District leadership | Nov. 2008 | June 2009 | $350 – General Fund |  |
| E1.e |  | Each school council shall submit to the district a plan of parent involvement activities for the year (e.g., Family Reading Night, Family Math Night, Parent Conferences, Leap Start, Orientation meetings, etc.). | Parents will become more active partners in their students’ educations. | Vicki Myers | Aug. 2008 | June 2009 |  |  |
| E1.f |  | District and school leadership will conduct walk-throughs to monitor instructional practices and analyze the results to monitor and guide improvement efforts. | Student achievement will increase as teachers, school leadership and district leadership work to achieve common expectations and use data for decision-making and program improvement. | District and school leadership | Aug. 2008 | May 2009 | $1400 – General Fund |  |
| E1.g |  | District leadership will meet regularly and use various data sources to monitor and revise the CDIP. | Student achievement will increase as teachers, school leadership and district leadership work to achieve common expectations and use data for decision-making and program improvement. | Mike Kenner | Aug. 2008 | May 2009 |  |  |
| E1.h |  | The Director of Special Education will meet regularly with school principals and teaching staff to follow-up on collaboration training and set goals for reaching proficiency for students with disabilities. | Needs of students at-risk of not meeting proficiency will be met more effectively through developmentally-appropriate instructional accommodations and specially designed instruction. | Kim Justice | Aug. 2008 | June 2009 |  |  |
| E2.a |  | Each school will develop and implement a Professional Learning Community model that builds upon the learning club model of Thoughtful Education to analyze and refine professional practice and student achievement. | All will become active participants in school improvement efforts. | Mike Kenner | Oct. 2008 | June 2009 | $6000– District Title I |  |
| E2.b |  | School and district leadership will attend random PLC meetings within schools to monitor their implementation and effectiveness. | Support provided will allow for greater ownership of school improvement at the school level. | District and school leadership | Dec. 2008 | June 2009 |  |  |
| E2.c |  | Teachers will utilize the PLC model to review and refine curriculum, instruction, assessment and to determine student interventions. | All will become active participants in school improvement efforts. | Principals | Dec. 2008 | June 2009 |  |  |
| E3.a |  | District leadership will develop and implement a process and procedures that outline how schools identify needs and request resources to support school needs. The process shall include: needs assessment, timelines for submission of need requests and procedures used to respond to assistance requests. | Resources will be used more efficiently and effectively to meet student learning needs. | District leadership | Aug. 2008 | June 2009 | $200 – General Fund |  |
| E3.b |  | District leadership will form a finance committee to meet monthly for the purpose of ensuring efficient and equitable use of funds. | Resources will be used more efficiently and effectively to meet student learning needs. | District leadership | Aug. 2008 | June 2009 |  |  |
| E3.c |  | The District Finance Committee will develop a request form and rubric to evaluate requests made and communicate it to appropriate stakeholders. | Resources will be used more efficiently and effectively to meet student learning needs. | District Finance Committee | Aug. 2008 | Feb. 2009 | $200 – General Fund |  |