Hardin County Schools Construction Projects Status Report

June 17, 2009

| Project | Contractor | Construction Start Date | Substantial Completion Date | Status |
| --- | --- | --- | --- | --- |
| Rineyville Elementary School | Whittenberg Construction | May 31, 2006 | August 26, 2008 | Remaining work is associated with site issues of acceptable grass growth, addressing of erosion and addressing certain areas of asphalt drainage. |
| Heartland Elementary School | Morel Construction | May/June 2008 | July 15, 2008 | Remaining work is associated with site issues of acceptable grass growth, addressing of erosion and addressing certain areas of asphalt drainage. |
| North Hardin High School Phase 2 and 3 Renovations | McNutt Construction | June 2, 2008 | October 2, 2009 | Major demolition work in progress. |
| Central Office Annex (Renovation of B & W Metals Building) | BCD Inc. | September 8, 2008 | March 14, 2009 | Remaining punch list item consist of addressing utility trench repairs per BCD’s letter. BG-4 anticipated being forwarded to board next month. |
| Main Student Entry (CHHS) | McNutt Construction | Contract dated October 22, 2008 | April 3, 2009 | Small number of punch list items outstanding. Largest item is installation of metal canopy over exit door with associated lighting. |
| Buildings & Grounds and Print Shop | McNutt Construction | Contract dated July 16, 2008 | May 30, 2009 | Print Shop is complete and occupied. Buildings and Grounds portion of building soffits and fascia work under progress. |
| Parkway Elementary School Partial Re-Roof | Swift Roofing | Work to begin onsite July 1, 2009 | August 1, 2009 |  |
| North Hardin High School Partial Re-Roof | Swift Roofing | Work to begin on site approximately July 15, 2009 | September 18, 2009 |  |
| Mulberry-Helm Educational Center Re-Roof | Swift Roofing | Work to begin on site June 24, 2009 | August 1, 2009 |  |
| Bus Garage Renovations | Jenkins-Essex Construction | Anticipate on site work to begin June 22 or 23, 2009 | September 23, 2009 |  |
| HCS Records/Storage | Klienholter Construction | Construction scheduled to begin June 22, 2009 | September 15, 2009 (contract completion date) |  |