Attn.: Phil Moyers							9/3/09

Peck Flannery Gream Warren

Re.: Hardin County Schools

Progress Report

Parkway Elementary:

This project is very near completion all roofing, flashing and sheet metal work is done the only outstanding work is the gravel surfacing on the cafeteria roof.

The 30-day curing period is now over so the installation of the white flood coat and marble chip surfacing can begin, this cure time insures the black cold adhesive does not stain the white flood coat.

The application of the EPDM coating was completed this week, we will be scheduling the installation of the gravel surfacing next week, once completed and the project site has final clean-up we can begin with inspection and close out of this project.

North Hardin HS:

At this time all low roof sections have been torn-off and the base sheet installed, during the demo process all skylights and abandoned roof curbs were removed as noted. Over the next two weeks we will be installing the cap sheet and base flashing allowing the cure time to begin.

Installation of the new roof hatch and ladder is being completed to date, removal of the library / gym roof will follow the cap sheet installation on the low areas. Sheet metal and gravel surfacing will follow.

Mulberry Helm:

This project also is nearing completion all roofing, flashing and sheet metal work is done. The installation of the gravel surfacing will begin mid September once again awaiting cure time.

Installation of two metal canopies are complete the third is awaiting approval, work will soon begin on the reconstruction of the existing canopy along with lighting. Final clean up and inspection will then follow.

Thank You,

Brian Delk

Project Manager