## Sheet1
KBE APPROVAL DATE: FEBRUARY 2016 | [6 empty] | DFP REVISIONS
BOONE COUNTY SCHOOLS DISTRICT FACILITY PLAN | [6 empty] | FINDING NO. 1: JUNE, 2017 |  |  |  | BOLD, RED
[7 empty] | FINDING NO. 2: SEPT., 2019 |  |  |  | BOLD, RED, ITALICS
[7 empty] | FINDING NO. 3: NOV., 2019 |  |  |  | BOLD, RED UNDERLINED
[7 empty] | FINDING NO. 4 DEC., 2020 |  |  |  | BOLD, RED, ITALICS, UNDERLINED
NEXT DFP DUE: FEBRUARY 2020
PLAN OF SCHOOL ORGANIZATION
1. | Current Plan |  |  | K-5, 6-8, 6-12, 9-12
2. | Long Range Plan |  |  | K-5, 6-8, 6-12, 9-12
SCHOOL CENTERS | [6 empty] | Status |  | Organization |  |  | Student Enrollment Capacity
1. | Secondary
| a. | Boone County High School |  |  |  |  | Permanent |  | 9-12 Center |  |  | 1412/999
| b. | Boone County Area Tech. Center |  |  |  |  | Permanent |  | 9-12 Center |  |  | varies
| c. | Conner High School |  |  |  |  | Permanent |  | 9-12 Center |  |  | 1376/1074
| d. | Cooper High School |  |  |  |  | Permanent |  | 9-12 Center |  |  | 1240/1265
| e. | Ryle High School |  |  |  |  | Permanent |  | 9-12 Center |  |  | 1841/1755
| f. | Ignite Institute |  |  |  |  | Permanent |  | 9-12 Center |  |  | new/1000
| g. | Ralph Rush/Staff Development Center |  |  |  |  | Permanent |  | 6-12 Center |  |  | varies
| h. | Boone County Student Services |  |  |  |  | Permanent |  | Center |  |  | varies
2. | Middle
| a. | Ballyshannon Middle School |  |  |  |  | Permanent |  | 6-8 Center |  |  | new/500
| b. | Camp Ernst Middle School |  |  |  |  | Permanent |  | 6-8 Center |  |  | 1043/899
| c. | Conner Middle School |  |  |  |  | Permanent |  | 6-8 Center |  |  | 1177/815
| d. | Gray Middle School |  |  |  |  | Permanent |  | 6-8 Center |  |  | 1089/1005
| e. | Jones Middle School |  |  |  |  | Permanent |  | 6-8 Center |  |  | 740/622
| f | Ockerman Middle School |  |  |  |  | Permanent |  | 6-8 Center |  |  | 922/853
3. | Elementary
| a. | Burlington Elementary School |  |  |  |  | Permanent |  | K-5 Center |  |  | 852/916
| b. | Collins Elementary School |  |  |  |  | Permanent |  | K-5 Center |  |  | 839/672
| c. | Erpenbeck Elementary School |  |  |  |  | Permanent |  | K-5 Center |  |  | 691/800
| d. | Florence Elementary School |  |  |  |  | Permanent |  | K-5 Center |  |  | 660/650
| e. | Goodridge Elementary School |  |  |  |  | Permanent |  | K-5 Center |  |  | 788/653
| f. | Kelly Elementary School |  |  |  |  | Permanent |  | K-5 Center |  |  | 240/402
| g. | Longbranch Elementary School |  |  |  |  | Permanent |  | K-5 Center |  |  | 851/900
| h. | Mann Elementary School |  |  |  |  | Permanent |  | K-5 Center |  |  | 816/900
| i. | New Haven Elementary School |  |  |  |  | Permanent |  | K-5 Center |  |  | 816/954
| j. | North Pointe Elementary School |  |  |  |  | Permanent |  | K-5 Center |  |  | 477/925
| k. | Ockerman Elementary School |  |  |  |  | Permanent |  | K-5 Center |  |  | 784/825
| l. | Stephens Elementary School |  |  |  |  | Permanent |  | K-5 Center |  |  | 642/880
| m. | Thornwilde Elementary School |  |  |  |  | Permanent |  | K-5 Center |  |  | 637/700
| n. | Yealey Elementary School |  |  |  |  | Permanent |  | K-5 Center |  |  | 553/687
CAPITAL CONSTRUCTION PRIORITIES (Schedule within the 2016-2018 Biennium)
1a. | New construction to meet student capacity; further implementation of established programs; or complete approved
| projects constructed in phases. | [9 empty] | Eff. % | Cost Est.
| 1. | Site acquisition for new Elementary School located Central County | [9 empty] | 700000
|  | New 600 700-student elementary school for 50 preschool school students | [5 empty] | 65736 | 76027 | sf. |  | 18492807.48
| 2. | Ryle High School | [6 empty] | 236929 | sf.
Major Addition to include; HVAC improvements; electric and security upgrades; new roadway, restrooms, stairs and circulation
|  | Construct: | 4 | Classrooms |  | 750 | sf. |  | 3000 | sf | 68% | 1078235.2941
|  |  | 4 | Classrooms |  | 800 | sf. |  | 3200 | sf | 68% | 1150117.6471
|  |  | 2 | Science Lab |  | 1500 | sf. |  | 3000 | sf | 68% | 1078235.2941
|  |  | 1 | Science Workroom |  | 245 | sf. |  | 245 | sf | 68% | 88055.8824
|  |  | 1 | Chemical Storage |  | 100 | sf. |  | 100 | sf | 68% | 35941.1765
|  |  | 1 | Resource Classroom |  | 400 | sf. |  | 400 | sf | 68% | 143764.7059
|  |  | 2 | Workroom |  | 350 | sf. |  | 700 | sf | 68% | 251588.2353
|  |  | 1 | Ag Lab |  | 1550 | sf. |  | 1550 | sf | 68% | 557088.2353
|  |  | 1 | Ag Office |  | 130 | sf. |  | 130 | sf | 68% | 46723.5294
|  |  | 1 | Ag Storage |  | 100 | sf. |  | 100 | sf | 68% | 35941.1765
|  |  | 1 | Ag Tools |  | 170 | sf. |  | 170 | sf | 68% | 61100
|  |  | 1 | Cafeteria Addition |  | 4900 | sf. |  | 4900 | sf | 68% | 1761117.6471
|  |  | 1 | Weight Room Addition |  | 1600 | sf. |  | 1600 | sf | 68% | 575058.8235
|  |  | 1 | PE Storage |  | 1200 | sf. |  | 1200 | sf | 68% | 431294.1176
1b. | New construction to replace inadequate spaces; expand existing or new buildings for educational purposes;
| consolidate schools; or replace deteriorated facilities. | [9 empty] | Eff. % | Cost Est.
| 1. | Ignite Institute | [6 empty] | 185000 | sf.
|  | New learning academy for 1,000 students focusing on STEAM delivery methods in a non-conventional classroom setting. This will be an existing building which will need full renovation. | [9 empty] | 15000000
1c. | Major renovation/additions of educational facilities; including expansions, kitchens, cafeterias, libraries,
| administrative areas, auditoriums, and gymnasiums. | [9 empty] | Eff. % | Cost Est.
1d. | KERA Strands New Additions: Preschool, SBDM Office & Conf., Fam. Res.
CAPITAL CONSTRUCTION PRIORITIES (Schedule after the 2016-2018 Biennium)
2a. | New construction to meet student capacity; further implementation of established programs; or complete approved
| projects constructed in phases. | [9 empty] | Eff. % | Cost Est.
| 1. | Site acquisition for new Elementary School located Southern County | [9 empty] | 700000
|  | Construct new 750-student elementary school | [6 empty] | 79216 | sf. |  | 17712697.6
| 2. | Site acquisition for new Middle School on site located Northern/Western County | [9 empty] | 1000000
| 3. | New Alternative School
|  | Construct a 400-student district-wide Alternative Education Center | [6 empty] | 51959 | sf. |  | 11955765.9
| 3. | Rise Academy (A5 Center) |  |  | 203 / |  | 1931, '57 |  | 20000 | sf.
Located within Florence Elementary
Over 30 Years - 30's, '57
|  | 1930's, 1957 Major renovation to include; part of first floor and entire second and third floors of the original 1930s building and the 1957 addition. This renovation includes HVAC, electric, data, and lighting improvements in this area; all finishes (furring out walls, any necessary abatement, new flooring, drywall, ceilings, display boards, lockers, etc.); LED lighting for building and site; rebuild restrooms on all floors; integration of an elevator; roofing; paving / sealing / concrete walks. There will also be renovations at the tie-ins to Florence Elementary School and the Ralph Rush Professional Development Center as required to complete the renovations described above. | [9 empty] | 6000000
| 4. | Cooper High School (target 1,500 enrollment by 2019) | [6 empty] | 183934 | sf.
|  | Purchase land to expand the Cooper / Longbranch Campus | [9 empty] | 600000
|  | Minor Renovation to include; ADA and Security - site lighting and access controls / hardware | [9 empty] | 75000
|  | Construct: | 14 | Classrooms |  | 750 | sf. |  | 10500 | sf. | 68% | 3773823.5294
|  |  | 1 | Business Ed Classroom |  | 900 | sf. |  | 900 | sf. | 68% | 323470.5882
|  |  | 1 | Business Ed Office |  | 150 | sf. |  | 150 | sf. | 68% | 53911.7647
|  |  | 1 | Greenhouse | [7 empty] | 80000
|  |  | 1 | Computer Lab |  | 1280 | sf. |  | 1280 | sf. | 68% | 460047.0588
|  |  | 2 | Project Lead the Way |  | 2000 | sf. |  | 4000 | sf. | 68% | 1437647.0588
Classroom/Lab
| 5. | Ryle High School (target 2,100 enrollment by 2019) | [6 empty] | 236929 | sf.
|  | Minor Renovation to include; HVAC improvements to 1992 building; ADA/Security - site lighting and access controls / hardware. | [9 empty] | 450000
|  | Construct: | 9th Grade Center Addition | [5 empty] | 25106 | sf | 68% | 9023391.7647
| 6. | Camp Ernst Middle School (target 1,200 enrollment by 2019) | [6 empty] | 111427 | sf.
|  | Minor Renovation to include; ADA/Security - site lighting and access controls / hardware. | [9 empty] | 75000
|  | Construct: | 8 | Standard Classrooms |  | 750 | sf. |  | 6000 | sf. | 71% | 1944507.0423
| 7. | Gray Middle School (target 1,200 enrollment by 2019) | [6 empty] | 115452 | sf.
|  | Minor Renovation to include; HVAC improvements to 1995 building; ADA/Security - site lighting and access controls / hardware. | [9 empty] | 75000
|  | Construct | 8 | Classrooms |  | 750 | sf. |  | 6000 | sf. | 71% | 1944507.0423
| 8. | Jones Middle School (target 775 enrollment by 2019) | [6 empty] | 105194 | sf.
|  | Minor Renovation to include; HVAC improvements to 1978 building; ADA/Security - site lighting and access controls / hardware; roofing | [9 empty] | 325000
|  | Construct | 4 | Classrooms |  | 750 | sf. |  | 3000 | sf. | 71% | 972253.5211
| 9. | Collins Elementary School (target 800 enrollment by 2019) | [6 empty] | 67686 | sf.
|  | Minor Renovation to include; HVAC improvements to 1989 building; ADA/Security - site lighting and access controls / hardware; convert existing Cafeteria into (2) Resource Rooms; Playground safety improvements. | [9 empty] | 750000
|  | Construct | 4 | Classrooms |  | 750 | sf. |  | 3000 | sf. | 74% | 906486.4865
|  |  | 1 | Cafeteria |  | 5400 | sf. |  | 5400 | sf. | 74% | 1631675.6757
| 10. | Goodridge Elementary School (target 775 enrollment by 2019) | [6 empty] | 72829 | sf.
|  | Minor Renovation to include; HVAC improvements to 1971 building; ADA/Security - site lighting and access controls / hardware; new security vestibule; Playground safety improvements. | [9 empty] | 175000
|  | Construct | 5 | Classrooms |  | 750 | sf. |  | 3750 | sf. | 74% | 1133108.1081
| 11. | Longbranch Elementary School (target 1,050 enrollment by 2019) | [6 empty] | 83750 | sf.
|  | Minor Renovation to include; ADA/Security - site lighting and access controls / hardware; Playground safety improvements. | [9 empty] | 75000
|  | Construct: | 6 | Standard Classrooms |  | 750 | sf. |  | 4500 | sf. | 74% | 1359729.7297
| 12. | Mann Elementary School (target 1,000 enrollment by 2019) | [6 empty] | 86239 | sf.
|  | Minor Renovation to include; ADA/Security - site lighting and access controls / hardware; Playground safety improvements. | [9 empty] | 75000
|  | Construct: | 4 | Standard Classrooms |  | 750 | sf. |  | 3000 | sf. | 74% | 906486.4865
| 13. | New Haven Elementary School/Annex (target 1,000 enrollment by 2019) | [6 empty] | 105448 | sf.
|  | Minor renovations to include; HVAC improvements to 1980's and 1990's buildings; ADA/Security - site lighting and access controls / hardware; Expanded parking/site acquisition; Playground safety improvements. | [9 empty] | 500000
|  | Construct: | 2 | Standard Classrooms |  | 750 | sf. |  | 1500 | sf. | 74% | 453243.2432
| 14. | Thornwilde Elementary School (target 800 enrollment by 2019) | [6 empty] | 76270 | sf.
|  | Minor Renovation to include; ADA/Security - site lighting and access controls / hardware; Playground safety improvements. | [9 empty] | 75000
|  | Construct: | 4 | Standard Classrooms |  | 750 | sf. |  | 3000 | sf. | 74% | 906486.4865
2b. | New construction to replace inadequate spaces; expand existing or new buildings for educational purposes;
| Consolidate schools; or replace deteriorated facilities. | [9 empty] | Eff. % | Cost Est.
2c. | Major renovation/additions of educational facilities; including expansions, kitchens, cafeterias, libraries,
| administrative areas, auditoriums, and gymnasiums. | [9 empty] | Eff. % | Cost Est.
| 1. | Boone County High School (target 1,405 enrollment by 2019) | [6 empty] | 229012 | sf.
|  | Major Renovation of the 1950's wings of original High School. The major renovation will include all mechanical, electrical, plumbing, communication technology; ADA/Security - site lighting and access controls / hardware; Renovation of all lab spaces including all casework, all finishes such as flooring, doors and hardware, ceilings, paint, carpet, and lockers; the building will be brought up to current new building standards; roofing (1950's wing) and other miscellaneous improvements; Renovation of existing Auditorium into Classrooms. Connector to Band Room. | [9 empty] | 4800000
|  | Construct | 1 | Auditorium |  | 5400 | sf. |  | 5400 | sf. | 68% | 1940823.5294
| 2. | Conner High School (target 1,700 enrollment by 2019) | [6 empty] | 183934 | sf.
|  | Minor Renovation to include; HVAC improvements to 1970 building; ADA/Security - site lighting and access controls / hardware; roofing (original building) | [9 empty] | 700000
|  | Construct | 12 | Classrooms |  | 750 | sf. |  | 9000 | sf. | 68% | 3234705.8824
|  |  | 1 | Fieldhouse |  | 10000 | sf. |  | 10000 | sf. | 68% | 3594117.6471
| 3. | Conner Middle School (target 900 enrollment by 2019) | [6 empty] | 123083 | sf.
|  | Major Renovation to include; HVAC improvements to 1962 and 1996 buildings; mechanical, electrical and plumbing; ADA/Security - site lighting and access controls / hardware; ceilings, restrooms; doors and hardware | [9 empty] | 8000000
| 4. | Ockerman Middle School (target 900 enrollment by 2019) | [6 empty] | 109471 | sf.
|  | Minor Renovation to include; ADA/Security - site lighting and access controls / hardware; Renovate (2) Classrooms into Science Classrooms. | [9 empty] | 150000
|  | Construct | 3 | Classrooms |  | 750 | sf. |  | 2250 | sf. | 71% | 729190.1408
| 5. | Burlington Elementary |  |  | 1939, '79, '85 & '00 |  |  |  | 103924 | sf.
|  | Minor Renovation to include; HVAC improvements to 1980's building; ADA/Security - site lighting and access controls / hardware; Floor coverings (in original 1930's building); Playground safety improvements. | [9 empty] | 275000
|  | 1939, 1979, & 1985 BUILDING SECTIONS - FINDING 3: Renovation to include; HVAC Improvements to the 1939 Building Section, window replacement, tuckpointing / waterproofing & exterior brick/limestone to the 1939 Building Section, drinking fountains and water bottle filling stations; electric upgrades, new LED lighting, new doors / frames, casework and sink in each classroom, marker/tack boards, lockers, metal stud/drywall furring and painting, flooring, rubber base and ceiling finishes; new wall padding in Sensory Room) | [9 empty] | 1706975
|  | 2000 BUILDING SECTION - FINDING 3: Renovation to include: Drinking fountains and water bottle filling stations | [9 empty] | 20000
| 6. | Erpenbeck Elementary School (target 800 enrollment by 2019) | [6 empty] | 76471 | sf.
|  | Minor Renovation to include; HVAC improvements to 1996 building; ADA/Security - site lighting and access controls / hardware; Playground safety improvements. | [9 empty] | 75000
| 7. | Florence Elementary School (target 600 enrollment by 2019) | [6 empty] | 115836 | sf.
|  | Minor Renovation to include; ADA/Security - site lighting and access controls / hardware; Playground safety improvements. | [9 empty] | 75000
| 8. | Kelly Elementary School (target 450 enrollment by 2019) | [6 empty] | 39676 | sf.
|  | Minor Renovation to include; ADA/Security - site lighting and access controls / hardware; Playground safety improvements. | [9 empty] | 75000
| 9. | North Pointe Elementary School (target 925 enrollment by 2019) | [6 empty] | 85078 | sf.
|  | Minor Renovation to include; ADA/Security - site lighting and access controls / hardware; roofing; Playground safety improvements. | [9 empty] | 675000
| 10. | Ockerman Elementary School (target 775 enrollment by 2019) | [6 empty] | 76744 | sf.
|  | Minor Renovation to include; ADA/Security - site lighting and access controls / hardware; Playground safety improvements. | [9 empty] | 75000
| 11. | Stephens Elementary School (target 900 enrollment by 2019) | [6 empty] | 79213 | sf.
|  | Major Renovation to include; HVAC improvements to 1992 building; ADA/Security - site lighting and access controls / hardware; roofing (1997 addition); Site improvements, access roads, parking lot expansion/repairs; Playground safety improvements. | [9 empty] | 395000
| 12. | Yealey Elementary School (target 600 enrollment by 2019) | [6 empty] | 73447 | sf.
|  | Minor Renovation to include; HVAC improvements to 1962 building; ADA/Security - site lighting and access controls / hardware; Playground safety improvements. | [9 empty] | 75000
| 13. | Boone County Area Tech Center | [6 empty] | 28382 | sf.
|  | Minor Renovation to include; HVAC improvements to include building; ventilation/exhaust system; ADA/Security - site lighting and access controls / hardware; | [9 empty] | 350000
2d. | KERA Strands new additions; Preschool, SBDM Office & Conference, Fam. Res.
| 1. | District White Board/ Projector Initiative
Provide fixed active boards and projectors in all classrooms district wide with wireless capability for hand-held student assessments and remote operation.
|  | Construct: | 1000 | Projectors |  |  | 1500 | each |  | 1500000
| 2. | Burlington Elementary |  |  | 1939. '79, '85 & '00 |  |  |  | 103924 | sf.
|  | 1939, 1979, & 1985 BUILDING SECTIONS - FINDING 3: Renovation to include; data/technology upgrades. | [9 empty] | 100000
2e. | Renovation to upgrade all existing facilities to meet the most current life safety requirements of the Kentucky
| Building Code. | [9 empty] | Eff. % | Cost Est.
| 1. | Burlington Elementary |  |  | 1939. '79, '85 & '00 |  |  |  | 103924 | sf.
|  | ALL BUILDING SECTIONS - FINDING 3: Renovation to include; exterior stair improvements for code compliance, handrail and guardrail upgrades to interior stairs for code compliance | [9 empty] | 150000
| 2. | Rise Academy (A5 Center) |  |  | 203 / |  | 1931, '57 |  | 20000 | sf.
Located within Florence Elementary
Over 30 Years - 30's, '57
|  | 1930's, 1957 Secure vestibule, elevator, buzzers, cameras, access controls at front entry, doors / hardware / access controls | [9 empty] | 50000
2f. | Renovation to upgrade all existing facilities to meet the most current handicapped accessibility
| requirements of the Kentucky Building Code. | [9 empty] | Eff. % | Cost Est.
| 1. | Rise Academy (A5 Center) |  |  | 203 / |  | 1931, '57 |  | 20000 | sf.
Located within Florence Elementary
Over 30 Years - 30's,'57
|  | 1930's, 1957 Renovation to include ADA upgrades to access controls at front doors, security cameras and other items such as handrails, guardrails, etc. | [9 empty] | 10000
CAPITAL CONSTRUCTION PRIORITIES (Regardless of Schedule)
3. | Construction of non-educational additions or expansions including; kitchen, cafeterias, administrative areas,
| auditoriums and gymnasiums. | [9 empty] | Eff. % | Cost Est.
4. | Management support areas; Construct, acquisition, or renovation of central offices, bus garages, or central stores
[11 empty] | Eff. % | Cost Est.
| 1. | Ralph Rush/Boone County Schools Staff Development Center | [6 empty] | 6000 | sf.
|  | Major Renovation to include; life safety improvements; floors; security system; ADA improvements. | [9 empty] | 1092000
| 2. | Central Storage
|  | Construct: | Construct a new central storage facility. | [5 empty] | 54000 | sf. |  | 6669000
| 3. | Florence Elementary School Annex | [6 empty] | 32000 | sf.
|  | Major Renovation to include; HVAC improvements to 1930's building; ADA and security - site lighting and access controls / hardware; restrooms; interior finishes; hardware | [9 empty] | 1200000
| 4. | Central Office | [6 empty] | 18600 | sf.
|  | Major renovation to include; HVAC improvements to 1973 buildings electric and plumbing upgrades; ADA/Security - site lighting and access controls / hardware | [9 empty] | 1100000
| 5. | Maintenance Building (existing on Ockerman Campus) | [6 empty] | 11660 | sf.
|  | Renovate into Central Office Annex | [9 empty] | 1166000
| 6. | Boone County Bus Lot and Garage
|  | Expansion and paving improvements; generator | [9 empty] | 600000
| 7. | Ryle High School
|  | Bus Parking Lot Expansion | [9 empty] | 200000
DISTRICT NEED | [11 empty] | 148699120.5309
5. | Discretionary Construction Projects; Functional Centers; Improvements by new construction or renovation.
| Estimated Costs of these projects will not be included in the FACILITY NEEDS ASSESSMENT TOTAL. | [9 empty] | Eff. %
| 1. | Boone County High School | [6 empty] | 229012 | sf.
|  | Renovation of existing paving areas | [9 empty] | 300000
|  | Construct: | 8 | Classrooms |  | 750 |  |  | 6000 | sf. | 68% | 2156470.5882
|  |  | 1 | Choir/Vocal Music Clsrm |  | 900 | sf. |  | 900 | sf. | 68% | 323470.5882
| 2. | Conner High School | [6 empty] | 183934 | sf.
|  | Roofing (addition) and renovation of existing paving areas | [9 empty] | 700000
| 3. | Cooper High School | [6 empty] | 188800 | sf.
|  | Renovation of existing paving areas | [9 empty] | 250000
| 4. | Ryle High School | [6 empty] | 236929 | sf.
|  | Replace lockers and floor coverings; fine grade lawn area | [9 empty] | 920000
|  | Construct: | 9th Grade Center Addition | [5 empty] | 35359 | sf | 68% | 12708440.5882
| 5. | Camp Ernst Middle School | [6 empty] | 111427 | sf.
|  | HVAC improvements to original 2005 building; roofing; renovation of existing paving areas | [9 empty] | 775000
| 6. | Conner Middle School | [6 empty] | 123083 | sf.
|  | Floor coverings; roofing (front classrooms and library) | [9 empty] | 700000
| 7. | Gray Middle School | [6 empty] | 115452 | sf.
|  | Floor coverings | [9 empty] | 400000
| 8. | Jones Middle School | [6 empty] | 105194 | sf.
|  | Renovation of existing paving areas | [9 empty] | 125000
| 9. | Ockerman Middle School | [6 empty] | 109471 | sf.
|  | Roofing and renovation of existing paving areas | [9 empty] | 250000
| 10. | Burlington Elementary School | [6 empty] | 103924 | sf.
|  | Roofing and renovation of existing paving areas | [9 empty] | 525000
|  | ALL BUILDING SECTIONS - FINDING 3: New elevator for code compliance | [9 empty] | 125000
| 11. | Collins Elementary School | [6 empty] | 67686 | sf.
|  | Renovation of existing paving areas | [9 empty] | 125000
| 12. | Erpenbeck Elementary School | [6 empty] | 76471 | sf.
|  | Roofing and renovation of existing paving areas | [9 empty] | 65000
| 13. | Florence Elementary School | [6 empty] | 115836 | sf.
|  | Roofing and renovation of existing paving areas | [9 empty] | 325000
| 14. | Kelly Elementary School | [6 empty] | 39676 | sf.
|  | Renovation of existing paving areas | [9 empty] | 25000
| 15. | New Haven Elementary School/Annex | [6 empty] | 105448 | sf.
|  | Roofing and renovation of existing paving areas | [9 empty] | 750000
|  | Construct: | 2 | Standard Classrooms |  | 750 | sf. |  | 1500 | sf. | 74% | 453243.2432
| 16. | North Pointe Elementary School | [6 empty] | 85078 | sf.
|  | Renovation of existing paving areas | [9 empty] | 100000
| 17. | Ockerman Elementary School | [6 empty] | 76744 | sf.
|  | Renovation of existing paving areas | [9 empty] | 50000
| 18. | Yealey Elementary School | [6 empty] | 73447 | sf.
|  | Renovation of existing paving areas | [9 empty] | 100000
| 19. | Florence Elementary School Annex | [6 empty] | 32000 | sf.
|  | Roofing | [9 empty] | 125000
| 20. | Central Office | [6 empty] | 18600 | sf.
|  | Roofing and renovation of existing paving areas | [9 empty] | 100000