## May 10, 2021
Proposed Change Orders for April 2021 Estill Board of Education
BG 18-361 Estill County ATC
Change Order No | Contractor/Supplier |  | Background/Rationale | Suggested Motion
REMOVAL OF SCOPE ALTERNATE 3 CREDIT CHANGE ORDERS
2-5 | Standafer Builders Asphalt Paving Divison |  | Owner requested change to delete scope for
Alternate 3 High School front parking lot
Move to approve credit change order 2-5 issued to the contract for Standafer Builders for the amount of ($51,000.00) for the removal of scope of work for Alternate 3 High School Front parking lot.
| Cost for Change Order | -51000
A/E fee
CM fee
| TOTAL COST | -51000 | reduction in cost- funds reallocted to construction
contingency
change is consistent with priorities on DFP
3-8 | RISING SUN DEVELOPING, INC. |  | Owner requested change to remove scope of work
for Alternate 3 High School front parking lot
Move to approve Change Order 3-8 a credit
| Cost for Change Order | -38590 |  | issued to the contract for Rising Sun
| A/E fee |  |  | Developing for the amount of ($38,590.00)
| CM fee |  |  | for removal of scope for Alternate 3 High School
| TOTAL COST | -38950 | reduction in cost- funds to be reallocated to | front parking lot
construction contingency
change is consistent with DFP
9-8 | CONLEY PAINTING |  | Owner requested change to remove scope of work
for Alternate 3 High School front parking lot
Move to approve Change Order 9-8 a credit
| Cost for Change Order | -850 |  | issued to the contract for Conley Painting for
| A/E fee |  |  | the amount of ($850.00) for removal of scope
| CM fee |  |  | for Alternate 3 High School front parking lot
| TOTAL COST | -850 | reduction in cost -funds to be reallocated to
construction contingency
change is consistent with DFP
ADDITIONS TO SCOPE OF WORK
3-9 | RISING SUN DEVELOPING |  | PR 26 Add two (2) additional windows and a door
at Tool Room 206C
Move to approve Change Order 3-9 issued to
| Cost for Change Order | 9658.5 |  | Rising Sun Developing for the amount of
| A/E fee | 531.22 |  | $9,658.50 for the addition of two (2) windows
| CM fee | 193.17 |  | and a door at Tool Room 206C
| TOTAL COST | 10382.89 | cost non-recurring to construction contingency
change is consistent with DFP
4-6 | CARMICLE MASONRY |  | PR 26 Add two (2) additional windows and a door
at Tool Room 206C
| Cost for Change Order | 3739.61 |  | Move to approve Change Order 3-9 issued to
| A/E fee | 205.69 |  | Carmicle Masonry for the amount of $3,739.61
| CM fee | 74.79 |  | for the addition of two (2) windows and a door
| TOTAL COST | 4020.09 |  | at Tool Room 206C
cost non-recurring to construction contingency
change is consistent with DFP
7-4 | BENNETT'S CARPETS |  | CLAIM #4 additional cost for soffit changes in
pedway. $1922.50
CLAIM # 5 add drywall at column line wall in
|  |  | main lobby $2,138.00 | motion to approve Change Order 7-4 issued
| Cost for Change Order | 4060.5 |  | to Bennett's Carpets for the amount of $4060.50
| A/E fee | 223.33 |  | to cover the additional cost for soffit changes in
| CM fee | 81.21 |  | the Pedway and to add drywall at column line
| TOTAL COST | 4365.04 | cost is not a recurring cost to construction fund | in main lobby
change is consistent with the DFP
ADDITIONS TO SCOPE OF WORK CONTINUED
9-9 | CONLEY PAINTING |  | PR 26 Add two (2) additional windows and a door
at Tool Room 206C
| Cost for Change Order | 442 |  | move to approve Change Order 9-9 issued to
| A/E fee | 24.31 |  | Conley Painting for the amount of $442.00
| CM fee | 8.84 |  | for the addition of 2 windows and a door at
| TOTAL COST | 475.15 | cost is not a recurring cost to construction | Tool Room 206C
contingency
change is consistent with DFP
901-6 | BABCON,INC. |  | PR 25 provide and install electrical circuitry for
hand dryers
| Cost for Change Order | 7956.67 |  | move to approve Change Order 901-6 issued
| A/E fee | 437.62 |  | to Babcon Inc. for the amount of $7,956.67 for
| CM fee | 159.13 |  | the cost to provide and install electrical circuitry
| TOTAL COST | 8553.42 | cost is not a recurring cost to construction | for hand dryers
contingency
change is consistent with DFP