**Board Memo**

**DATE:** 6/10/2021

**AGENDA ITEM DETAILS:**

**School/Department**

Turf Fields at the High Schools

**Product Vendor or Grant Issuer**

Change Order for Turf Fields, BG 20-184

**Product or Grant Name**

Change Order #2

**Date/Term (Beginning and End Dates/Year)**

5/26/2021

**APPLICABLE BOARD POLICY:**

05.1

**DESCRIBE USE OF CONTRACT/PURCHASE/AGREEMENT**

This change order consists of the following:  
Proposal 4Rc - In an effort to accelerate and hold the schedule, it was determined that the D events, such as the high jump, would be constructed in concrete rather than asphalt prior to receiving the rubber asphalt coating. The concrete allows for a better winter weather installation and also has a longer life span and thus an enhanced value to the District. This change is at Cooper High School. ADD $18,702.

Proposal 15 - This change order is for additional milling and overlay around the lower concession building at Boone County High School - there were some areas that would have been harder to get to after the new track was complete and we wanted to add them while the contractor was on-site. ADD $6,254.

Proposal 16 - This change order is for additional full depth repair of deep cracks at the bleachers at Boone County High School. ADD $2,173.

Proposal 17 - This change order is for adding 75 linear feet of concrete extruded curb at Boone County High School. ADD $1,777.

TOTAL Change Order - $28,906.00

**FUNDING FOR PURCHASES AND OTHER REQUESTS:**

**Total Cost**

$28,906.00

**Funding Source**

Construction

**\*If more than one funding source, list below along with amount or percent for each source**

Click or tap here to enter text.

**IF THIS IS A GRANT, ENTER AMOUNT TO BE AWARDED:**

Click or tap here to enter text.

**RECOMMENDATION:**

I recommend the Board approve the Changer Order #2 for Turf Fields, BG 20-184 (OHeil) in the amount of $28,906.00, as presented.

**CONTACT PERSON: (submitter)**

Mike Poiry, Assistant Superintendent of Operations