**Board Memo**

**DATE:** 6/10/2021

**AGENDA ITEM DETAILS:**

**School/Department**

Boone County High School

**Product Vendor or Grant Issuer**

Change Order for Boone County High School Add/Reno, BG 20-183

**Product or Grant Name**

Change Order #3

**Date/Term (Beginning and End Dates/Year)**

5/25/2021

**APPLICABLE BOARD POLICY:**

05.1

**DESCRIBE USE OF CONTRACT/PURCHASE/AGREEMENT**

This change order consists of the following:  
Proposal 7 - Provide standard stainless steel junction box in lieu of custom stainless steel wireway for branch feeder distribution from mechanical room. The standard junction box solution physically fits better with the electrical contractors Switchgear package (switchgear package is an approved equivalent to the Basis of Design). DEDUCT $8,674.

Proposal 11R2 - Relocate existing 30 circuit electrical panel from existing projector room (elevated room) to new classroom below to facilitate demolition of existing projector room. ADD $5,205.

Proposal 13 - Added additional exterior façade letters from Auditorium to Performing Arts Center.

ADD $8,088.

TOTAL Change Order - $4,619.00

**FUNDING FOR PURCHASES AND OTHER REQUESTS:**

**Total Cost**

$4,619.00

**Funding Source**

Construction

**\*If more than one funding source, list below along with amount or percent for each source**

Click or tap here to enter text.

**IF THIS IS A GRANT, ENTER AMOUNT TO BE AWARDED:**

Click or tap here to enter text.

**RECOMMENDATION:**

I recommend the Board approve the Boone County High Add/Reno Change Order #3 for BG 20-183 in the amount of $4,619.00, as presented.

**CONTACT PERSON: (submitter)**

Mike Poiry, Assistant Superintendent of Operations