**Board Memo**

**DATE:** 7/15/2021

**AGENDA ITEM DETAILS:**

**School/Department**

Boone County, Conner, Cooper, and Ryle High Schools

**Product Vendor or Grant Issuer**

Change Order for Turf Fields, BG 20-184

**Product or Grant Name**

Change Order #1 (Motz) Target Technologies Purchase Order

**Date/Term (Beginning and End Dates/Year)**

5/25/2021

**APPLICABLE BOARD POLICY:**

05.1

**DESCRIBE USE OF CONTRACT/PURCHASE/AGREEMENT**

This change order consists of the following:

Target Technologies was not able to provide adequate sand material to meet the schedule at Boone County High. Motz will be handling procurement of additional sand via another vendor with no additional Change Order being presented to the District. DEDUCT $6,840.

**FUNDING FOR PURCHASES AND OTHER REQUESTS:**

**Total Cost**

No Cost

**Funding Source**

Construction

 **\*If more than one funding source, list below along with amount or percent for each source**

Click or tap here to enter text.

**IF THIS IS A GRANT, ENTER AMOUNT TO BE AWARDED:**

Click or tap here to enter text.

**RECOMMENDATION:**

I recommend the Board approve the Change Order #1 for Turf Fields (Motz) Target Technologies Purchase Order, BG 20-184, as presented.

**CONTACT PERSON: (submitter)**

Mike Poiry, Assistant Superintendent of Operations