**Board Memo**

**DATE:** 7/15/2021

**AGENDA ITEM DETAILS:**

**School/Department**

Boone County, Conner, Cooper, and Ryle High Schools

**Product Vendor or Grant Issuer**

Change Order for Turf Fields, BG 20-184

**Product or Grant Name**

Change Order #3

**Date/Term (Beginning and End Dates/Year)**

6/25/2021

**APPLICABLE BOARD POLICY:**

05.1

**DESCRIBE USE OF CONTRACT/PURCHASE/AGREEMENT**

This change order consists of the following:

Opening up and repairing an uncharted drain line under the field at Conner High School. ADD $1,967.

Repairing an existing storm line at Boone County High School that was creating a sink hole which could jeopardize the future turf field. ADD $1,669.

There was an existing power feeder inside a conduit serving the lights on the far side of the field at Conner High School. When the flagpole was installed years ago it nicked this wire which was starting to send a fault and needed to be replaced. ADD $6,716.

**FUNDING FOR PURCHASES AND OTHER REQUESTS:**

**Total Cost**

$10,352.00

**Funding Source**

Construction

**\*If more than one funding source, list below along with amount or percent for each source**

Click or tap here to enter text.

**IF THIS IS A GRANT, ENTER AMOUNT TO BE AWARDED:**

Click or tap here to enter text.

**RECOMMENDATION:**

I recommend the Board approve the Change Order #3 for Turf Fields (OHeil) BG 20-184, as presented.

**CONTACT PERSON: (submitter)**

Mike Poiry, Assistant Superintendent of Operations