**Board Memo**

**DATE:** 8/12/2021

**AGENDA ITEM DETAILS:**

**School/Department**

Boone County High School

**Product Vendor or Grant Issuer**

Change Order

**Product or Grant Name**

Change Order #4 for Boone County High School Reno, BG 20-183

**Date/Term (Beginning and End Dates/Year)**

7/28/2021

**APPLICABLE BOARD POLICY:**

05.1

**DESCRIBE USE OF CONTRACT/PURCHASE/AGREEMENT**

This change order includes the following:

Proposal 9R2 - Provide and install make up water stations for hot and chiller water systems. Make up water stations were indicated to be provided for both systems, but were not including the plumber's scope for domestic water connection. ADD $2,521.

Proposal 15R3 - During the ceiling demolition the existing vent hood ductwork was discovered to be unused. This Change Order is to remove entire assembly and patch roof. ADD $6,876.

Proposal 16R3 - New work necessitated additional rework of existing piping in the Mechanical Room to allow connections to be made. ADD $1,945.

Proposal 24 - Provide an electrical power source of sufficient size to resolve permanent power needs of the science room as well as temporary needs for the school's hot water requirements during construction.

ADD $5,000.

Proposal 26 - Additional subfloor to provide a flush condition to the existing stage rather than steps down into office area. ADD $5,183.

**FUNDING FOR PURCHASES AND OTHER REQUESTS:**

**Total Cost**

$21,525.00

**Funding Source**

Construction

**\*If more than one funding source, list below along with amount or percent for each source**

Click or tap here to enter text.

**IF THIS IS A GRANT, ENTER AMOUNT TO BE AWARDED:**

**RECOMMENDATION:**

I recommend the Board approve the Change Order #4 for Boone County High Reno, BG 20-183, as presented.

**CONTACT PERSON: (submitter)**

Kim Best, Assistant Superintendent of Operations