## August 2021
Proposed Change Orders for August 2021 Estill Board of Education
BG 18-361 Estill County ATC
Change Order No | Contractor/Supplier |  | Background/Rationale | Suggested Motion
3-12 | Rising Sun Developing |  | reduce scope of work by removing provision and
installation of lettering to read "ENGINEERS" in the pedway
| Cost for Change Order | -6748
A/E fee
CM fee
| TOTAL COST | -6748 | credit returns funds to construction contingency
change is consistent with priorities on DFP
Move to approve Change Order number 3-12 issued to the contract for Rising Sun Developing for a credit amount of ($6,748.00) to delete scope of work to provide lettering for "Engineers" for the pedway. Reduction in scope results in funds being returned to Construction Contingency
Resubmittal of Time Extension Change Orders originally presented to and approved by the Board on January 16, 2020.
2-1 | Standafer Builders | 0 | When change orders were originally presented to KDE
3-1 | Rising Sun Developing | 0 | for review and approval, KDE would not approve them
4-1 | Carmicle Masonry | 0 | because they objected to the explanation provided
5-1 | Rising Sun Developing | 0 | as the reason for the change order.
6-1 | Kalkreuth Roofing | 0 | The original language stated that the delay resulted from
7-1 | Bennett's Flooring | 0 | time taken for KDE final review of contracts.
8-1 | Rodgers Aluminum and Glass | 0 | The language has been rephrased to remove "blame"
9-1 | Conley Painting | 0 | placed on KDE, and to provide description consistent
10-1 | Spectra Flooring | 0 | with KAR 4:160
11-1 | Martina Brothers | 0 | The change orders remain as zero dollar change orders.
12-1 | D-C Elevator | 0 | The number of days requested remains the same.
13-1 | Landmark Sprinkler | 0
14-1 | Central KY Sheet Metal | 0
15-1 | Babcon | 0
Motion to acknowledge that Time Extension
Change Orders originally reviewed and
approved by Board on January 16, 2020
have been revised to reflect language consistent
with KAR 4:160 as the reason for requested
time extension.