**Board Memo**

**DATE:** 10/14/2021

**AGENDA ITEM DETAILS:**

**School/Department**

Ryle High School

**Product Vendor or Grant Issuer**

Change Order

**Product or Grant Name**

Change Order #1 for Concrete Improvements 2021, BG 21-201

**Date/Term (Beginning and End Dates/Year)**

9/29/2021

**APPLICABLE BOARD POLICY:**

05.1

**DESCRIBE USE OF CONTRACT/PURCHASE/AGREEMENT**

This Change Order includes the following:

There were two locations at Ryle High School where the existing curb inlets were deteriorating. It was determined during construction that it would be easiest to replace them while the contractor was mobilized   
on-site. ADD $14,201.00

**FUNDING FOR PURCHASES AND OTHER REQUESTS:**

**Total Cost**

$14,201.00

**Funding Source**

Construction

**\*If more than one funding source, list below along with amount or percent for each source**

Click or tap here to enter text.

**IF THIS IS A GRANT, ENTER AMOUNT TO BE AWARDED:**

**RECOMMENDATION:**

I recommend the Board approve the Change Order #1 for Concrete Improvements 2021, BG 21-201, as presented.

**CONTACT PERSON: (submitter)**

Kim Best, Assistant Superintendent of Operations