**Board Memo**

**DATE:** 11/11/2021

**AGENDA ITEM DETAILS:**

**School/Department**

Steeplechase Elementary School

**Product Vendor or Grant Issuer**

Change Order

**Product or Grant Name**

Change Order #8 for Steeplechase Elementary Bid Package #2, BG 19-078

**Date/Term (Beginning and End Dates/Year)**

10/27/2021

**APPLICABLE BOARD POLICY:**

05.1

**DESCRIBE USE OF CONTRACT/PURCHASE/AGREEMENT**

This Change Order includes the following:

Proposal 27 – Additional area of undercutting and stabilization of existing soils that was encountered prior to installing the pavement. This was an area where soils were still existing.

ADD - $7,354.00

Proposal 42 – Add power to two ADA automatic door operators so they can act independently for added safety.

ADD - $2,763.00

Proposal 44 – Add enhanced light reflectors to shield the neighborhoods from any light pollution from the parking lot lights. Typically this is not a problem but since the houses are so much higher than the school they are getting some feedback.

ADD - $7,472.00

Proposal 46 – Remove the copper date box insert from the scope of work – artifacts will not be placed inside the date stone and the District realizes a cost saving.

DEDUCT - $500.00

**FUNDING FOR PURCHASES AND OTHER REQUESTS:**

**Total Cost**

$17,089.00

**Funding Source**

Construction

**\*If more than one funding source, list below along with amount or percent for each source**

Click or tap here to enter text.

**IF THIS IS A GRANT, ENTER AMOUNT TO BE AWARDED:**

Click or tap here to enter text.

**RECOMMENDATION:**

I recommend the Board approve Change Order #8 for Steeplechase Elementary Bid Package #2, BG 19-078,  
as presented.

**CONTACT PERSON: (submitter)**

Kim Best, Assistant Superintendent of Operations