**Board Memo**

**DATE:** 11/11/2021

**AGENDA ITEM DETAILS:**

**School/Department**

Florence Elementary School, RISE Academy, and Conner High School

**Product Vendor or Grant Issuer**

Change Order

**Product or Grant Name**

Change Order #1 for Paving Improvements 2021, BG 21-200

**Date/Term (Beginning and End Dates/Year)**

9/29/2021

**APPLICABLE BOARD POLICY:**

05.1

**DESCRIBE USE OF CONTRACT/PURCHASE/AGREEMENT**

This Change Order includes the following:

Proposal 1 - Install a 4" french drain diagonally through the existing student lot at Conner High where water was bleeding out.

ADD - $7,875.00

Proposal 3 - Additional sealcoating to asphalt patches from the concrete replacement project.

ADD - $7,865.00

Proposal 4 - Credit for not sealcoating at Florence Elementary since the contractor is still on-site for the RISE Academy renovations. We do not want this investment being ruined and this work can be included in a future project.

DEDUCT - $3,680.00

Proposal 5 - Credit for undercut allowance which did not need to be utilized as part of the project.

DEDUCT - $500.00

**FUNDING FOR PURCHASES AND OTHER REQUESTS:**

**Total Cost**

$11,560.00

**Funding Source**

Construction

**\*If more than one funding source, list below along with amount or percent for each source**

Click or tap here to enter text.

**IF THIS IS A GRANT, ENTER AMOUNT TO BE AWARDED:**

**RECOMMENDATION:**

I recommend the Board approve the Change Order #1 for Paving Improvements 2021, BG 21-200, as presented.

**CONTACT PERSON: (submitter)**

Kim Best, Assistant Superintendent of Operations