**Board Memo**

**DATE:** 3/10/2022

**AGENDA ITEM DETAILS:**

**School/Department**

Steeplechase Elementary School

**Product Vendor or Grant Issuer**

Change Order

**Product or Grant Name**

Change Order #10 for Steeplechase Elementary School BP #2, BG 19-078

**Date/Term (Beginning and End Dates/Year)**

2/23/2022

**APPLICABLE BOARD POLICY:**

05.1

**DESCRIBE USE OF CONTRACT/PURCHASE/AGREEMENT**

This Change Order includes the following:

Proposals 5 and 21 – These Change Orders requests have been submitted as a result of additional costs incurred by the contractor due to significant Covid delays during the construction of Steeplechase Elementary School relative to quarantines and manufacturer shipping delays.

ADD $119,012.00

Proposal 51R – In laying out the gym floor striping it was determined that adding an accent border would greatly enhance the field of play.

ADD $1,184.00

Proposal 52 – Increasing the number of bike racks since the community has such a high level of support for bike traffic.

ADD $754.00

**FUNDING FOR PURCHASES AND OTHER REQUESTS:**

**Total Cost**

$120,950.00

**Funding Source**

Construction

**\*If more than one funding source, list below along with amount or percent for each source**

Click or tap here to enter text.

**IF THIS IS A GRANT, ENTER AMOUNT TO BE AWARDED:**

Click or tap here to enter text.

**RECOMMENDATION:**

I recommend the Board approve the Change Order #10 for Steeplechase Elementary School BP #2, BG 19-078, as presented.

**CONTACT PERSON: (submitter)**

Kim Best, Assistant Superintendent of Operations