## Sheet1
2009-2010 CDIP Impact Check | IP= implemented partially
I=implemented
P= progressing
COMPONENT: District Initiatives and Parental Involvement | 2010-03-08 | comments
PRIORITY NEED: IMPROVE PARENTAL INVOLVEMENT AT ALL LEVELS
Goals: Partially by using new Parent Involvement Coordinator:
MEASURE: *Increase volunteer hours by 50% (more than 50 hours) | I | 1968 hr thru Jan ytd; ly 1209 total
*Train parents interested to help w/walkthru's (5 minimum) | I | currently have 8 parents who rotate
*Parents notified of events using automated all-call (100%) | I | is 100% with curent #'s from parents
Strategy/Activity (goal completion by 7/1/2010)
*District DILT Team will be trained through the Pritchard Committee to lead effective parental involvement | I,P | fully implemented, continue refining
*Minimum of 5 parents trained to help with monitoring | I | fully implemented, continue refining
*Parents trained in using the eWalk and student questioning | I,P | fully implemented, continue refining
*Parents encouraged to volunteer at registration and throughout the school year | I,P | fully implemented, continue refining
*Schools have parents email to communicate regularly (if available) | I,P | fully implemented, continue refining
*Purchase/use automated phone system to communicate important events and notices | I | fully implemented, used regularly
PRIORITY NEED: DILT REVIEW OWN BEST PRACTICES AND USE INTERNAL EXPERTS
Goals: Use DILT Team to refine Best Practices to help students increase their level of proficiency
BENCHMARK/MEASURE: *KCCT 85% proficient or above
*ITBS 50% proficient or above (at ele level), formerly CTBS test
Strategy/Activity (goal completion by 7/1/2010)
*Formation/continuation of the DILT team w/stipends as available | I,P | fully implemented, continue refining
*Continue use of Thoughtful Ed critical vocabulary and related strategies | I,P | fully implemented, continue refining
*Continued implementation and monitoring of "Stiggins" PD | I,P | fully implemented, continue refining
PRIORITY NEED: MAXIMIZE ESS RESOURCES W/FOCUS ON READING/MATH
Goals: Increase KCCT (Cats) and CTBS scores, both above 70% Prof or Dist |  | current learning checks in progress
*Benchmark/Measure: KPR Reading/Language Arts 70% or above prof/dist |  | current learning checks in progress
*KPR Math 70% or above prof/dist by
Strategy/Activity (goal completion by 7/1/2010)
Utilize daytime ESS waiver to help identified students who need extra help | I,P | fully implemented, continue refining
COMPONENT: Instruction
PRIORITY NEED: EACH SCHOOL HAS ACCOUNTABILTY PLAN
Goals: Improved CATS % of prof/dist and NCLB scores thru monitoring and regular learning checks
MEASURE: *Subject specific learning checks to check for student progress
*Thinklink Math Assessments |  | current learning checks in progress
*Literacy First/Thinklink Reading Assessments |  | current learning checks in progress
Strategy/Activity (goal completion by 7/1/2010)
Each school will have an Accountability Plan that includes scheduled learning checks | I | fully implemented, continue refining
Schools will be monitored through the Districts monitoring plan and be given feedback | I,P | fully implemented, continue refining
Proficiency Quest will be used to create lesson plans | I,P | fully implemented, continue refining
COMPONENT: Math
PRIORITY NEED: IMPROVE MATH SCORES AND DECREASE # OF NOVICE AND APPRENTICE
Goal: Increase proficient/distinguished scores by 9% to 66% on KCCT Test, novice under 5% |  | current learning checks in progress
MEASURE: *Thinklink Math assessment at 70% or above by 7/1/2010 |  | current learning checks in progress
Strategy/Activity (goal completion by 7/1/2010)
*Use of Thinklink (3 time per yr min) and RTI assessments in math to ensure student progress | I,P | fully implemented, continue refining
*100% of all teachers will utilize research based math strategies to improve student comprehension | I,P | fully implemented, continue refining
*District will provide a Math/Language Arts Coach for Grades K-8 | I,P | fully implemented, continue refining
*District will provide the MAP assessment for grades K-1 in Math and Reading | I,P | fully implemented, continue refining
COMPONENT: Reading
PRIORITY NEED: IMP THE % OF PROF/DIST IN READING TO 69%, REDUCE NOVICE TO 6.33%
Goal: Dist total pro/dist above 69% on KCCT (Cats) Test , Novice 6.3% or lower |  | current learning checks in progress
MEASURE: *Use of Thinklink Reading, with assessment a min of 3 times per yr to monitor progress (82%) |  | current learning checks in progress
Strategy/Activity (goal completion by 7/1/2010)
*Teachers utilize research based pre-reading strategies to improve all phases of comprehension | I,P | fully implemented, continue refining
*Use of Thinklink (3 time per yr min) and RTI assessments in reading to ensure student progress | I,P | fully implemented, continue refining
*Reading teachers will collaborate with Reading Coaches to develop, implement and refine activities | I,P | fully implemented, continue refining
COMPONENT: Special Education
PRIORITY NEED: ADDITIONAL TIME NEEDED FOR TEACHER ALTERNATE PORT COMPLETION
Goal: Adaptive PE time will allow for improvement of stu motor skills while allowing for teacher portfolio time
MEASURE: *Improvement in both Math and Reading KCCT scores to 50% on each
Strategy/Activity (goal completion by 7/1/2010)
*Alt Portfolio (FMD) Teachers meet 1 time a month for peer teacher review | I | fully implemented, used regularly
*Adaptive PE time for students will allow for additional portfolio time and additional plan time 2x a week | I | fully implemented, used regularly
PRIORITY NEED: TARGETED PROCESS TO MONITOR SPECIFIC STUDENTS IN READING AND MATH
Goal: Each SPED Teacher will target two student's for reading and math and track/ensure their progress
MEASURE: *Improvement in both Math and Reading KCCT scores to 45% on each by 7/1/2010
Strategy/Activity (goal completion by 7/1/2010)
*Each SPED Teacher will complete AYP by ensuring success by targetred students and giving feedback | I | fully implemented, used regularly
PRIORITY NEED: A SUPPLEMENTAL ESL AT-RISK STUDENTS IN GRADES K-8
Goal: Utilize the Earobics foundations and connections web-based program K-8 for targeted students
MEASURE: *Improvement in both Math and Reading KCCT scores to 50% on each by 7/1/2010
Strategy/Activity (goal completion by 7/1/2010)
*Provide supplemental web-based reading enrichment program for grades K-3 | I | fully implemented, used regularly
*Provide additional PD for teachers using the supplemental reading program Earobics | I | fully implemented, used regularly