**Board Memo**

**DATE:** 6/9/2022

**AGENDA ITEM DETAILS:**

**School/Department**

RA Jones Middle School

**Product Vendor or Grant Issuer**

Change Order

**Product or Grant Name**

Change Order #1 for RA Jones Middle School Reno, BG 21-202

**Date/Term (Beginning and End Dates/Year)**

5/25/2022

**APPLICABLE BOARD POLICY:**

05.1

**DESCRIBE USE OF CONTRACT/PURCHASE/AGREEMENT**

This Change Order includes the following:

Proposal 5RR – Upon commencement of construction, it was determined that the 2005 drawings showed a separate 3” domestic water line and 6” fire protection line which doesn’t match the conditions – the lines were actually still combined in a single 6: line from the original construction. This change is for reworking the existing piping in the Mechanical Room to separate the fire line from the domestic water line and to move the meter out to the vault in the parking lot instead of inside the building.

ADD - $17,775.00

**FUNDING FOR PURCHASES AND OTHER REQUESTS:**

**Total Cost**

$17,775.00

**Funding Source**

Construction

 **\*If more than one funding source, list below along with amount or percent for each source**

Click or tap here to enter text.

**IF THIS IS A GRANT, ENTER AMOUNT TO BE AWARDED:**

Click or tap here to enter text.

**RECOMMENDATION:**

I recommend the Board approve the Change Order #1 for RA Jones Middle School Reno, BG 21-202, as presented.

**CONTACT PERSON: (submitter)**

Kim Best, Assistant Superintendent of Operations