## Estill HS 6-10-2022
Estill HS Phase 7
ESTILL COUNTY BOARD OF EDUCATION
BG-1 PROBABLE COSTS ITEMS
| OTHER OWNER INVOICES | [7 empty] | Codell Chg Order fees & Add'l services amounts |  |  |  |  | SITE SURVEY |  |  |  |  | BANK RATING
MUNIS # | [5 empty] | TOTAL CONST. | ARCHITECT/ENG | CM FEE |  | CONTINGENCY | A/E Change Order fees | FISCAL AGENT FEE | BOND DISCOUNT FEE |  | GEOTECHNICAL INVESTIGATIONS | COMMISSIONING | PRINTING | PLAN REVIEW |  | SPECIAL INSPECTIONS | ADVERTISING | EQUIPMENT/ FURNISHINGS | EQUIPMENT COMPUTERS | TOTAL
[6 empty] | 11749774 | 836560.59 | 402995 | 0 | 587488.7 | 0 | 100645.06 | 268600 | 44610 | 30390 | 25000 | 8900 | 9953 |  | 73550 | 0 | 100000 | 0 | 14238466.35
DATE
| COMPANY | SUBMITTED | INVOICE | INVOICE | INVOICE
| NAME | TO OWNER | DATE | NUMBER | AMOUNT
| KC Industries | 2022-02-15 | 2022-02-15 | 758-1300000370 | 22240 | [16 empty] | -22240
| Toadvine Enterprises | 2022-06-09 | 2022-05-18 | 8755 | 39558 | [16 empty] | -39558
| Vine and Branch | 2021-11-05 | 2021-11-02 | 3699 | 6203 | [16 empty] | -6203
| Vine and Branch | 2022-03-11 | 2022-03-08 | 3869 | 6203 | [16 empty] | -6203
| Vine and Branch | 2022-06-09 | 2022-05-18 | 3958 | 12135.75 | [16 empty] | -12135.75
| Pay Estimate 1 | 2021-10-06
| Contractors/Suppliers |  |  |  | 576201.26 | -576201.26
| Codell |  |  |  | 58814.06 |  |  | -58814.06
| Change Order 12-1 |  |  | 21620 | [5 empty] | -21620
|  |  | A/E fee | 1189.1 | [5 empty] | -1189.1 | 1189.1
|  |  | CM fee | 432.4 |  |  |  |  | 432.4 | -432.4
| Change Order 13-1 |  |  | 35231.14 | [5 empty] | -35231.14
|  |  | A/E fee | 1937.71 | [5 empty] | -1937.71 | 1937.71
|  |  | CM fee | 704.62 |  |  |  |  | 704.62 | -704.62
| Pay Estimate 2 | 2021-11-05
| Contractors/Suppliers |  |  |  | 582684.7 | -582684.7
| Codell |  |  |  | 35357.36 |  |  | -35357.36
| Pay Estimate 3 | 2021-12-03
| Contractors/Suppliers |  |  |  | 717104.71 | -717104.71
| Codell |  |  |  | 37916.47 |  |  | -37916.47
| Change Order 13-2 |  |  | 5120 | [5 empty] | -5120
|  |  | A/E fee | 281.6 | [5 empty] | -281.6 | 281.6
|  |  | CM fee | 102.4 |  |  |  |  | 102.4 | -102.4
| Change Order 15-1 |  |  | 184778.93 | [5 empty] | -184778.93
|  |  | A/E fee | 10162.84 | [5 empty] | -10162.84 | 10162.84
|  |  | CM fee | 3695.58 |  |  |  |  | 3695.58 | -3695.58
| rejected by board Change Order 15-2 |  |  | 0 | [5 empty] | 0
|  |  | A/E fee | 0 | [5 empty] | 0 | 0
|  |  | CM fee | 0 |  |  |  |  | 0 | 0
| Pay Estimate 4 | 2022-01-07
| Contractors/Suppliers |  |  |  | 571252.68 | -571252.68
| Codell |  |  |  | 23104 |  |  | -23104
| Pay Estimate 5 | 2022-02-09
| Contractors/Suppliers |  |  |  | 583089.46 | -583089.46
| Codell |  |  |  | 23060.83 |  |  | -23060.83
| Change Order 1-1 |  |  | 129883 | [5 empty] | -129883
|  |  | A/E fee | 7143.57 | [5 empty] | -7143.57 | 7143.57
|  |  | CM fee | 2597.66 |  |  |  |  | 2597.66 | -2597.66
| Change Order 7-1 |  |  | 40509.9 | [5 empty] | -40509.9
|  |  | A/E fee | 2228.04 | [5 empty] | -2228.04 | 2228.04
|  |  | CM fee | 810.2 |  |  |  |  | 810.2 | -810.2
| Change Order 8-1 |  |  | 5035 | [5 empty] | -5035
|  |  | A/E fee | 276.93 | [5 empty] | -276.93 | 276.93
|  |  | CM fee | 100.7 |  |  |  |  | 100.7 | -100.7
| Change Order 9-1 |  |  | 10279 | [5 empty] | -10279
|  |  | A/E fee | 565.35 | [5 empty] | -565.35 | 565.35
|  |  | CM fee | 205.58 |  |  |  |  | 205.58 | -205.58
| Change Order 10-1 |  |  | 3550 | [5 empty] | -3550
|  |  | A/E fee | 195.25 | [5 empty] | -195.25 | 195.25
|  |  | CM fee | 71 |  |  |  |  | 71 | -71
| Change Order 13-3 |  |  | 21672.08 | [5 empty] | -21672.08
|  |  | A/E fee | 1191.96 | [5 empty] | -1191.96 | 1191.96
|  |  | CM fee | 433.44 |  |  |  |  | 433.44 | -433.44
| Change Order 15-3 |  |  | 366676.94 | [5 empty] | -366676.94
|  |  | A/E fee | 20167.23 | [5 empty] | -20167.23 | 20167.23
|  |  | CM fee | 7333.54 |  |  |  |  | 7333.54 | -7333.54
| Change Order 3-1 |  |  | 0 | [5 empty] | 0
| Change Order 5-1 |  |  | 0 | [5 empty] | 0
| Change Order 11-1 |  |  | 0 | [5 empty] | 0
Pay Estimate 6
| Contractors/Suppliers |  |  |  | 637545.99 | -637545.99
| Codell |  |  |  | 24055 |  |  | -24055
Pay Estimate 7
| Contractors/Suppliers |  |  |  | 514095.97 | -514095.97
| Codell |  |  |  | 21898 |  |  | -21898
Pay Estimate 8
| Contractors/Suppliers |  |  |  | 1167302.56 | -1167302.56
| Codell |  |  |  | 28327.86 |  |  | -28327.86
| Change Order 1-2 |  |  | 1380 | [5 empty] | -1380
|  |  | A/E fee | 0 | [5 empty] | 0
|  |  | CM fee | 0 | [5 empty] | 0
| Change Order 12-2 |  |  | 101739.61 | [5 empty] | -101739.61
|  |  | A/E fee | 5595.69 | [5 empty] | -5595.69 | 5595.69
|  |  | CM fee | 2034.79 |  |  |  |  | 2034.79 | -2034.79
| Change Order 13-4 |  |  | 5044 | [5 empty] | -5044
|  |  | A/E fee | 277.42 | [5 empty] | -277.42 | 277.42
|  |  | CM fee | 100.88 |  |  |  |  | 100.88 | -100.88
| Change Order 15-4 |  |  | 13800 | [5 empty] | -13800
|  |  | A/E fee | 759 | [5 empty] | -759 | 759
|  |  | CM fee | 276 |  |  |  |  | 276 | -276
Pay Estimate 9
| Contractors/Suppliers |  |  |  | 1385326.23 | -1385326.23
| Codell |  |  |  | 36364.4 |  |  | -36364.4
TOTALS: | [5 empty] | 5015170.44 | 836560.59 | 114097.02 | 18898.79 | -429701.38 | 51971.69 | 100645.06 | 268600 | 44610 | 30390 | 25000 | 8900 | 9953 | 0 | 73550 | 0 |  | 0 | 14238466.35
| Total Change Orders and Change Order Fees to Date: |  |  | 1017190.08
|  | minus a/e fee |  | -51971.69
|  | minus CM fee |  | -18898.79
946319.6
Toadvine/vine and Branch PO's
$6,230.00
$16,181.00
$39,558.00

## Estill HS
Estill HS Phase 7
ESTILL COUNTY BOARD OF EDUCATION
BG-1 PROBABLE COSTS ITEMS
| OTHER OWNER INVOICES | [7 empty] | Codell Chg Order fees & Add'l services amounts |  |  |  |  | SITE SURVEY |  |  |  |  | BANK RATING
MUNIS # | [5 empty] | TOTAL CONST. | ARCHITECT/ENG | CM FEE |  | CONTINGENCY | A/E Change Order fees | FISCAL AGENT FEE | BOND DISCOUNT FEE |  | GEOTECHNICAL INVESTIGATIONS | COMMISSIONING | PRINTING | PLAN REVIEW |  | SPECIAL INSPECTIONS | ADVERTISING | EQUIPMENT/ FURNISHINGS | EQUIPMENT COMPUTERS | TOTAL
[6 empty] | 11749774 | 836560.59 | 402995 | 0 | 587488.7 | 0 | 100645.06 | 268600 | 44610 | 30390 | 25000 | 8900 | 9953 |  | 73550 | 0 | 100000 | 0 | 14238466.35
DATE
| COMPANY | SUBMITTED | INVOICE | INVOICE | INVOICE
| NAME | TO OWNER | DATE | NUMBER | AMOUNT
| KC Industries | 22-15-2022 | 2022-02-15 | 758-1300000370 | 22240 | [16 empty] | -22240
| Vine and Branch | 2021-11-05 | 2021-11-02 | 3699 | 6203 | [16 empty] | -6203
| Vine and Branch | 2022-03-11 | 2022-03-08 | 3869 | 6203 | [16 empty] | -6203
| Pay Estimate 1 | 2021-10-06
| Contractors/Suppliers |  |  |  | 576201.26 | -576201.26
| Codell |  |  |  | 58814.06 |  |  | -58814.06
| Change Order 12-1 |  |  | 21620 | [5 empty] | -21620
|  |  | A/E fee | 1189.1 | [5 empty] | -1189.1 | 1189.1
|  |  | CM fee | 432.4 |  |  |  |  | 432.4 | -432.4
| Change Order 13-1 |  |  | 35231.14 | [5 empty] | -35231.14
|  |  | A/E fee | 1937.71 | [5 empty] | -1937.71 | 1937.71
|  |  | CM fee | 704.62 |  |  |  |  | 704.62 | -704.62
| Pay Estimate 2 | 2021-11-05
| Contractors/Suppliers |  |  |  | 582684.7 | -582684.7
| Codell |  |  |  | 35357.36 |  |  | -35357.36
| Pay Estimate 3 | 2021-12-03
| Contractors/Suppliers |  |  |  | 717104.71 | -717104.71
| Codell |  |  |  | 37916.47 |  |  | -37916.47
| Change Order 13-2 |  |  | 5120 | [5 empty] | -5120
|  |  | A/E fee | 281.6 | [5 empty] | -281.6 | 281.6
|  |  | CM fee | 102.4 |  |  |  |  | 102.4 | -102.4
| Change Order 15-1 |  |  | 184778.93 | [5 empty] | -184778.93
|  |  | A/E fee | 10162.84 | [5 empty] | -10162.84 | 10162.84
|  |  | CM fee | 3695.58 |  |  |  |  | 3695.58 | -3695.58
| rejected by board Change Order 15-2 |  |  | 0 | [5 empty] | 0
|  |  | A/E fee | 0 | [5 empty] | 0 | 0
|  |  | CM fee | 0 |  |  |  |  | 0 | 0
| Pay Estimate 4 | 2022-01-07
| Contractors/Suppliers |  |  |  | 571252.68 | -571252.68
| Codell |  |  |  | 23104 |  |  | -23104
| Pay Estimate 5 | 2022-02-09
| Contractors/Suppliers |  |  |  | 583089.46 | -583089.46
| Codell |  |  |  | 23060.83 |  |  | -23060.83
| Change Order 1-1 |  |  | 129883 | [5 empty] | -129883
|  |  | A/E fee | 7143.57 | [5 empty] | -7143.57 | 7143.57
|  |  | CM fee | 2597.66 |  |  |  |  | 2597.66 | -2597.66
| Change Order 7-1 |  |  | 40509.9 | [5 empty] | -40509.9
|  |  | A/E fee | 2228.04 | [5 empty] | -2228.04 | 2228.04
|  |  | CM fee | 810.2 |  |  |  |  | 810.2 | -810.2
| Change Order 8-1 |  |  | 5035 | [5 empty] | -5035
|  |  | A/E fee | 276.93 | [5 empty] | -276.93 | 276.93
|  |  | CM fee | 100.7 |  |  |  |  | 100.7 | -100.7
| Change Order 9-1 |  |  | 10279 | [5 empty] | -10279
|  |  | A/E fee | 565.35 | [5 empty] | -565.35 | 565.35
|  |  | CM fee | 205.58 |  |  |  |  | 205.58 | -205.58
| Change Order 10-1 |  |  | 3550 | [5 empty] | -3550
|  |  | A/E fee | 195.25 | [5 empty] | -195.25 | 195.25
|  |  | CM fee | 71 |  |  |  |  | 71 | -71
| Change Order 13-3 |  |  | 21672.08 | [5 empty] | -21672.08
|  |  | A/E fee | 1191.96 | [5 empty] | -1191.96 | 1191.96
|  |  | CM fee | 433.44 |  |  |  |  | 433.44 | -433.44
| Change Order 15-3 |  |  | 366676.94 | [5 empty] | -366676.94
|  |  | A/E fee | 20167.23 | [5 empty] | -20167.23 | 20167.23
|  |  | CM fee | 7333.54 |  |  |  |  | 7333.54 | -7333.54
| Change Order 3-1 |  |  | 0 | [5 empty] | 0
| Change Order 5-1 |  |  | 0 | [5 empty] | 0
| Change Order 11-1 |  |  | 0 | [5 empty] | 0
Pay Estimate 6
| Contractors/Suppliers |  |  |  | 637545.99 | -637545.99
| Codell |  |  |  | 24055 |  |  | -24055
Pay Estimate 7
| Contractors/Suppliers |  |  |  | 514095.97 | -514095.97
| Codell |  |  |  | 21898 |  |  | -21898
TOTALS: | [5 empty] | 7567799.23 | 836560.59 | 178789.28 | 16487.12 | -298693.99 | 45339.58 | 100645.06 | 268600 | 44610 | 30390 | 25000 | 8900 | 9953 | 0 | 73550 | 0 |  | 0 | 14238466.35
| Total Change Orders and Change Order Fees to Date: |  |  | 886182.69
|  | minus a/e fee |  | -45339.58
|  | minus CM fee |  | -16487.12
824355.99
Toadvine/vine and Branch PO's
$6,230.00
$16,181.00
$39,558.00