Garrard County Board of Education Meeting

September 15, 2022

Construction Update

GCHS Project

- Pre-Bid Meeting @ GCHS on Tuesday, October 4 @ 10:00 a.m.

- Bid Opening @ GCHS on Tuesday, October 18 @ 2:00 p.m. – Library

- Possible Bid selection – Thursday, October 20 @ Board Meeting @ GCHS

- Groundbreaking – November – date to be determined

- Fields & Floor Meeting with coaches – Tuesday, September 20 @ GCHS

- Aesthetics – Building & Interior finishes – GCHS/District/Board Committee to recommend to the board

Other Projects

- LES – Tile near completion – additional work over the breaks to complete work

- LES – Windows – seeking bids – currently no vendors willing to provide estimates

- ATC – Vestibule work planned for Fall Break

- GEC – Dual Vestibule work planned for Christmas Break

- GMS – Gathering estimates on canopy replacements, sidewalk replacements, front area removal, asphalt replacement

- Elementary Playgrounds – Supply chain issues prevented work this summer – Current estimates are work beginning in mid-October. Equipment is scheduled to leave the factory on October 27. Anticipated 10-12 week job.