**Board Memo**

**DATE:** 10/13/2022

**AGENDA ITEM DETAILS:**

**School/Department**

Boone County High School

**Product Vendor or Grant Issuer**

Change Order

**Product or Grant Name**

Change Order #9 for Boone County High Reno, BG 20-183

**Date/Term (Beginning and End Dates/Year)**

9/28/2022

**APPLICABLE BOARD POLICY:**

05.1

**DESCRIBE USE OF CONTRACT/PURCHASE/AGREEMENT**

This Change Order includes the following:

Proposal 55R3 – This is for undercutting, removing and stabilizing the existing unsuitable soils in the parking lot area where soft conditions were found prior to paving.

ADD - $14,640.00

Proposal 56 – During construction it was determined that a smaller, exposed junction box was available, and for a minimal cost, could be swapped out with the cheaper one that was specified. This allows for a smaller, thinner appearance.

ADD - $3,022.00

Proposal 57 – This is for adjustments in the Automatic Transfer Switch location as in the construction, with the final vendor that was specified, some additional clearance was required.

ADD - $4,687.00

Proposal 58 – Building Code official required additional fire alarm pull station devices to enhance the accessibility to a device.

ADD - $3,643.00

Proposal 60R – The building official requested an additional guardrail at one location along the edge of the roof as an additional safety measure when working on the rooftop equipment.

ADD - $2,639.00

**FUNDING FOR PURCHASES AND OTHER REQUESTS:**

**Total Cost**

$28,631.00

**Funding Source**

Construction

 **\*If more than one funding source, list below along with amount or percent for each source**

Click or tap here to enter text.

**IF THIS IS A GRANT, ENTER AMOUNT TO BE AWARDED:**

Click or tap here to enter text.

**RECOMMENDATION:**

I recommend the Board approve the Change Order #9 for Boone County High School Reno, BG 20-183, as presented.

**CONTACT PERSON: (submitter)**

Kim Best, Assistant Superintendent of Operations