**Board Memo**

**DATE:** 12/8/2022

**AGENDA ITEM DETAILS:**

**School/Department**

Boone County Schools

**Product Vendor or Grant Issuer**

Change Order

**Product or Grant Name**

Change Order #1 for Boone County Schools Paving 2022, BG 22-321

**Date/Term (Beginning and End Dates/Year)**

11/17/2022

**APPLICABLE BOARD POLICY:**

05.1

**DESCRIBE USE OF CONTRACT/PURCHASE/AGREEMENT**

This Change Order includes the following:

Allowance No. 1 – Existing full depth asphalt required less replacement than what was included in the bid.

DEDUCT - $14,250.00

Allowance No. 2 – Existing concrete sidewalks required less replacement than what was included in the bid.

DEDUCT - $11,600.00

Proposal 1R – Replace three existing storm boxes which made sense while the contractor was on-site.

ADD - $20,400.00

Proposal 3R – Replace two existing storm boxes which made sense while the contract was on-site.

ADD - $13,600.00

Proposal 4 – This is a credit for additional work that was provided in the bid to help reduce ponding water from the hillside at Stephens Elementary. It was determined some of the prior remediation efforts have been working and this work can be credited back to the Owner.

DEDUCT - $12,500.00

**FUNDING FOR PURCHASES AND OTHER REQUESTS:**

**Total Cost**

DEDUCT $4,350.00

**Funding Source**

Construction

 **\*If more than one funding source, list below along with amount or percent for each source**

Click or tap here to enter text.

**IF THIS IS A GRANT, ENTER AMOUNT TO BE AWARDED:**

Click or tap here to enter text.

**RECOMMENDATION:**

I recommend the Board approve the Change Order #1 for Boone County Schools Paving 2022, BG 22-321,

as presented.

**CONTACT PERSON: (submitter)**

Kim Best, Assistant Superintendent of Operations