**Board Memo**

**DATE:** 12/8/2022

**AGENDA ITEM DETAILS:**

**School/Department**

Steeplechase Elementary School

**Product Vendor or Grant Issuer**

Change Order

**Product or Grant Name**

Change Order #12 for Steeplechase Elementary School BP #2, BG 19-078

**Date/Term (Beginning and End Dates/Year)**

11/17/2022

**APPLICABLE BOARD POLICY:**

05.1

**DESCRIBE USE OF CONTRACT/PURCHASE/AGREEMENT**

This change order is a result of additional costs incurred by the contractor due to significant Covid delays during the construction of Steeplechase Elementary relative to labor quarantines and manufacturer shipping delays.

ADD - $88,864.00

**FUNDING FOR PURCHASES AND OTHER REQUESTS:**

**Total Cost**

$88,864.00

**Funding Source**

Construction

**\*If more than one funding source, list below along with amount or percent for each source**

Click or tap here to enter text.

**IF THIS IS A GRANT, ENTER AMOUNT TO BE AWARDED:**

Click or tap here to enter text.

**RECOMMENDATION:**

I recommend the Board approve the Change Order #12 for Steeplechase Elementary School BP #2, BG 19-078, as presented.

**CONTACT PERSON: (submitter)**

Kim Best, Assistant Superintendent of Operations