Continuous School Improvement

Planning Cycle

Goal Builder

Phase 3 (Nov. 1-Jan. 1)

Plotting the Course

Establishing Goals, Objectives, Strategies and Activities

AND

Phase 4 (Jan. 1-Dec. 31)

Making District/School Improvement Continuous

Progress Monitoring and Evaluation

## IMPORTANT NOTE:

This workbook has been adapted from the original Goal Building Template located on KDE’s Comprehensive Improvement Planning for Schools and Districts webpage (https://education.ky.gov/school/csip/Pages/default.aspx).

This adaptation will allow for the document to serve as a “one-stop” location for both the plan and the continuous monitoring and evaluation during this year’s implementation period.  The planning of goals, objectives, strategies and activities that are required of the Continuous Improvement Cycle - Phase 3 process look just as they do in the original template.  The adaptation will allow for support in the Phase 4 process of continuous monitoring and evaluation using the 30-60-90 day planning format. Additional planning and quality tools for continuous improvement can be located on the Continuous Improvement for Gap Closure webpage (https://education.ky.gov/school/stratclsgap/Pages/default.aspx).

# Comprehensive School Improvement Plan (CSIP)

## Rationale

​School improvement efforts are a collaborative process involving multiple stakeholders. Through the improvement planning process, leaders focus on priority needs, funding, and closing achievement gaps among identified subgroups of students. When implemented with fidelity, the Comprehensive School Improvement Plan (CSIP) cultivates an environment that promotes student growth and achievement.

While the focus of continuous improvement is student performance, the work must be guided by the aspects of teaching and learning that affect performance. An effective improvement process should address the contributing factors creating the learning environment (inputs) and the performance data (outcomes). Through the Needs Assessment for Schools, priorities were identified and processes, practices, and/or conditions were chosen for focus. This goal building template will assist your improvement team to address those priorities and outline your targets and the activities intended to produce the desired changes. Progress monitoring details will ensure that your plan is being reviewed regularly to determine the success of each strategy.

Please note that the objectives (short-term targets) set by your school under the Achievement Gap section of this planning template will be used by the district’s superintendent to determine whether or not your school met its targets to reduce the gap in student achievement for any student group for two consecutive years as required by KRS 158.649. Likewise, operational definitions for each required planning component can be found on page 2 of the planning template.

For those schools operating a Title I Schoolwide Program, this plan meets the requirements of Section 1114 of the Every Student Succeeds Act as well as state requirements under 703 KAR 5:225. No separate Schoolwide Program Plan is required.

Operational Definitions
Goal: Long-term three to five year targets based on the required school level goals. Elementary/middle schools must have goals for proficiency, separate academic indicator, achievement gap, and growth. High schools must have goals for proficiency, separate academic indicator, achievement gap, graduation rate, and transition readiness. Long-term targets should be informed by The Needs Assessment for Schools.

Objective: Short-term target to be attained by the end of the current academic year. There can be multiple objectives for each goal.

Strategy: An approach to systematically address the process, practice, or condition that the school will focus its efforts upon in order to reach its goals or objectives. There can be multiple strategies for each objective.  The strategy can be based upon Kentucky’s six (6) Key Core Work Processes listed below or another established improvement approach (i.e. Six Sigma, Shipley, Baldridge, etc.).

Activity: Actionable steps used to deploy the chosen strategy. There can be multiple activities for each strategy.

Key Core Work Processes: A series of processes identified by the Kentucky Department of Education that involve the majority of an organization’s workforce and relate to its core competencies. These are the factors that determine an organization’s success and help it prioritize areas for growth.

| - KCWP 1: Design and Deploy Standards - KCWP 2: Design and Deliver Instruction - KCWP 3: Design and Deliver Assessment Literacy | - KCWP 4: Review, Analyze and Apply Data - KCWP 5: Design, Align and Deliver Support - KCWP 6: Establishing Learning Culture and Environment |
| --- | --- |

Measure of Success: Criteria that shows the impact of the work. The measures may be quantitative or qualitative, but are observable in some way.

Progress Monitoring: Process used to assess the implementation of the plan, the rate of improvement, and the effectiveness of the plan. Should include timelines and responsible individuals.

Funding: Local, state, or federal funds/grants used to support (or needed to support) the improvement initiative.

## Requirements for Building an Improvement Plan

- The required goals for elementary/middle schools include the following:

  - State Assessment Results in reading and mathematics

  - State Assessment Results in science, social studies and writing

  - Achievement Gap

  - English Learner Progress

  - Quality of School Climate and Safety

- The required goals for high schools include the following:

  - State Assessment Results in reading and mathematics

  - State Assessment Results in science, social studies and writing

  - Achievement Gap

  - English Learner Progress

  - Quality of School Climate and Safety

  - Postsecondary Readiness

  - Graduation Rate

## Explanations/Directions

| Goal: Schools should determine long-term goals that are three to five year targets for each required school level indicator. Elementary/middle schools must address proficiency, separate academic indicator, achievement gap, and growth. High schools must address proficiency, separate academic indicator, achievement gap, graduation rate, and transition readiness. Long-term targets should be informed by The Needs Assessment for Schools. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective | Strategy | Activities | Measure of Success | Progress Monitoring | Funding |  |
| Schools should determine short-term objectives to be attained by the end of the current academic year. There can be multiple objectives for each goal. | Describe your approach to systematically address a process, practice, or condition that was identified as a priority during the Needs Assessment for Schools. There can be multiple strategies for each objective. The strategy can be based upon Kentucky’s six (6) Key Core Work Processes or another established improvement approach (i.e. Six Sigma, Shipley, Baldridge, etc.). | Describe the actionable steps that will occur to deploy the chosen strategy. There can be multiple activities for each strategy. | List the criteria that will gauge the impact of your work. The measures may be quantitative or qualitative but are observable in some way. Consider measures of input as well as outcomes for both staff and students. | Describe the process used to assess the implementation of the plan, the rate of improvement, and the effectiveness of the plan. Your description should include the artifacts to be reviewed, specific timelines, and responsible individuals. | List the specific federal, state, or local funding source(s) used to support each improvement initiative. If your school is a recipient of Title I, Part A funds, your CSIP serves as your annual plan and must indicate how Title I funds are utilized to carry out the planned activities. |  |

## Goal 1: State Assessment Results in reading and mathematics

| Goal 1 (State your reading and math goal.): By Spring of 2025, 64% of all students will achieve at or above grade level in reading and 63% in math as measured by iReady. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective | Strategy | Activities | Measure of Success | Progress Monitoring | Funding |  |
| Objective 1: By Spring of 2023, the percentage of students performing on grade level in Reading will increase by 5% by EOY Tier 1 (“at or above grade level”) as measured by iReady. R - 49% - 54% | KCWP1: Design and Deploy Standards | Complete phases 2, 3 and 4 of the curriculum development process. Professional learning on how to use the Model Curriculum Framework to develop a high quality district ELA curriculum. Review all ELA instructional resources making sure the district is using HQIRs. | District articulated ELA/Math learning philosophy. Professional learning documentation. Meeting agendas and results. | 30-60-90 day planning | Title I – iReady Title II – Stipends |  |
|  |  | Coaching for instructional coaches | Coaching plans, scheduled activities | 30-60-90 day planning | Title I and II – IC salaries and travel |  |
|  | KCWP 2: Design and deliver instruction | Implementation of instructional protocol | Professional Learning Documentation Curriculum and planning documents. | Principal Walk through data, unit plans/anchor charts and Observations | Title II Reading: |  |
|  |  | ELA: Implement Phonics and Phonemic Awareness programs | Walk through data with OVEC Professional Learning with OVEC | Principal, Coach and OVEC walk through data and coaching meetings |  |  |
| Objective 2 By Spring of 2023, the percentage of students performing on grade level in Math will increase by 5% by EOY Tier 1 (“at or above grade level”) as measured by iReady. M - 48% - 53% | KCWP 1: Design and deploy standards through vertical alignment of standards. | Complete phases 1, 2, 3 and 4 of the curriculum development process. Professional learning on how to use the Model Curriculum Framework to develop a high quality district Math curriculum. Review all Math instructional resources making sure the district is using HQIRs. | District articulated ELA/Math learning philosophy. Professional learning documentation. Meeting agendas and results. | 30-60-90 day planning | Title I – iReady Title II – Stipends |  |
|  |  | Coaching for instructional coaches | Coaching plans, scheduled activities | 30-60-90 day planning | Title I and II – IC salaries and travel |  |
|  | KCWP 2: Design and deliver instruction | Implementation of instructional protocol | Professional Learning Documentation Curriculum and planning documents. | Principal Walk through data, unit plans/anchor charts and Observations | Title II Reading: |  |

## Goal 2: State Assessment Results in science, social studies and writing

| Goal 2 (State your science, social studies, and writing goal.): By Spring of 2025, 60 % of students will demonstrate proficiency in writing as measured by schoolwide established grade level benchmarks. By Spring of 2025, 48% of students will demonstrate proficiency in social studies as measured by the KAS. By Spring of 2025, 37% of students will demonstrate proficiency in science as measures by the KAS. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective | Strategy | Activities | Measure of Success | Progress Monitoring | Funding |  |
| Objective 1: By Spring of 2023, 45% of all students will demonstrate proficiency in writing as measured by schoolwide established grade level benchmarks. | KCWP 2: Refine our system for delivering writing instruction in order to ensure that all students are developing toward proficiency as writers. | The school writing team (composed of school administration and teachers) will meet bimonthly. The team will determine a timeline to review writing samples. Throughout the year, the team will also decide appropriate adjustments and/or next steps needed in order to continuously improve. This work will be supported by KDE Continuous Improvement Coaches | Non-Negotiable Writing Behaviors Student Writing Samples Meeting Agenda and Minutes | 30-60-90 Day Plan |  |  |
| Objective 2 By Spring of 2023, Increase Social Studies scores proficient and distinguished from 33% to 37% according to KAS. | KCWP 1: Design and Deploy Standards | Meet with Team Leads to discuss and plan for standards deconstruction | Meeting Agenda and Minutes | 30-60-90 Day Plan |  |  |
| Objective 3 By Spring of 2023, Increase Science scores in proficient and distinguished from 22% to 27% according to KAS. | KCWP 1: Design and Deploy Standards | Meet with Team Leads to discuss and plan for standards deconstruction | Meeting Agenda and Minutes | 30-60-90 Day Plan |  |  |

## Goal 3: Achievement Gap

## KRS 158.649 requires the school-based decision making (SBDM) council, or the principal if no council exists, to set the school's yearly targets for eliminating any achievement gap. The targets should be established with input from parents, faculty, and staff and submitted to the superintendent for consideration and the local board of education for adoption. In addition to being a statutory requirement, intentionally focusing on the achievement gaps that exist among a school’s underserved student populations is also a vital component of the continuous improvement process. Schools should use a variety of measures and analysis when conducting its review of its achievement gaps, including a review of the school’s climate and culture. Schools are not required to establish long term achievement gap goals; however, schools must establish yearly targets (objectives).

| Objective | Strategy | Activities | Measure of Success | Progress Monitoring | Funding |
| --- | --- | --- | --- | --- | --- |
| Objective 1 From Fall of 2022 to Spring of 2023, 4% of students in the reported gap groups of “Student with Disabilities” will increase to 20% achieve at or above grade level in reading as measured by iReady. | KCWP 4: Review, Analyze and Apply Data Results | A Professional Learning Committee will be formed and meet monthly. The purpose of this team is to meet to discuss data, resources and strategies to meet the needs of students. | Meeting Agenda and Minutes | 30-60-90 Day Plan |  |
| Objective 2 From Fall of 2022 to Spring of 2023, 6% of students in the reported gap groups of “Student with Disabilities” will increase to 22% achieve at or above grade level in reading as measured by iReady. | KCWP 4: Review, Analyze and Apply Data Results | A Professional Learning Committee will be formed and meet monthly. The purpose of this team is to meet to discuss data, resources and strategies to meet the needs of students. | Meeting Agenda and Minutes | 30-60-90 Day Plan |  |

## Goal 4: English Learner Progress

| Goal 4 (State your English Learner goal.): By Spring of 2025, 100% of English Learners will increase at least one category (.5) per year as measured by ACCESS. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective | Strategy | Activities | Measure of Success | Progress Monitoring | Funding |  |
| By Spring of 2023, 100% of English Learners will increase at least one category (.5) per year as measured by ACCESS. | KCWP 2: Design and Deliver Instruction | Work with the EL Director to provide training and resources for the assistants working with EL students. | Meeting Agendas and Minutes | 30-60-90 Day Plan |  |  |

## Goal 5: Quality of School Climate and Safety

| Goal 5 (State your climate and safety goal.): By Spring of 2024, we will increase the increase the number of teachers who feel extremely positive and quiet positive from 26% to 50%. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objective | Strategy | Activities | Measure of Success | Progress Monitoring | Funding |  |
| Objective 1 By Spring of 2023 we will increase the number of teachers who feel extremely positive and quiet positive from 26% to 35%. | KCWP 6 Learning Culture and Environment | The Culture team will ask the staff what the survey meant to them and discuss and determine strategies to increase positivity. | Survey | Working Conditions Survey 30-60-90 Day Plan |  |  |

## Special Considerations for Targeted Support and Improvement (TSI) including Additional Targeted Support and Improvement (ATSI) Schools

TSI schools (including ATSI schools) must embed their subgroup(s) plan for improvement within their CSIPs. TSI stakeholders, including the principal and other school leaders, teachers, and parents, should carefully consider what must be done to ensure the subgroup(s) perform(s) at high levels in the state accountability system. In addition to identifying strategies and activities within the CSIP that address the specific needs of underperforming groups, provide narrative information regarding the additional requirements for TSI schools in the following chart:

Components of Turnaround Leadership Development and Support:

Consider: How will you ensure that school leadership has or develops the skills and disposition to achieve accelerated, meaningful, and sustainable increases in student achievement for underperforming subgroups? Response: The school leadership will monitor the plan and collaborate with others. Leadership will work with the District office, KDE continuous improvement coaches and OVEC. The principal is on the ELA Curriculum Committee and will be on the math committee when it begins. The 30-60-90 day plan will be reviewed monthly at SBDM meetings.

Identification of Critical Resources Inequities:

Consider: Describe the process used to review the allocation and use of resources (people, time, and money), any resource inequities that were identified that may contribute to underperformance, and how identified resource inequities will be addressed. Response: Special Education teachers professional learning mirrored the expectations of general education teachers. They are allocated the same amount of classroom money as the gen ed. OVEC provided training specifically for Special Education teachers. Our teachers took advantage of those opportunities and were paid a stipend to do so. This extra pd will help them grow.

Additional Actions That Address the Causes of Consistently Underperforming Subgroups of Students

Consider: Describe the process used to review the learning culture related to your targeted subgroup(s) and any additional actions that were determined to address the causes of underperformance. Response: The master schedule allows time for special education students to be in reading and math groups with their classroom teacher as well as resource time with their special education teacher. If students are missing any core times their special education teacher is responsible for making up that content. In collaboration with our Special Education Director we will have monthly PLC meetings for the special education team.

Targeted Subgroups and Evidence-Based Interventions:

Consider: Identify the areas of need revealed by the analysis of academic and non-academic data that will be addressed through CSIP activities for your targeted subgroup(s). What evidence-based practice(s) will the school incorporate that specifically targets the subgroup(s) achievement that contributed to the TSI identification? How will we monitor the evidence-based practice to ensure it is implemented with fidelity? Response: Hattie, J. (2012). Visible Learning for Teachers: Maximizing Impact on Learning. Routledge: New York, NY. Gallatin County Lower Elementary Schools have been trained in Collective Teacher Efficacy. With the collaboration of Team Leads and the District Leadership and OVEC we decided t implement the CTE strategy. CTE refers to staff shared beliefs that through collective action, thy can influence positive outcomes. This is an effect size of 1.57 which is the number one ranking factor of influencing students achievement. It is three times more powerful than and predictive of student achievement than socioeconomic status. There are six enabling conditions and we will focus on a few of them. The first one is ensuring that we have teacher input on important school wide decisions. The second on is to increase teachers knowledge about one another’s work. We will provide more opportunities for staff to observe each other and be peer mentors. The last one is to continue to work on building an effective systems of intervention. We are working to create a MTSS manual that includes documentation for interventions. We believe the ESSA Level is a 1.

## TSI/ATSI Evidence-based Practices

The Every Student Succeeds Act (2015) created new expectations for evidence-based decision making at school and district levels. More specific information regarding evidence-based practices and requirements can be found on the Kentucky Department of Education’s Evidence-based Practices website. While evidence documentation in the CSIP is only required for schools identified for Targeted Support and Improvement (TSI) including Additional Targeted Support and Improvement (ATSI) and Comprehensive Support and Improvement (CSI), KDE encourages all school leaders to review evidence related to new programs, practices, or interventions being implemented in the school. In addition to documenting the evidence below, TSI, ATSI and CSI schools are expected to upload a description of their evidence review process, the findings of their evidence review, and a discussion of the local implications into eProve. Specific directions regarding the documentation requirements can be found in the “Compliance Requirements” resource available on KDE’s Evidence-based Practices website.

Complete the table below to document the evidence that supports the Activities outlined in this plan. Additional rows may be added to accommodate additional pieces of evidence.

| Evidence-based Activity | Evidence Citation | Uploaded in eProve |
| --- | --- | --- |
| Train staff to implement inductive teaching strategies. | Hattie, J. (2009). Visible Learning: a synthesis of over 800 meta-analyses relating to achievement. Routledge: New York, NY. | ☒ |
| Collective Teacher Efficacy – implement procedures for professional learning communities to increase special needs students | Hattie, J. (2012). Visible Learning for Teachers: Maximizing Impact on Learning. Routledge: New York, NY. | ☐ |
|  |  | ☐ |
|  |  | ☐ |
|  |  | ☐ |