DECISION PAPER

TO: MEMBERS OF THE NELSON COUNTY BOARD OF EDUCATION

FROM: Charles Thompson, Construction and Maintenance Liaison/DPP

CC: Dr. Janice Lantz

SUBJECT: Change Order #7 for Thomas Nelson High School

DATE: June 15, 2010

ISSUE: More rock than anticipated was excavated at the project site. To reduce cost an on site location, rather than to haul off, was found for materials. At that site a catch basin was in place that had to be raised. Kelsey Construction, LLC can provide all labor and materials to raise catch basin for $453.37.

RECOMMENDATION: Approve Change Order #7 for Thomas Nelson High School.

RECOMMENDED MOTION: I move that the Nelson County Board of Education approve Change Order #7 for Thomas Nelson High School.